## Checklists
Building | Area | Inspection Type | Progress | Status | Start Date | Finish Date | Completion Date | 25% Target | 25% Completed | 25% Link | 50% Target | 50% Completed | 50% Link | 75% Target | 75% Completed | 75% Link | 100% Target | 100% Completed | 100% Link | Form Link
RPL10 | 10CMDF1 | L2 – Infrastructure | 0 | Upcoming | 04/24/2026 | 04/30/2026 |  |  |  |  | 04/27/2026 |  | Link |  |  |  | 04/30/2026 |  | Link | Link
RPL10 | 10CMDF1 | L3 – ISP | 0 | Upcoming | 05/01/2026 | 05/06/2026 |  |  |  |  | 05/04/2026 |  | Link |  |  |  | 05/06/2026 |  | Link | Link
RPL10 | 10CMDF1 | L3 – OSP | 0 | Upcoming | 05/05/2026 | 05/08/2026 |  |  |  |  | 05/07/2026 |  | Link |  |  |  | 05/08/2026 |  | Link | Link
RPL10 | 10CMDF1 | L4 – Network | 0 | Upcoming | 05/11/2026 | 05/15/2026 |  |  |  |  | 05/13/2026 |  | Link |  |  |  | 05/15/2026 |  | Link | Link
RPL10 | 10CMDF1 | L5 – Punchlist | 0 | Not Started | [15 empty] | Link
RPL10 | 10CMDF2 | L2 – Infrastructure | 0 | Upcoming | 04/24/2026 | 04/30/2026 |  |  |  |  | 04/27/2026 |  | Link |  |  |  | 04/30/2026 |  | Link | Link
RPL10 | 10CMDF2 | L3 – ISP | 0 | Upcoming | 05/01/2026 | 05/07/2026 |  |  |  |  | 05/04/2026 |  | Link |  |  |  | 05/07/2026 |  | Link | Link
RPL10 | 10CMDF2 | L3 – OSP | 0 | Upcoming | 05/05/2026 | 05/11/2026 |  |  |  |  | 05/08/2026 |  | Link |  |  |  | 05/11/2026 |  | Link | Link
RPL10 | 10CMDF2 | L4 – Network | 0 | Upcoming | 05/12/2026 | 05/18/2026 |  |  |  |  | 05/15/2026 |  | Link |  |  |  | 05/18/2026 |  | Link | Link
RPL10 | 10CMDF2 | L5 – Punchlist | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF1b | L2 – Infrastructure | 0 | Upcoming | 06/09/2026 | 07/21/2026 |  | 06/20/2026 |  | Link | 06/30/2026 |  | Link | 07/11/2026 |  | Link | 07/21/2026 |  | Link | Link
RPL10 | 10EF1b | L3 – ISP | 0 | Upcoming | 12/07/2026 | 02/02/2027 |  | 12/22/2026 |  | Link | 01/05/2027 |  | Link | 01/19/2027 |  | Link | 02/02/2027 |  | Link | Link
RPL10 | 10EF1b | L3 – OSP | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF1b | L4 – Network | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF1b | L5 – Punchlist | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF1f | L2 – Infrastructure | 0 | Upcoming | 06/03/2026 | 06/16/2026 |  | 06/08/2026 |  | Link | 06/10/2026 |  | Link | 06/13/2026 |  | Link | 06/16/2026 |  | Link | Link
RPL10 | 10EF1f | L3 – ISP | 0 | Upcoming | 12/07/2026 | 02/02/2027 |  | 12/22/2026 |  | Link | 01/05/2027 |  | Link | 01/19/2027 |  | Link | 02/02/2027 |  | Link | Link
RPL10 | 10EF1f | L3 – OSP | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF1f | L4 – Network | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF1f | L5 – Punchlist | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF2b | L2 – Infrastructure | 0 | Upcoming | 07/08/2026 | 08/18/2026 |  | 07/20/2026 |  | Link | 07/29/2026 |  | Link | 08/08/2026 |  | Link | 08/18/2026 |  | Link | Link
RPL10 | 10EF2b | L3 – ISP | 0 | Upcoming | 12/07/2026 | 02/02/2027 |  | 12/22/2026 |  | Link | 01/05/2027 |  | Link | 01/19/2027 |  | Link | 02/02/2027 |  | Link | Link
RPL10 | 10EF2b | L3 – OSP | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF2b | L4 – Network | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF2b | L5 – Punchlist | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF2f | L2 – Infrastructure | 0 | Upcoming | 06/23/2026 | 08/04/2026 |  | 07/04/2026 |  | Link | 07/14/2026 |  | Link | 07/25/2026 |  | Link | 08/04/2026 |  | Link | Link
RPL10 | 10EF2f | L3 – ISP | 0 | Upcoming | 12/07/2026 | 02/02/2027 |  | 12/22/2026 |  | Link | 01/05/2027 |  | Link | 01/19/2027 |  | Link | 02/02/2027 |  | Link | Link
RPL10 | 10EF2f | L3 – OSP | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF2f | L4 – Network | 0 | Not Started | [15 empty] | Link
RPL10 | 10EF2f | L5 – Punchlist | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSEF1 | L2 – Infrastructure | 50 | Past Due | 04/06/2026 | 04/08/2026 |  |  |  |  | 04/07/2026 | 04/07/2026 | Link |  |  |  | 04/08/2026 |  | Link | Link
RPL10 | 10GSEF1 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSEF1 | L3 – OSP | 0 | Past Due | 04/13/2026 | 04/16/2026 |  |  |  |  | 04/15/2026 |  | Link |  |  |  | 04/16/2026 |  | Link | Link
RPL10 | 10GSEF1 | L4 – Network | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSEF1 | L5 – Punchlist | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSEF2 | L2 – Infrastructure | 50 | Past Due | 04/06/2026 | 04/08/2026 |  |  |  |  | 04/07/2026 | 04/08/2026 | Link |  |  |  | 04/08/2026 |  | Link | Link
RPL10 | 10GSEF2 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSEF2 | L3 – OSP | 0 | Past Due | 04/13/2026 | 04/16/2026 |  |  |  |  | 04/15/2026 |  | Link |  |  |  | 04/16/2026 |  | Link | Link
RPL10 | 10GSEF2 | L4 – Network | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSEF2 | L5 – Punchlist | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSMDF1 | L2 – Infrastructure | 50 | Past Due | 04/13/2026 | 04/15/2026 |  |  |  |  | 04/14/2026 | 04/15/2026 | Link |  |  |  | 04/15/2026 |  | Link | Link
RPL10 | 10GSMDF1 | L3 – ISP | 0 | Upcoming | 04/16/2026 | 04/21/2026 |  |  |  |  | 04/20/2026 |  | Link |  |  |  | 04/21/2026 |  | Link | Link
RPL10 | 10GSMDF1 | L3 – OSP | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSMDF1 | L4 – Network | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSMDF1 | L5 – Punchlist | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSMDF2 | L2 – Infrastructure | 50 | Past Due | 04/13/2026 | 04/15/2026 |  |  |  |  | 04/14/2026 | 04/14/2026 | Link |  |  |  | 04/15/2026 |  | Link | Link
RPL10 | 10GSMDF2 | L3 – ISP | 0 | Upcoming | 04/16/2026 | 04/21/2026 |  |  |  |  | 04/20/2026 |  | Link |  |  |  | 04/21/2026 |  | Link | Link
RPL10 | 10GSMDF2 | L3 – OSP | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSMDF2 | L4 – Network | 0 | Not Started | [15 empty] | Link
RPL10 | 10GSMDF2 | L5 – Punchlist | 0 | Not Started | [15 empty] | Link
RPL10 | GSIDFN11 | L2 – Infrastructure | 0 | Upcoming | 09/03/2026 | 09/10/2026 |  |  |  |  | 09/07/2026 |  | Link |  |  |  | 09/10/2026 |  | Link | Link
RPL10 | GSIDFN11 | L3 – ISP | 0 | Upcoming | 09/16/2026 | 10/01/2026 |  | 09/21/2026 |  |  | 09/24/2026 |  |  | 09/28/2026 |  |  | 10/01/2026 |  |  | Link
RPL10 | GSIDFN11 | L3 – OSP | 0 | Upcoming | 09/09/2026 | 09/15/2026 |  |  |  |  | 09/12/2026 | [5 empty] | 09/15/2026
RPL10 | GSIDFN11 | L4 – Network | 0 | Upcoming | 09/16/2026 | 09/18/2026 |  |  |  |  | 09/17/2026 | [5 empty] | 09/18/2026
RPL10 | GSIDFN11 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFN12 | L2 – Infrastructure | 0 | Upcoming | 07/15/2026 | 07/21/2026 |  |  |  |  | 07/18/2026 | [5 empty] | 07/21/2026 |  |  | Link
RPL10 | GSIDFN12 | L3 – ISP | 0 | Upcoming | 07/28/2026 | 08/12/2026 |  | 08/01/2026 |  |  | 08/05/2026 |  |  | 08/10/2026 |  |  | 08/12/2026 |  |  | Link
RPL10 | GSIDFN12 | L3 – OSP | 0 | Upcoming | 07/20/2026 | 07/27/2026 |  |  |  |  | 07/24/2026 | [5 empty] | 07/27/2026
RPL10 | GSIDFN12 | L4 – Network | 0 | Upcoming | 07/28/2026 | 07/30/2026 |  |  |  |  | 07/29/2026 | [5 empty] | 07/30/2026
RPL10 | GSIDFN12 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFN13 | L2 – Infrastructure | 0 | Past Due | 03/23/2026 | 03/27/2026 |  |  |  |  | 03/25/2026 |  | Link |  |  |  | 03/27/2026 |  | Link | Link
RPL10 | GSIDFN13 | L3 – ISP | 0 | Upcoming | 04/27/2026 | 05/12/2026 |  | 05/01/2026 |  |  | 05/05/2026 |  |  | 05/09/2026 |  |  | 05/12/2026 |  |  | Link
RPL10 | GSIDFN13 | L3 – OSP | 0 | Upcoming | 04/20/2026 | 04/24/2026 |  |  |  |  | 04/22/2026 | [5 empty] | 04/24/2026
RPL10 | GSIDFN13 | L4 – Network | 0 | Upcoming | 04/27/2026 | 04/29/2026 |  |  |  |  | 04/28/2026 | [5 empty] | 04/29/2026
RPL10 | GSIDFN13 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFN21 | L2 – Infrastructure | 0 | Upcoming | 09/11/2026 | 09/17/2026 |  |  |  |  | 09/14/2026 | [5 empty] | 09/17/2026 |  |  | Link
RPL10 | GSIDFN21 | L3 – ISP | 0 | Upcoming | 10/08/2026 | 10/23/2026 |  | 10/12/2026 |  |  | 10/16/2026 |  |  | 10/20/2026 |  |  | 10/23/2026 |  |  | Link
RPL10 | GSIDFN21 | L3 – OSP | 0 | Upcoming | 10/01/2026 | 10/07/2026 |  |  |  |  | 10/05/2026 | [5 empty] | 10/07/2026
RPL10 | GSIDFN21 | L4 – Network | 0 | Upcoming | 10/08/2026 | 10/12/2026 |  |  |  |  | 10/10/2026 | [5 empty] | 10/12/2026
RPL10 | GSIDFN21 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFN22 | L2 – Infrastructure | 0 | Upcoming | 07/16/2026 | 07/22/2026 |  |  |  |  | 07/20/2026 | [5 empty] | 07/22/2026 |  |  | Link
RPL10 | GSIDFN22 | L3 – ISP | 0 | Upcoming | 08/18/2026 | 09/02/2026 |  | 08/22/2026 |  |  | 08/26/2026 |  |  | 08/31/2026 |  |  | 09/02/2026 |  |  | Link
RPL10 | GSIDFN22 | L3 – OSP | 0 | Upcoming | 08/11/2026 | 08/17/2026 |  |  |  |  | 08/14/2026 | [5 empty] | 08/17/2026
RPL10 | GSIDFN22 | L4 – Network | 0 | Upcoming | 08/18/2026 | 08/20/2026 |  |  |  |  | 08/19/2026 | [5 empty] | 08/20/2026
RPL10 | GSIDFN22 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFN23 | L2 – Infrastructure | 0 | Past Due | 03/23/2026 | 03/27/2026 |  |  |  |  | 03/25/2026 |  | Link |  |  |  | 03/27/2026 |  | Link | Link
RPL10 | GSIDFN23 | L3 – ISP | 0 | Upcoming | 04/27/2026 | 05/12/2026 |  | 05/01/2026 |  |  | 05/05/2026 |  |  | 05/09/2026 |  |  | 05/12/2026 |  |  | Link
RPL10 | GSIDFN23 | L3 – OSP | 0 | Upcoming | 04/20/2026 | 04/24/2026 |  |  |  |  | 04/22/2026 | [5 empty] | 04/24/2026
RPL10 | GSIDFN23 | L4 – Network | 0 | Upcoming | 04/27/2026 | 04/29/2026 |  |  |  |  | 04/28/2026 | [5 empty] | 04/29/2026
RPL10 | GSIDFN23 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFN31 | L2 – Infrastructure | 0 | Past Due | 04/13/2026 | 04/17/2026 |  |  |  |  | 04/15/2026 |  | Link |  |  |  | 04/17/2026 |  | Link | Link
RPL10 | GSIDFN31 | L3 – ISP | 0 | Upcoming | 05/04/2026 | 05/19/2026 |  | 05/08/2026 |  |  | 05/12/2026 |  |  | 05/16/2026 |  |  | 05/19/2026 |  |  | Link
RPL10 | GSIDFN31 | L3 – OSP | 0 | Upcoming | 04/20/2026 | 05/01/2026 |  | 04/23/2026 |  |  | 04/27/2026 |  |  | 04/29/2026 |  |  | 05/01/2026
RPL10 | GSIDFN31 | L4 – Network | 0 | Upcoming | 05/04/2026 | 05/06/2026 |  |  |  |  | 05/05/2026 | [5 empty] | 05/06/2026
RPL10 | GSIDFN31 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFN32 | L2 – Infrastructure | 0 | Upcoming | 11/17/2026 | 11/23/2026 |  |  |  |  | 11/20/2026 | [5 empty] | 11/23/2026 |  |  | Link
RPL10 | GSIDFN32 | L3 – ISP | 0 | Upcoming | 12/10/2026 | 12/28/2026 |  | 12/15/2026 |  |  | 12/19/2026 |  |  | 12/24/2026 |  |  | 12/28/2026 |  |  | Link
RPL10 | GSIDFN32 | L3 – OSP | 0 | Upcoming | 11/24/2026 | 12/09/2026 |  | 11/28/2026 |  |  | 12/02/2026 |  |  | 12/07/2026 |  |  | 12/09/2026
RPL10 | GSIDFN32 | L4 – Network | 0 | Upcoming | 12/10/2026 | 12/14/2026 |  |  |  |  | 12/12/2026 | [5 empty] | 12/14/2026
RPL10 | GSIDFN32 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFN33 | L2 – Infrastructure | 0 | Upcoming | 05/07/2026 | 05/13/2026 |  |  |  |  | 05/11/2026 | [5 empty] | 05/13/2026 |  |  | Link
RPL10 | GSIDFN33 | L3 – ISP | 0 | Upcoming | 05/29/2026 | 06/15/2026 |  | 06/03/2026 |  |  | 06/08/2026 |  |  | 06/11/2026 |  |  | 06/15/2026 |  |  | Link
RPL10 | GSIDFN33 | L3 – OSP | 0 | Upcoming | 05/14/2026 | 05/28/2026 |  | 05/18/2026 |  |  | 05/21/2026 |  |  | 05/25/2026 |  |  | 05/28/2026
RPL10 | GSIDFN33 | L4 – Network | 0 | Upcoming | 05/29/2026 | 06/02/2026 |  |  |  |  | 06/01/2026 | [5 empty] | 06/02/2026
RPL10 | GSIDFN33 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFN41 | L2 – Infrastructure | 0 | Past Due | 04/13/2026 | 04/17/2026 |  |  |  |  | 04/15/2026 |  | Link |  |  |  | 04/17/2026 |  | Link | Link
RPL10 | GSIDFN41 | L3 – ISP | 0 | Upcoming | 05/04/2026 | 05/19/2026 |  | 05/08/2026 |  | Link | 05/12/2026 |  | Link | 05/16/2026 |  | Link | 05/19/2026 |  | Link | Link
RPL10 | GSIDFN41 | L3 – OSP | 0 | Upcoming | 04/20/2026 | 05/01/2026 |  | 04/23/2026 |  | Link | 04/27/2026 |  |  | 04/29/2026 |  |  | 05/01/2026
RPL10 | GSIDFN41 | L4 – Network | 0 | Upcoming | 05/04/2026 | 05/06/2026 |  |  |  |  | 05/05/2026 | [5 empty] | 05/06/2026
RPL10 | GSIDFN41 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFN42 | L2 – Infrastructure | 0 | Upcoming | 11/04/2026 | 11/10/2026 |  |  |  |  | 11/07/2026 | [5 empty] | 11/10/2026 |  |  | Link
RPL10 | GSIDFN42 | L3 – ISP | 0 | Upcoming | 11/30/2026 | 12/15/2026 |  | 12/04/2026 |  |  | 12/08/2026 |  |  | 12/12/2026 |  |  | 12/15/2026 |  |  | Link
RPL10 | GSIDFN42 | L3 – OSP | 0 | Upcoming | 11/12/2026 | 11/25/2026 |  | 11/16/2026 |  |  | 11/19/2026 |  |  | 11/23/2026 |  |  | 11/25/2026
RPL10 | GSIDFN42 | L4 – Network | 0 | Upcoming | 11/30/2026 | 12/02/2026 |  |  |  |  | 12/01/2026 | [5 empty] | 12/02/2026
RPL10 | GSIDFN42 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFN43 | L2 – Infrastructure | 0 | Upcoming | 05/07/2026 | 05/13/2026 |  |  |  |  | 05/11/2026 | [5 empty] | 05/13/2026 |  |  | Link
RPL10 | GSIDFN43 | L3 – ISP | 0 | Upcoming | 05/29/2026 | 06/15/2026 |  | 06/03/2026 |  |  | 06/08/2026 |  |  | 06/11/2026 |  |  | 06/15/2026 |  |  | Link
RPL10 | GSIDFN43 | L3 – OSP | 0 | Upcoming | 05/14/2026 | 05/28/2026 |  | 05/18/2026 |  |  | 05/21/2026 |  |  | 05/25/2026 |  |  | 05/28/2026
RPL10 | GSIDFN43 | L4 – Network | 0 | Upcoming | 05/29/2026 | 06/02/2026 |  |  |  |  | 06/01/2026 | [5 empty] | 06/02/2026
RPL10 | GSIDFN43 | L5 – Punchlist | 0 | Not Started
RPL10 | GSIDFNE1 | L2 – Infrastructure | 0 | Past Due | 03/23/2026 | 03/27/2026 |  |  |  |  | 03/25/2026 |  | Link |  |  |  | 03/27/2026 |  | Link | Link
RPL10 | GSIDFNE1 | L3 – ISP | 0 | Upcoming | 04/28/2026 | 05/18/2026 |  | 05/04/2026 |  | Link | 05/08/2026 |  | Link | 05/13/2026 |  | Link | 05/18/2026 |  | Link | Link
RPL10 | GSIDFNE1 | L3 – OSP | 0 | Upcoming | 04/20/2026 | 04/27/2026 |  |  |  |  | 04/24/2026 | [5 empty] | 04/27/2026
RPL10 | GSIDFNE1 | L4 – Network | 0 | Upcoming | 04/28/2026 | 04/30/2026 |  |  |  |  | 04/29/2026 |  | Link |  |  |  | 04/30/2026
RPL10 | GSIDFNE1 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS1 MP01/02 CFD1 | L2 – Infrastructure | 0 | Upcoming | 09/18/2026 | 09/23/2026 |  |  |  |  | 09/21/2026 |  | Link |  |  |  | 09/23/2026 |  | Link | Link
RPL10 | RPL10 NS1 MP01/02 CFD1 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS1 MP01/02 CFD1 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS1 MP01/02 CFD1 | L4 – Network | 0 | Upcoming | 09/24/2026 | 12/11/2026 |  | 10/14/2026 |  | Link | 11/02/2026 |  | Link | 11/23/2026 |  | Link | 12/11/2026 |  | Link
RPL10 | RPL10 NS1 MP01/02 CFD1 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS1 MP03/04 CFD2 | L2 – Infrastructure | 0 | Upcoming | 08/26/2026 | 08/31/2026 |  |  |  |  | 08/29/2026 |  | Link |  |  |  | 08/31/2026 |  | Link | Link
RPL10 | RPL10 NS1 MP03/04 CFD2 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS1 MP03/04 CFD2 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS1 MP03/04 CFD2 | L4 – Network | 0 | Upcoming | 09/01/2026 | 12/04/2026 |  | 09/25/2026 |  | Link | 10/19/2026 |  | Link | 11/11/2026 |  | Link | 12/04/2026 |  | Link
RPL10 | RPL10 NS1 MP03/04 CFD2 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS1 MP05/06 CFD3 | L2 – Infrastructure | 0 | Upcoming | 08/13/2026 | 08/18/2026 |  |  |  |  | 08/17/2026 |  | Link |  |  |  | 08/18/2026 |  | Link | Link
RPL10 | RPL10 NS1 MP05/06 CFD3 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS1 MP05/06 CFD3 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS1 MP05/06 CFD3 | L4 – Network | 0 | Upcoming | 08/31/2026 | 11/23/2026 |  | 09/21/2026 |  | Link | 10/12/2026 |  | Link | 11/02/2026 |  | Link | 11/23/2026 |  | Link
RPL10 | RPL10 NS1 MP05/06 CFD3 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS1 MP07/08 CFD4 | L2 – Infrastructure | 0 | Upcoming | 07/20/2026 | 07/23/2026 |  |  |  |  | 07/22/2026 |  | Link |  |  |  | 07/23/2026 |  | Link | Link
RPL10 | RPL10 NS1 MP07/08 CFD4 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS1 MP07/08 CFD4 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS1 MP07/08 CFD4 | L4 – Network | 0 | Upcoming | 08/07/2026 | 10/16/2026 |  | 08/25/2026 |  | Link | 09/11/2026 |  | Link | 09/29/2026 |  | Link | 10/16/2026 |  | Link
RPL10 | RPL10 NS1 MP07/08 CFD4 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS1 MP09/10 CFD5 | L2 – Infrastructure | 0 | Upcoming | 06/12/2026 | 06/17/2026 |  |  |  |  | 06/15/2026 |  | Link |  |  |  | 06/17/2026 |  | Link | Link
RPL10 | RPL10 NS1 MP09/10 CFD5 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS1 MP09/10 CFD5 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS1 MP09/10 CFD5 | L4 – Network | 0 | Upcoming | 07/02/2026 | 10/07/2026 |  | 07/27/2026 |  | Link | 08/20/2026 |  | Link | 09/14/2026 |  | Link | 10/07/2026 |  | Link
RPL10 | RPL10 NS1 MP09/10 CFD5 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS1 MP11/12 CFD6 | L2 – Infrastructure | 0 | Upcoming | 06/09/2026 | 06/12/2026 |  |  |  |  | 06/11/2026 |  | Link |  |  |  | 06/12/2026 |  | Link | Link
RPL10 | RPL10 NS1 MP11/12 CFD6 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS1 MP11/12 CFD6 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS1 MP11/12 CFD6 | L4 – Network | 0 | Upcoming | 06/15/2026 | 08/28/2026 |  | 07/04/2026 |  | Link | 07/22/2026 |  | Link | 08/10/2026 |  | Link | 08/28/2026 |  | Link
RPL10 | RPL10 NS1 MP11/12 CFD6 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS2 MP13/14 CFD1 | L2 – Infrastructure | 0 | Upcoming | 10/28/2026 | 11/02/2026 |  |  |  |  | 10/31/2026 |  | Link |  |  |  | 11/02/2026 |  | Link | Link
RPL10 | RPL10 NS2 MP13/14 CFD1 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS2 MP13/14 CFD1 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS2 MP13/14 CFD1 | L4 – Network | 0 | Upcoming | 11/20/2026 | 01/27/2027 |  | 12/07/2026 |  | Link | 12/24/2026 |  | Link | 01/11/2027 |  | Link | 01/27/2027 |  | Link
RPL10 | RPL10 NS2 MP13/14 CFD1 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS2 MP15/16 CFD2 | L2 – Infrastructure | 0 | Upcoming | 09/23/2026 | 09/28/2026 |  |  |  |  | 09/26/2026 |  | Link |  |  |  | 09/28/2026 |  | Link | Link
RPL10 | RPL10 NS2 MP15/16 CFD2 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS2 MP15/16 CFD2 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS2 MP15/16 CFD2 | L4 – Network | 0 | Upcoming | 10/13/2026 | 01/15/2027 |  | 11/06/2026 |  | Link | 11/30/2026 |  | Link | 12/23/2026 |  | Link | 01/15/2027 |  | Link
RPL10 | RPL10 NS2 MP15/16 CFD2 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS2 MP17/18 CFD3 | L2 – Infrastructure | 0 | Upcoming | 09/01/2026 | 09/04/2026 |  |  |  |  | 09/03/2026 |  | Link |  |  |  | 09/04/2026 |  | Link | Link
RPL10 | RPL10 NS2 MP17/18 CFD3 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS2 MP17/18 CFD3 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS2 MP17/18 CFD3 | L4 – Network | 0 | Upcoming | 10/28/2026 | 01/08/2027 |  | 11/16/2026 |  | Link | 12/03/2026 |  | Link | 12/21/2026 |  | Link | 01/08/2027 |  | Link
RPL10 | RPL10 NS2 MP17/18 CFD3 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS2 MP19/20 CFD4 | L2 – Infrastructure | 0 | Upcoming | 08/11/2026 | 08/14/2026 |  |  |  |  | 08/13/2026 |  | Link |  |  |  | 08/14/2026 |  | Link | Link
RPL10 | RPL10 NS2 MP19/20 CFD4 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS2 MP19/20 CFD4 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS2 MP19/20 CFD4 | L4 – Network | 0 | Upcoming | 08/31/2026 | 11/30/2026 |  | 09/23/2026 |  | Link | 10/16/2026 |  | Link | 11/09/2026 |  | Link | 11/30/2026 |  | Link
RPL10 | RPL10 NS2 MP19/20 CFD4 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS2 MP21/22 CFD5 | L2 – Infrastructure | 0 | Upcoming | 07/21/2026 | 07/24/2026 |  |  |  |  | 07/23/2026 |  | Link |  |  |  | 07/24/2026 |  | Link | Link
RPL10 | RPL10 NS2 MP21/22 CFD5 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS2 MP21/22 CFD5 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS2 MP21/22 CFD5 | L4 – Network | 0 | Upcoming | 08/10/2026 | 11/17/2026 |  | 09/04/2026 |  | Link | 09/29/2026 |  | Link | 10/24/2026 |  | Link | 11/17/2026 |  | Link
RPL10 | RPL10 NS2 MP21/22 CFD5 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS2 MP23/24 CFD6 | L2 – Infrastructure | 0 | Upcoming | 07/07/2026 | 07/10/2026 |  |  |  |  | 07/09/2026 |  | Link |  |  |  | 07/10/2026 |  | Link | Link
RPL10 | RPL10 NS2 MP23/24 CFD6 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS2 MP23/24 CFD6 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS2 MP23/24 CFD6 | L4 – Network | 0 | Upcoming | 07/13/2026 | 10/08/2026 |  | 08/04/2026 |  | Link | 08/26/2026 |  | Link | 09/17/2026 |  | Link | 10/08/2026 |  | Link
RPL10 | RPL10 NS2 MP23/24 CFD6 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS3 MP25/26 CFD1 | L2 – Infrastructure | 0 | Upcoming | 11/04/2026 | 11/09/2026 |  |  |  |  | 11/07/2026 |  | Link |  |  |  | 11/09/2026 |  | Link | Link
RPL10 | RPL10 NS3 MP25/26 CFD1 | L3 – ISP | 0 | Not Started | [15 empty] | Link
RPL10 | RPL10 NS3 MP25/26 CFD1 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS3 MP25/26 CFD1 | L4 – Network | 0 | Upcoming | 11/25/2026 | 01/07/2027 |  | 12/07/2026 |  | Link | 12/17/2026 |  | Link | 12/28/2026 |  | Link | 01/07/2027 |  | Link
RPL10 | RPL10 NS3 MP25/26 CFD1 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS3 MP27/28 CFD2 | L2 – Infrastructure | 0 | Upcoming | 11/09/2026 | 11/13/2026 |  |  |  |  | 11/11/2026 |  | Link |  |  |  | 11/13/2026 |  | Link | Link
RPL10 | RPL10 NS3 MP27/28 CFD2 | L3 – ISP | 0 | Not Started
RPL10 | RPL10 NS3 MP27/28 CFD2 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS3 MP27/28 CFD2 | L4 – Network | 0 | Upcoming | 12/02/2026 | 02/18/2027 |  | 12/22/2026 |  | Link | 01/11/2027 |  | Link | 01/30/2027 |  | Link | 02/18/2027 |  | Link
RPL10 | RPL10 NS3 MP27/28 CFD2 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS3 MP29/30 CFD3 | L2 – Infrastructure | 0 | Upcoming | 11/24/2026 | 12/01/2026 |  |  |  |  | 11/28/2026 |  | Link |  |  |  | 12/01/2026 |  | Link | Link
RPL10 | RPL10 NS3 MP29/30 CFD3 | L3 – ISP | 0 | Not Started
RPL10 | RPL10 NS3 MP29/30 CFD3 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS3 MP29/30 CFD3 | L4 – Network | 0 | Upcoming | 12/16/2026 | 03/02/2027 |  | 01/04/2027 |  | Link | 01/23/2027 |  | Link | 02/11/2027 |  | Link | 03/02/2027 |  | Link
RPL10 | RPL10 NS3 MP29/30 CFD3 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS3 MP31/32 CFD4 | L2 – Infrastructure | 0 | Upcoming | 12/10/2026 | 12/15/2026 |  |  |  |  | 12/14/2026 |  | Link |  |  |  | 12/15/2026 |  | Link | Link
RPL10 | RPL10 NS3 MP31/32 CFD4 | L3 – ISP | 0 | Not Started
RPL10 | RPL10 NS3 MP31/32 CFD4 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS3 MP31/32 CFD4 | L4 – Network | 0 | Upcoming | 12/31/2026 | 04/06/2027 |  | 01/25/2027 |  | Link | 02/17/2027 |  | Link | 03/13/2027 |  | Link | 04/06/2027 |  | Link
RPL10 | RPL10 NS3 MP31/32 CFD4 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS3 MP33/34 CFD5 | L2 – Infrastructure | 0 | Upcoming | 12/31/2026 | 01/14/2027 |  | 01/04/2027 |  | Link | 01/07/2027 |  | Link | 01/11/2027 |  | Link | 01/14/2027 |  | Link | Link
RPL10 | RPL10 NS3 MP33/34 CFD5 | L3 – ISP | 0 | Not Started
RPL10 | RPL10 NS3 MP33/34 CFD5 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS3 MP33/34 CFD5 | L4 – Network | 0 | Upcoming | 01/15/2027 | 04/16/2027 |  | 02/08/2027 |  | Link | 03/02/2027 |  | Link | 03/25/2027 |  | Link | 04/16/2027 |  | Link
RPL10 | RPL10 NS3 MP33/34 CFD5 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS3 MP35/36 CFD6 | L2 – Infrastructure | 0 | Upcoming | 01/19/2027 | 01/22/2027 |  |  |  |  | 01/21/2027 |  | Link |  |  |  | 01/22/2027 |  | Link | Link
RPL10 | RPL10 NS3 MP35/36 CFD6 | L3 – ISP | 0 | Not Started
RPL10 | RPL10 NS3 MP35/36 CFD6 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS3 MP35/36 CFD6 | L4 – Network | 0 | Upcoming | 02/08/2027 | 04/22/2027 |  | 02/27/2027 |  | Link | 03/17/2027 |  | Link | 04/05/2027 |  | Link | 04/22/2027 |  | Link
RPL10 | RPL10 NS3 MP35/36 CFD6 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS4 MP37/38 CFD1 | L2 – Infrastructure | 0 | Upcoming | 10/09/2026 | 10/14/2026 |  |  |  |  | 10/12/2026 |  | Link |  |  |  | 10/14/2026 |  | Link | Link
RPL10 | RPL10 NS4 MP37/38 CFD1 | L3 – ISP | 0 | Not Started
RPL10 | RPL10 NS4 MP37/38 CFD1 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS4 MP37/38 CFD1 | L4 – Network | 0 | Upcoming | 11/09/2026 | 12/29/2026 |  | 11/23/2026 |  | Link | 12/04/2026 |  | Link | 12/17/2026 |  | Link | 12/29/2026 |  | Link
RPL10 | RPL10 NS4 MP37/38 CFD1 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS4 MP39/40 CFD2 | L2 – Infrastructure | 0 | Upcoming | 10/16/2026 | 10/29/2026 |  | 10/20/2026 |  | Link | 10/23/2026 |  | Link | 10/26/2026 |  | Link | 10/29/2026 |  | Link | Link
RPL10 | RPL10 NS4 MP39/40 CFD2 | L3 – ISP | 0 | Not Started
RPL10 | RPL10 NS4 MP39/40 CFD2 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS4 MP39/40 CFD2 | L4 – Network | 0 | Upcoming | 11/13/2026 | 02/08/2027 |  | 12/05/2026 |  | Link | 12/28/2026 |  | Link | 01/18/2027 |  | Link | 02/08/2027 |  | Link
RPL10 | RPL10 NS4 MP39/40 CFD2 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS4 MP41/42 CFD3 | L2 – Infrastructure | 0 | Upcoming | 11/12/2026 | 11/17/2026 |  |  |  |  | 11/16/2026 |  | Link |  |  |  | 11/17/2026 |  | Link | Link
RPL10 | RPL10 NS4 MP41/42 CFD3 | L3 – ISP | 0 | Not Started
RPL10 | RPL10 NS4 MP41/42 CFD3 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS4 MP41/42 CFD3 | L4 – Network | 0 | Upcoming | 12/04/2026 | 02/18/2027 |  | 12/23/2026 |  | Link | 01/11/2027 |  | Link | 01/30/2027 |  | Link | 02/18/2027 |  | Link
RPL10 | RPL10 NS4 MP41/42 CFD3 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS4 MP43/44 CFD4 | L2 – Infrastructure | 0 | Upcoming | 11/16/2026 | 11/19/2026 |  |  |  |  | 11/18/2026 |  | Link |  |  |  | 11/19/2026 |  | Link | Link
RPL10 | RPL10 NS4 MP43/44 CFD4 | L3 – ISP | 0 | Not Started
RPL10 | RPL10 NS4 MP43/44 CFD4 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS4 MP43/44 CFD4 | L4 – Network | 0 | Upcoming | 12/15/2026 | 03/25/2027 |  | 01/09/2027 |  | Link | 02/03/2027 |  | Link | 03/01/2027 |  | Link | 03/25/2027 |  | Link
RPL10 | RPL10 NS4 MP43/44 CFD4 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS4 MP45/46 CFD5 | L2 – Infrastructure | 0 | Upcoming | 12/14/2026 | 12/17/2026 |  |  |  |  | 12/16/2026 |  | Link |  |  |  | 12/17/2026 |  | Link | Link
RPL10 | RPL10 NS4 MP45/46 CFD5 | L3 – ISP | 0 | Not Started
RPL10 | RPL10 NS4 MP45/46 CFD5 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS4 MP45/46 CFD5 | L4 – Network | 0 | Upcoming | 01/05/2027 | 04/06/2027 |  | 01/28/2027 |  | Link | 02/20/2027 |  | Link | 03/15/2027 |  | Link | 04/06/2027 |  | Link
RPL10 | RPL10 NS4 MP45/46 CFD5 | L5 – Punchlist | 0 | Not Started
RPL10 | RPL10 NS4 MP47/48 CFD6 | L2 – Infrastructure | 0 | Upcoming | 12/14/2026 | 12/17/2026 |  |  |  |  | 12/16/2026 |  | Link |  |  |  | 12/17/2026 |  | Link | Link
RPL10 | RPL10 NS4 MP47/48 CFD6 | L3 – ISP | 0 | Not Started
RPL10 | RPL10 NS4 MP47/48 CFD6 | L3 – OSP | 0 | Not Started
RPL10 | RPL10 NS4 MP47/48 CFD6 | L4 – Network | 0 | Upcoming | 01/22/2027 | 04/13/2027 |  | 02/12/2027 |  | Link | 03/04/2027 |  | Link | 03/24/2027 |  | Link | 04/13/2027 |  | Link
RPL10 | RPL10 NS4 MP47/48 CFD6 | L5 – Punchlist | 0 | Not Started
RPL9 | 9GSEF1 | L2 – Infrastructure | 0 | Upcoming | 07/01/2027 | 07/06/2027 |  |  |  |  | 07/05/2027 | [5 empty] | 07/06/2027
RPL9 | 9GSEF1 | L3 – ISP | 0 | Not Started
RPL9 | 9GSEF1 | L3 – OSP | 0 | Upcoming | 07/07/2027 | 07/12/2027 |  |  |  |  | 07/10/2027 | [5 empty] | 07/12/2027
RPL9 | 9GSEF1 | L4 – Network | 0 | Not Started
RPL9 | 9GSEF1 | L5 – Punchlist | 0 | Not Started
RPL9 | 9GSEF2 | L2 – Infrastructure | 0 | Upcoming | 07/01/2027 | 07/06/2027 |  |  |  |  | 07/05/2027 | [5 empty] | 07/06/2027
RPL9 | 9GSEF2 | L3 – ISP | 0 | Not Started
RPL9 | 9GSEF2 | L3 – OSP | 0 | Upcoming | 07/07/2027 | 07/12/2027 |  |  |  |  | 07/10/2027 | [5 empty] | 07/12/2027
RPL9 | 9GSEF2 | L4 – Network | 0 | Not Started
RPL9 | 9GSEF2 | L5 – Punchlist | 0 | Not Started
RPL9 | 9GSMDF1 | L2 – Infrastructure | 0 | Upcoming | 03/19/2027 | 03/23/2027 |  |  |  |  | 03/22/2027 | [5 empty] | 03/23/2027
RPL9 | 9GSMDF1 | L3 – ISP | 0 | Not Started
RPL9 | 9GSMDF1 | L3 – OSP | 0 | Not Started
RPL9 | 9GSMDF1 | L4 – Network | 0 | Not Started
RPL9 | 9GSMDF1 | L5 – Punchlist | 0 | Not Started
RPL9 | 9GSMDF2 | L2 – Infrastructure | 0 | Upcoming | 03/12/2027 | 03/16/2027 |  |  |  |  | 03/15/2027 | [5 empty] | 03/16/2027
RPL9 | 9GSMDF2 | L3 – ISP | 0 | Not Started
RPL9 | 9GSMDF2 | L3 – OSP | 0 | Not Started
RPL9 | 9GSMDF2 | L4 – Network | 0 | Not Started
RPL9 | 9GSMDF2 | L5 – Punchlist | 0 | Not Started
RPL9 | GSIDF9A1 | L2 – Infrastructure | 0 | Upcoming | 07/23/2027 | 07/29/2027 |  |  |  |  | 07/26/2027 | [5 empty] | 07/29/2027
RPL9 | GSIDF9A1 | L3 – ISP | 0 | Upcoming | 08/26/2027 | 09/13/2027 |  | 08/31/2027 |  |  | 09/04/2027 |  |  | 09/09/2027 |  |  | 09/13/2027
RPL9 | GSIDF9A1 | L3 – OSP | 0 | Upcoming | 08/26/2027 | 09/02/2027 |  |  |  |  | 08/30/2027 | [5 empty] | 09/02/2027
RPL9 | GSIDF9A1 | L4 – Network | 0 | Upcoming | 09/03/2027 | 09/08/2027 |  |  |  |  | 09/06/2027 | [5 empty] | 09/08/2027
RPL9 | GSIDF9A1 | L5 – Punchlist | 0 | Not Started
RPL9 | GSIDF9A2 | L2 – Infrastructure | 0 | Upcoming | 03/08/2027 | 03/12/2027 |  |  |  |  | 03/10/2027 | [5 empty] | 03/12/2027
RPL9 | GSIDF9A2 | L3 – ISP | 0 | Upcoming | 04/22/2027 | 05/07/2027 |  | 04/26/2027 |  |  | 04/30/2027 |  |  | 05/04/2027 |  |  | 05/07/2027
RPL9 | GSIDF9A2 | L3 – OSP | 0 | Upcoming | 04/22/2027 | 04/29/2027 |  |  |  |  | 04/26/2027 | [5 empty] | 04/29/2027
RPL9 | GSIDF9A2 | L4 – Network | 0 | Upcoming | 06/12/2028 | 06/14/2028 |  |  |  |  | 06/13/2028 | [5 empty] | 06/14/2028
RPL9 | GSIDF9A2 | L5 – Punchlist | 0 | Not Started
RPL9 | GSIDF9B1 | L2 – Infrastructure | 0 | Upcoming | 07/01/2027 | 07/08/2027 |  |  |  |  | 07/05/2027 | [5 empty] | 07/08/2027
RPL9 | GSIDF9B1 | L3 – ISP | 0 | Upcoming | 07/29/2027 | 08/13/2027 |  | 08/02/2027 |  |  | 08/06/2027 |  |  | 08/10/2027 |  |  | 08/13/2027
RPL9 | GSIDF9B1 | L3 – OSP | 0 | Upcoming | 07/29/2027 | 08/05/2027 |  |  |  |  | 08/02/2027 | [5 empty] | 08/05/2027
RPL9 | GSIDF9B1 | L4 – Network | 0 | Upcoming | 08/06/2027 | 08/10/2027 |  |  |  |  | 08/09/2027 | [5 empty] | 08/10/2027
RPL9 | GSIDF9B1 | L5 – Punchlist | 0 | Not Started
RPL9 | GSIDF9B2 | L2 – Infrastructure | 0 | Upcoming | 03/05/2027 | 03/11/2027 |  |  |  |  | 03/08/2027 | [5 empty] | 03/11/2027
RPL9 | GSIDF9B2 | L3 – ISP | 0 | Upcoming | 04/22/2027 | 05/07/2027 |  | 04/26/2027 |  |  | 04/30/2027 |  |  | 05/04/2027 |  |  | 05/07/2027
RPL9 | GSIDF9B2 | L3 – OSP | 0 | Upcoming | 04/22/2027 | 04/29/2027 |  |  |  |  | 04/26/2027 | [5 empty] | 04/29/2027
RPL9 | GSIDF9B2 | L4 – Network | 0 | Upcoming | 05/25/2028 | 05/30/2028 |  |  |  |  | 05/29/2028 | [5 empty] | 05/30/2028
RPL9 | GSIDF9B2 | L5 – Punchlist | 0 | Not Started
RPL9 | GSIDF9C1 | L2 – Infrastructure | 0 | Upcoming | 10/07/2027 | 10/13/2027 |  |  |  |  | 10/11/2027 | [5 empty] | 10/13/2027
RPL9 | GSIDF9C1 | L3 – ISP | 0 | Upcoming | 11/10/2027 | 11/30/2027 |  | 11/15/2027 |  |  | 11/20/2027 |  |  | 11/25/2027 |  |  | 11/30/2027
RPL9 | GSIDF9C1 | L3 – OSP | 0 | Upcoming | 11/10/2027 | 11/18/2027 |  | 11/12/2027 |  |  | 11/15/2027 |  |  | 11/16/2027 |  |  | 11/18/2027
RPL9 | GSIDF9C1 | L4 – Network | 0 | Upcoming | 11/19/2027 | 11/23/2027 |  |  |  |  | 11/22/2027 | [5 empty] | 11/23/2027
RPL9 | GSIDF9C1 | L5 – Punchlist | 0 | Not Started
RPL9 | GSIDF9C2 | L2 – Infrastructure | 0 | Upcoming | 05/07/2027 | 05/13/2027 |  |  |  |  | 05/10/2027 | [5 empty] | 05/13/2027
RPL9 | GSIDF9C2 | L3 – ISP | 0 | Upcoming | 05/21/2027 | 06/08/2027 |  | 05/26/2027 |  |  | 05/31/2027 |  |  | 06/04/2027 |  |  | 06/08/2027
RPL9 | GSIDF9C2 | L3 – OSP | 0 | Upcoming | 05/21/2027 | 05/28/2027 |  |  |  |  | 05/25/2027 | [5 empty] | 05/28/2027
RPL9 | GSIDF9C2 | L4 – Network | 0 | Upcoming | 06/01/2027 | 06/03/2027 |  |  |  |  | 06/02/2027 | [5 empty] | 06/03/2027
RPL9 | GSIDF9C2 | L5 – Punchlist | 0 | Not Started
RPL9 | GSIDF9C3 | L2 – Infrastructure | 0 | Not Started
RPL9 | GSIDF9C3 | L3 – ISP | 0 | Not Started
RPL9 | GSIDF9C3 | L3 – OSP | 0 | Not Started
RPL9 | GSIDF9C3 | L4 – Network | 0 | Not Started
RPL9 | GSIDF9C3 | L5 – Punchlist | 0 | Not Started
RPL9 | GSIDF9D1 | L2 – Infrastructure | 0 | Upcoming | 09/16/2027 | 09/22/2027 |  |  |  |  | 09/20/2027 | [5 empty] | 09/22/2027
RPL9 | GSIDF9D1 | L3 – ISP | 0 | Upcoming | 10/13/2027 | 10/28/2027 |  | 10/18/2027 |  |  | 10/21/2027 |  |  | 10/25/2027 |  |  | 10/28/2027
RPL9 | GSIDF9D1 | L3 – OSP | 0 | Upcoming | 10/13/2027 | 10/20/2027 |  |  |  |  | 10/18/2027 | [5 empty] | 10/20/2027
RPL9 | GSIDF9D1 | L4 – Network | 0 | Upcoming | 10/21/2027 | 10/25/2027 |  |  |  |  | 10/23/2027 | [5 empty] | 10/25/2027
RPL9 | GSIDF9D1 | L5 – Punchlist | 0 | Not Started
RPL9 | GSIDF9D2 | L2 – Infrastructure | 0 | Not Started
RPL9 | GSIDF9D2 | L3 – ISP | 0 | Upcoming | 05/28/2027 | 06/15/2027 |  | 06/02/2027 |  |  | 06/07/2027 |  |  | 06/11/2027 |  |  | 06/15/2027
RPL9 | GSIDF9D2 | L3 – OSP | 0 | Upcoming | 05/28/2027 | 06/07/2027 |  | 05/31/2027 |  |  | 06/02/2027 |  |  | 06/05/2027 |  |  | 06/07/2027
RPL9 | GSIDF9D2 | L4 – Network | 0 | Upcoming | 06/08/2027 | 06/10/2027 |  |  |  |  | 06/09/2027 | [5 empty] | 06/10/2027
RPL9 | GSIDF9D2 | L5 – Punchlist | 0 | Not Started
RPL9 | GSIDF9D3 | L2 – Infrastructure | 0 | Not Started
RPL9 | GSIDF9D3 | L3 – ISP | 0 | Not Started
RPL9 | GSIDF9D3 | L3 – OSP | 0 | Not Started
RPL9 | GSIDF9D3 | L4 – Network | 0 | Not Started
RPL9 | GSIDF9D3 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHA MP01/02 MFD1 | L2 – Infrastructure | 0 | Upcoming | 07/22/2027 | 08/18/2027 |  | 07/29/2027 |  |  | 08/05/2027 |  |  | 08/12/2027 |  |  | 08/18/2027
RPL9 | RPL9 DHA MP01/02 MFD1 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHA MP01/02 MFD1 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHA MP01/02 MFD1 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHA MP01/02 MFD1 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHA MP03/04 MFD2 | L2 – Infrastructure | 0 | Upcoming | 08/12/2027 | 09/09/2027 |  | 08/19/2027 |  |  | 08/26/2027 |  |  | 09/02/2027 |  |  | 09/09/2027
RPL9 | RPL9 DHA MP03/04 MFD2 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHA MP03/04 MFD2 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHA MP03/04 MFD2 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHA MP03/04 MFD2 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHA MP05/06 MFD3 | L2 – Infrastructure | 0 | Upcoming | 08/26/2027 | 09/23/2027 |  | 09/02/2027 |  |  | 09/09/2027 |  |  | 09/16/2027 |  |  | 09/23/2027
RPL9 | RPL9 DHA MP05/06 MFD3 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHA MP05/06 MFD3 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHA MP05/06 MFD3 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHA MP05/06 MFD3 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHA MP07/08 MFD4 | L2 – Infrastructure | 0 | Upcoming | 09/10/2027 | 10/07/2027 |  | 09/17/2027 |  |  | 09/24/2027 |  |  | 10/01/2027 |  |  | 10/07/2027
RPL9 | RPL9 DHA MP07/08 MFD4 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHA MP07/08 MFD4 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHA MP07/08 MFD4 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHA MP07/08 MFD4 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHA MP09/10 MFD5 | L2 – Infrastructure | 0 | Upcoming | 09/28/2027 | 10/25/2027 |  | 10/05/2027 |  |  | 10/12/2027 |  |  | 10/19/2027 |  |  | 10/25/2027
RPL9 | RPL9 DHA MP09/10 MFD5 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHA MP09/10 MFD5 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHA MP09/10 MFD5 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHA MP09/10 MFD5 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHB MP11/12 MFD1 | L2 – Infrastructure | 0 | Upcoming | 06/14/2027 | 07/12/2027 |  | 06/21/2027 |  |  | 06/28/2027 |  |  | 07/05/2027 |  |  | 07/12/2027
RPL9 | RPL9 DHB MP11/12 MFD1 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHB MP11/12 MFD1 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHB MP11/12 MFD1 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHB MP11/12 MFD1 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHB MP13/14 MFD2 | L2 – Infrastructure | 0 | Upcoming | 07/15/2027 | 08/11/2027 |  | 07/22/2027 |  |  | 07/29/2027 |  |  | 08/05/2027 |  |  | 08/11/2027
RPL9 | RPL9 DHB MP13/14 MFD2 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHB MP13/14 MFD2 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHB MP13/14 MFD2 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHB MP13/14 MFD2 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHB MP15/16 MFD3 | L2 – Infrastructure | 0 | Upcoming | 07/29/2027 | 08/25/2027 |  | 08/05/2027 |  |  | 08/12/2027 |  |  | 08/19/2027 |  |  | 08/25/2027
RPL9 | RPL9 DHB MP15/16 MFD3 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHB MP15/16 MFD3 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHB MP15/16 MFD3 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHB MP15/16 MFD3 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHB MP17/18 MFD4 | L2 – Infrastructure | 0 | Upcoming | 08/12/2027 | 09/09/2027 |  | 08/19/2027 |  |  | 08/26/2027 |  |  | 09/02/2027 |  |  | 09/09/2027
RPL9 | RPL9 DHB MP17/18 MFD4 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHB MP17/18 MFD4 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHB MP17/18 MFD4 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHB MP17/18 MFD4 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHB MP19/20 MFD5 | L2 – Infrastructure | 0 | Upcoming | 08/30/2027 | 09/27/2027 |  | 09/06/2027 |  |  | 09/13/2027 |  |  | 09/20/2027 |  |  | 09/27/2027
RPL9 | RPL9 DHB MP19/20 MFD5 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHB MP19/20 MFD5 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHB MP19/20 MFD5 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHB MP19/20 MFD5 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHC MP21/22 MFD1 | L2 – Infrastructure | 0 | Upcoming | 10/06/2027 | 11/02/2027 |  | 10/13/2027 |  |  | 10/20/2027 |  |  | 10/27/2027 |  |  | 11/02/2027
RPL9 | RPL9 DHC MP21/22 MFD1 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHC MP21/22 MFD1 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHC MP21/22 MFD1 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHC MP21/22 MFD1 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHC MP23/24 MFD2 | L2 – Infrastructure | 0 | Upcoming | 10/27/2027 | 11/24/2027 |  | 11/03/2027 |  |  | 11/10/2027 |  |  | 11/17/2027 |  |  | 11/24/2027
RPL9 | RPL9 DHC MP23/24 MFD2 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHC MP23/24 MFD2 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHC MP23/24 MFD2 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHC MP23/24 MFD2 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHC MP25/26 MFD3 | L2 – Infrastructure | 0 | Upcoming | 11/10/2027 | 12/10/2027 |  | 11/18/2027 |  |  | 11/25/2027 |  |  | 12/03/2027 |  |  | 12/10/2027
RPL9 | RPL9 DHC MP25/26 MFD3 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHC MP25/26 MFD3 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHC MP25/26 MFD3 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHC MP25/26 MFD3 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHC MP27/28 MFD4 | L2 – Infrastructure | 0 | Upcoming | 11/29/2027 | 12/27/2027 |  | 12/06/2027 |  |  | 12/13/2027 |  |  | 12/20/2027 |  |  | 12/27/2027
RPL9 | RPL9 DHC MP27/28 MFD4 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHC MP27/28 MFD4 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHC MP27/28 MFD4 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHC MP27/28 MFD4 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHD MP29/30 MFD1 | L2 – Infrastructure | 0 | Upcoming | 09/08/2027 | 10/05/2027 |  | 09/15/2027 |  |  | 09/22/2027 |  |  | 09/29/2027 |  |  | 10/05/2027
RPL9 | RPL9 DHD MP29/30 MFD1 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHD MP29/30 MFD1 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHD MP29/30 MFD1 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHD MP29/30 MFD1 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHD MP31/32 MFD2 | L2 – Infrastructure | 0 | Upcoming | 09/29/2027 | 10/26/2027 |  | 10/06/2027 |  |  | 10/13/2027 |  |  | 10/20/2027 |  |  | 10/26/2027
RPL9 | RPL9 DHD MP31/32 MFD2 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHD MP31/32 MFD2 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHD MP31/32 MFD2 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHD MP31/32 MFD2 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHD MP33/34 MFD3 | L2 – Infrastructure | 0 | Upcoming | 10/13/2027 | 11/09/2027 |  | 10/20/2027 |  |  | 10/27/2027 |  |  | 11/03/2027 |  |  | 11/09/2027
RPL9 | RPL9 DHD MP33/34 MFD3 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHD MP33/34 MFD3 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHD MP33/34 MFD3 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHD MP33/34 MFD3 | L5 – Punchlist | 0 | Not Started
RPL9 | RPL9 DHD MP35/36 MFD4 | L2 – Infrastructure | 0 | Upcoming | 10/27/2027 | 11/24/2027 |  | 11/03/2027 |  |  | 11/10/2027 |  |  | 11/17/2027 |  |  | 11/24/2027
RPL9 | RPL9 DHD MP35/36 MFD4 | L3 – ISP | 0 | Not Started
RPL9 | RPL9 DHD MP35/36 MFD4 | L3 – OSP | 0 | Not Started
RPL9 | RPL9 DHD MP35/36 MFD4 | L4 – Network | 0 | Not Started
RPL9 | RPL9 DHD MP35/36 MFD4 | L5 – Punchlist | 0 | Not Started
RPL8 | 8GSEF1 | L2 – Infrastructure | 0 | Upcoming | 04/06/2027 | 04/08/2027 |  |  |  |  | 04/07/2027 | [5 empty] | 04/08/2027
RPL8 | 8GSEF1 | L3 – ISP | 0 | Not Started
RPL8 | 8GSEF1 | L3 – OSP | 0 | Upcoming | 04/15/2027 | 04/20/2027 |  |  |  |  | 04/19/2027 | [5 empty] | 04/20/2027
RPL8 | 8GSEF1 | L4 – Network | 0 | Not Started
RPL8 | 8GSEF1 | L5 – Punchlist | 0 | Not Started
RPL8 | 8GSEF2 | L2 – Infrastructure | 0 | Upcoming | 04/06/2027 | 04/08/2027 |  |  |  |  | 04/07/2027 | [5 empty] | 04/08/2027
RPL8 | 8GSEF2 | L3 – ISP | 0 | Not Started
RPL8 | 8GSEF2 | L3 – OSP | 0 | Upcoming | 04/15/2027 | 04/20/2027 |  |  |  |  | 04/19/2027 | [5 empty] | 04/20/2027
RPL8 | 8GSEF2 | L4 – Network | 0 | Not Started
RPL8 | 8GSEF2 | L5 – Punchlist | 0 | Not Started
RPL8 | 8GSMDF1 | L2 – Infrastructure | 0 | Upcoming | 12/14/2026 | 12/16/2026 |  |  |  |  | 12/15/2026 | [5 empty] | 12/16/2026
RPL8 | 8GSMDF1 | L3 – ISP | 0 | Not Started
RPL8 | 8GSMDF1 | L3 – OSP | 0 | Not Started
RPL8 | 8GSMDF1 | L4 – Network | 0 | Not Started
RPL8 | 8GSMDF1 | L5 – Punchlist | 0 | Not Started
RPL8 | 8GSMDF2 | L2 – Infrastructure | 0 | Upcoming | 12/07/2026 | 12/09/2026 |  |  |  |  | 12/08/2026 | [5 empty] | 12/09/2026
RPL8 | 8GSMDF2 | L3 – ISP | 0 | Not Started
RPL8 | 8GSMDF2 | L3 – OSP | 0 | Not Started
RPL8 | 8GSMDF2 | L4 – Network | 0 | Not Started
RPL8 | 8GSMDF2 | L5 – Punchlist | 0 | Not Started
RPL8 | GSIDF8A1 | L2 – Infrastructure | 0 | Upcoming | 06/01/2027 | 06/07/2027 |  |  |  |  | 06/04/2027 | [5 empty] | 06/07/2027
RPL8 | GSIDF8A1 | L3 – ISP | 0 | Upcoming | 05/07/2027 | 05/24/2027 |  | 05/12/2027 |  |  | 05/17/2027 |  |  | 05/20/2027 |  |  | 05/24/2027
RPL8 | GSIDF8A1 | L3 – OSP | 0 | Upcoming | 05/07/2027 | 05/14/2027 |  |  |  |  | 05/11/2027 | [5 empty] | 05/14/2027
RPL8 | GSIDF8A1 | L4 – Network | 0 | Upcoming | 05/17/2027 | 05/19/2027 |  |  |  |  | 05/18/2027 | [5 empty] | 05/19/2027
RPL8 | GSIDF8A1 | L5 – Punchlist | 0 | Not Started
RPL8 | GSIDF8A2 | L2 – Infrastructure | 0 | Upcoming | 11/09/2026 | 11/16/2026 |  |  |  |  | 11/13/2026 | [5 empty] | 11/16/2026
RPL8 | GSIDF8A2 | L3 – ISP | 0 | Upcoming | 01/27/2027 | 02/11/2027 |  | 02/01/2027 |  |  | 02/04/2027 |  |  | 02/08/2027 |  |  | 02/11/2027
RPL8 | GSIDF8A2 | L3 – OSP | 0 | Upcoming | 01/27/2027 | 02/03/2027 |  |  |  |  | 02/01/2027 | [5 empty] | 02/03/2027
RPL8 | GSIDF8A2 | L4 – Network | 0 | Upcoming | 02/12/2027 | 02/17/2027 |  |  |  |  | 02/15/2027 | [5 empty] | 02/17/2027
RPL8 | GSIDF8A2 | L5 – Punchlist | 0 | Not Started
RPL8 | GSIDF8B1 | L2 – Infrastructure | 0 | Upcoming | 05/17/2027 | 05/21/2027 |  |  |  |  | 05/19/2027 | [5 empty] | 05/21/2027
RPL8 | GSIDF8B1 | L3 – ISP | 0 | Upcoming | 04/19/2027 | 05/04/2027 |  | 04/23/2027 |  |  | 04/27/2027 |  |  | 05/01/2027 |  |  | 05/04/2027
RPL8 | GSIDF8B1 | L3 – OSP | 0 | Upcoming | 04/19/2027 | 04/26/2027 |  |  |  |  | 04/23/2027 | [5 empty] | 04/26/2027
RPL8 | GSIDF8B1 | L4 – Network | 0 | Upcoming | 04/27/2027 | 04/29/2027 |  |  |  |  | 04/28/2027 | [5 empty] | 04/29/2027
RPL8 | GSIDF8B1 | L5 – Punchlist | 0 | Not Started
RPL8 | GSIDF8B2 | L2 – Infrastructure | 0 | Upcoming | 11/09/2026 | 11/16/2026 |  |  |  |  | 11/13/2026 | [5 empty] | 11/16/2026
RPL8 | GSIDF8B2 | L3 – ISP | 0 | Upcoming | 01/27/2027 | 02/11/2027 |  | 02/01/2027 |  |  | 02/04/2027 |  |  | 02/08/2027 |  |  | 02/11/2027
RPL8 | GSIDF8B2 | L3 – OSP | 0 | Upcoming | 01/27/2027 | 02/03/2027 |  |  |  |  | 02/01/2027 | [5 empty] | 02/03/2027
RPL8 | GSIDF8B2 | L4 – Network | 0 | Upcoming | 02/12/2027 | 02/17/2027 |  |  |  |  | 02/15/2027 | [5 empty] | 02/17/2027
RPL8 | GSIDF8B2 | L5 – Punchlist | 0 | Not Started
RPL8 | GSIDF8C1 | L2 – Infrastructure | 0 | Upcoming | 09/27/2027 | 10/01/2027 |  |  |  |  | 09/29/2027 | [5 empty] | 10/01/2027
RPL8 | GSIDF8C1 | L3 – ISP | 0 | Upcoming | 07/23/2027 | 08/09/2027 |  | 07/28/2027 |  |  | 08/02/2027 |  |  | 08/05/2027 |  |  | 08/09/2027
RPL8 | GSIDF8C1 | L3 – OSP | 0 | Upcoming | 07/23/2027 | 07/30/2027 |  |  |  |  | 07/27/2027 | [5 empty] | 07/30/2027
RPL8 | GSIDF8C1 | L4 – Network | 0 | Upcoming | 08/02/2027 | 08/04/2027 |  |  |  |  | 08/03/2027 | [5 empty] | 08/04/2027
RPL8 | GSIDF8C1 | L5 – Punchlist | 0 | Not Started
RPL8 | GSIDF8C2 | L2 – Infrastructure | 0 | Not Started
RPL8 | GSIDF8C2 | L3 – ISP | 0 | Upcoming | 02/22/2027 | 03/09/2027 |  | 02/26/2027 |  |  | 03/02/2027 |  |  | 03/06/2027 |  |  | 03/09/2027
RPL8 | GSIDF8C2 | L3 – OSP | 0 | Upcoming | 02/22/2027 | 03/01/2027 |  |  |  |  | 02/26/2027 | [5 empty] | 03/01/2027
RPL8 | GSIDF8C2 | L4 – Network | 0 | Upcoming | 03/02/2027 | 03/04/2027 |  |  |  |  | 03/03/2027 | [5 empty] | 03/04/2027
RPL8 | GSIDF8C2 | L5 – Punchlist | 0 | Not Started
RPL8 | GSIDF8C3 | L2 – Infrastructure | 0 | Not Started
RPL8 | GSIDF8C3 | L3 – ISP | 0 | Not Started
RPL8 | GSIDF8C3 | L3 – OSP | 0 | Not Started
RPL8 | GSIDF8C3 | L4 – Network | 0 | Not Started
RPL8 | GSIDF8C3 | L5 – Punchlist | 0 | Not Started
RPL8 | GSIDF8D1 | L2 – Infrastructure | 0 | Upcoming | 09/13/2027 | 09/17/2027 |  |  |  |  | 09/15/2027 | [5 empty] | 09/17/2027
RPL8 | GSIDF8D1 | L3 – ISP | 0 | Upcoming | 07/02/2027 | 07/20/2027 |  | 07/07/2027 |  |  | 07/12/2027 |  |  | 07/16/2027 |  |  | 07/20/2027
RPL8 | GSIDF8D1 | L3 – OSP | 0 | Upcoming | 07/02/2027 | 07/12/2027 |  | 07/05/2027 |  |  | 07/07/2027 |  |  | 07/10/2027 |  |  | 07/12/2027
RPL8 | GSIDF8D1 | L4 – Network | 0 | Upcoming | 07/13/2027 | 07/15/2027 |  |  |  |  | 07/14/2027 | [5 empty] | 07/15/2027
RPL8 | GSIDF8D1 | L5 – Punchlist | 0 | Not Started
RPL8 | GSIDF8D2 | L2 – Infrastructure | 0 | Upcoming | 02/19/2027 | 02/25/2027 |  |  |  |  | 02/22/2027 | [5 empty] | 02/25/2027
RPL8 | GSIDF8D2 | L3 – ISP | 0 | Upcoming | 03/01/2027 | 03/16/2027 |  | 03/05/2027 |  |  | 03/09/2027 |  |  | 03/13/2027 |  |  | 03/16/2027
RPL8 | GSIDF8D2 | L3 – OSP | 0 | Upcoming | 03/01/2027 | 03/08/2027 |  |  |  |  | 03/05/2027 | [5 empty] | 03/08/2027
RPL8 | GSIDF8D2 | L4 – Network | 0 | Upcoming | 03/09/2027 | 03/11/2027 |  |  |  |  | 03/10/2027 | [5 empty] | 03/11/2027
RPL8 | GSIDF8D2 | L5 – Punchlist | 0 | Not Started
RPL8 | GSIDF8D3 | L2 – Infrastructure | 0 | Not Started
RPL8 | GSIDF8D3 | L3 – ISP | 0 | Not Started
RPL8 | GSIDF8D3 | L3 – OSP | 0 | Not Started
RPL8 | GSIDF8D3 | L4 – Network | 0 | Not Started
RPL8 | GSIDF8D3 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHA MP01/02 MFD1 | L2 – Infrastructure | 0 | Upcoming | 04/21/2027 | 05/18/2027 |  | 04/28/2027 |  |  | 05/05/2027 |  |  | 05/12/2027 |  |  | 05/18/2027
RPL8 | RPL8 DHA MP01/02 MFD1 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHA MP01/02 MFD1 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHA MP01/02 MFD1 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHA MP01/02 MFD1 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHA MP03/04 MFD2 | L2 – Infrastructure | 0 | Upcoming | 05/12/2027 | 06/09/2027 |  | 05/19/2027 |  |  | 05/26/2027 |  |  | 06/02/2027 |  |  | 06/09/2027
RPL8 | RPL8 DHA MP03/04 MFD2 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHA MP03/04 MFD2 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHA MP03/04 MFD2 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHA MP03/04 MFD2 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHA MP05/06 MFD3 | L2 – Infrastructure | 0 | Upcoming | 05/26/2027 | 06/23/2027 |  | 06/02/2027 |  |  | 06/09/2027 |  |  | 06/16/2027 |  |  | 06/23/2027
RPL8 | RPL8 DHA MP05/06 MFD3 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHA MP05/06 MFD3 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHA MP05/06 MFD3 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHA MP05/06 MFD3 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHA MP07/08 MFD4 | L2 – Infrastructure | 0 | Upcoming | 06/10/2027 | 07/08/2027 |  | 06/17/2027 |  |  | 06/24/2027 |  |  | 07/01/2027 |  |  | 07/08/2027
RPL8 | RPL8 DHA MP07/08 MFD4 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHA MP07/08 MFD4 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHA MP07/08 MFD4 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHA MP07/08 MFD4 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHA MP09/10 MFD5 | L2 – Infrastructure | 0 | Upcoming | 06/28/2027 | 07/26/2027 |  | 07/05/2027 |  |  | 07/12/2027 |  |  | 07/19/2027 |  |  | 07/26/2027
RPL8 | RPL8 DHA MP09/10 MFD5 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHA MP09/10 MFD5 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHA MP09/10 MFD5 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHA MP09/10 MFD5 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHB MP11/12 MFD1 | L2 – Infrastructure | 0 | Upcoming | 04/02/2027 | 04/29/2027 |  | 04/09/2027 |  |  | 04/16/2027 |  |  | 04/23/2027 |  |  | 04/29/2027
RPL8 | RPL8 DHB MP11/12 MFD1 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHB MP11/12 MFD1 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHB MP11/12 MFD1 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHB MP11/12 MFD1 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHB MP13/14 MFD2 | L2 – Infrastructure | 0 | Upcoming | 04/23/2027 | 05/20/2027 |  | 04/30/2027 |  |  | 05/07/2027 |  |  | 05/14/2027 |  |  | 05/20/2027
RPL8 | RPL8 DHB MP13/14 MFD2 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHB MP13/14 MFD2 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHB MP13/14 MFD2 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHB MP13/14 MFD2 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHB MP15/16 MFD3 | L2 – Infrastructure | 0 | Upcoming | 05/07/2027 | 06/04/2027 |  | 05/14/2027 |  |  | 05/21/2027 |  |  | 05/28/2027 |  |  | 06/04/2027
RPL8 | RPL8 DHB MP15/16 MFD3 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHB MP15/16 MFD3 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHB MP15/16 MFD3 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHB MP15/16 MFD3 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHB MP17/18 MFD4 | L2 – Infrastructure | 0 | Upcoming | 05/21/2027 | 06/18/2027 |  | 05/28/2027 |  |  | 06/04/2027 |  |  | 06/11/2027 |  |  | 06/18/2027
RPL8 | RPL8 DHB MP17/18 MFD4 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHB MP17/18 MFD4 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHB MP17/18 MFD4 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHB MP17/18 MFD4 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHB MP19/20 MFD5 | L2 – Infrastructure | 0 | Upcoming | 06/09/2027 | 07/07/2027 |  | 06/16/2027 |  |  | 06/23/2027 |  |  | 06/30/2027 |  |  | 07/07/2027
RPL8 | RPL8 DHB MP19/20 MFD5 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHB MP19/20 MFD5 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHB MP19/20 MFD5 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHB MP19/20 MFD5 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHC MP21/22 MFD1 | L2 – Infrastructure | 0 | Upcoming | 07/07/2027 | 08/03/2027 |  | 07/14/2027 |  |  | 07/21/2027 |  |  | 07/28/2027 |  |  | 08/03/2027
RPL8 | RPL8 DHC MP21/22 MFD1 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHC MP21/22 MFD1 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHC MP21/22 MFD1 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHC MP21/22 MFD1 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHC MP23/24 MFD2 | L2 – Infrastructure | 0 | Upcoming | 07/28/2027 | 08/24/2027 |  | 08/04/2027 |  |  | 08/11/2027 |  |  | 08/18/2027 |  |  | 08/24/2027
RPL8 | RPL8 DHC MP23/24 MFD2 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHC MP23/24 MFD2 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHC MP23/24 MFD2 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHC MP23/24 MFD2 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHC MP25/26 MFD3 | L2 – Infrastructure | 0 | Upcoming | 08/11/2027 | 09/08/2027 |  | 08/18/2027 |  |  | 08/25/2027 |  |  | 09/01/2027 |  |  | 09/08/2027
RPL8 | RPL8 DHC MP25/26 MFD3 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHC MP25/26 MFD3 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHC MP25/26 MFD3 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHC MP25/26 MFD3 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHC MP27/28 MFD4 | L2 – Infrastructure | 0 | Upcoming | 08/25/2027 | 09/22/2027 |  | 09/01/2027 |  |  | 09/08/2027 |  |  | 09/15/2027 |  |  | 09/22/2027
RPL8 | RPL8 DHC MP27/28 MFD4 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHC MP27/28 MFD4 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHC MP27/28 MFD4 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHC MP27/28 MFD4 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHD MP29/30 MFD1 | L2 – Infrastructure | 0 | Upcoming | 06/17/2027 | 07/15/2027 |  | 06/24/2027 |  |  | 07/01/2027 |  |  | 07/08/2027 |  |  | 07/15/2027
RPL8 | RPL8 DHD MP29/30 MFD1 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHD MP29/30 MFD1 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHD MP29/30 MFD1 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHD MP29/30 MFD1 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHD MP31/32 MFD2 | L2 – Infrastructure | 0 | Upcoming | 07/09/2027 | 08/05/2027 |  | 07/16/2027 |  |  | 07/23/2027 |  |  | 07/30/2027 |  |  | 08/05/2027
RPL8 | RPL8 DHD MP31/32 MFD2 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHD MP31/32 MFD2 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHD MP31/32 MFD2 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHD MP31/32 MFD2 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHD MP33/34 MFD3 | L2 – Infrastructure | 0 | Upcoming | 07/23/2027 | 08/19/2027 |  | 07/30/2027 |  |  | 08/06/2027 |  |  | 08/13/2027 |  |  | 08/19/2027
RPL8 | RPL8 DHD MP33/34 MFD3 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHD MP33/34 MFD3 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHD MP33/34 MFD3 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHD MP33/34 MFD3 | L5 – Punchlist | 0 | Not Started
RPL8 | RPL8 DHD MP35/36 MFD4 | L2 – Infrastructure | 0 | Upcoming | 08/06/2027 | 09/02/2027 |  | 08/13/2027 |  |  | 08/20/2027 |  |  | 08/27/2027 |  |  | 09/02/2027
RPL8 | RPL8 DHD MP35/36 MFD4 | L3 – ISP | 0 | Not Started
RPL8 | RPL8 DHD MP35/36 MFD4 | L3 – OSP | 0 | Not Started
RPL8 | RPL8 DHD MP35/36 MFD4 | L4 – Network | 0 | Not Started
RPL8 | RPL8 DHD MP35/36 MFD4 | L5 – Punchlist | 0 | Not Started
RPL7 | 7GSEF1 | L2 – Infrastructure | 0 | Upcoming | 11/23/2026 | 11/25/2026 |  |  |  |  | 11/24/2026 | [5 empty] | 11/25/2026
RPL7 | 7GSEF1 | L3 – ISP | 0 | Not Started
RPL7 | 7GSEF1 | L3 – OSP | 0 | Upcoming | 11/30/2026 | 12/03/2026 |  |  |  |  | 12/02/2026 | [5 empty] | 12/03/2026
RPL7 | 7GSEF1 | L4 – Network | 0 | Not Started
RPL7 | 7GSEF1 | L5 – Punchlist | 0 | Not Started
RPL7 | 7GSEF2 | L2 – Infrastructure | 0 | Upcoming | 11/23/2026 | 11/25/2026 |  |  |  |  | 11/24/2026 | [5 empty] | 11/25/2026
RPL7 | 7GSEF2 | L3 – ISP | 0 | Not Started
RPL7 | 7GSEF2 | L3 – OSP | 0 | Upcoming | 11/30/2026 | 12/03/2026 |  |  |  |  | 12/02/2026 | [5 empty] | 12/03/2026
RPL7 | 7GSEF2 | L4 – Network | 0 | Not Started
RPL7 | 7GSEF2 | L5 – Punchlist | 0 | Not Started
RPL7 | 7GSMDF1 | L2 – Infrastructure | 0 | Upcoming | 10/01/2026 | 10/05/2026 |  |  |  |  | 10/03/2026 | [5 empty] | 10/05/2026
RPL7 | 7GSMDF1 | L3 – ISP | 0 | Not Started
RPL7 | 7GSMDF1 | L3 – OSP | 0 | Not Started
RPL7 | 7GSMDF1 | L4 – Network | 0 | Not Started
RPL7 | 7GSMDF1 | L5 – Punchlist | 0 | Not Started
RPL7 | 7GSMDF2 | L2 – Infrastructure | 0 | Upcoming | 09/24/2026 | 09/28/2026 |  |  |  |  | 09/26/2026 | [5 empty] | 09/28/2026
RPL7 | 7GSMDF2 | L3 – ISP | 0 | Not Started
RPL7 | 7GSMDF2 | L3 – OSP | 0 | Not Started
RPL7 | 7GSMDF2 | L4 – Network | 0 | Not Started
RPL7 | 7GSMDF2 | L5 – Punchlist | 0 | Not Started
RPL7 | GSIDF7A1 | L2 – Infrastructure | 0 | Upcoming | 01/26/2027 | 02/01/2027 |  |  |  |  | 01/29/2027 | [5 empty] | 02/01/2027
RPL7 | GSIDF7A1 | L3 – ISP | 0 | Upcoming | 02/03/2027 | 02/19/2027 |  | 02/08/2027 |  |  | 02/11/2027 |  |  | 02/15/2027 |  |  | 02/19/2027
RPL7 | GSIDF7A1 | L3 – OSP | 0 | Upcoming | 02/03/2027 | 02/10/2027 |  |  |  |  | 02/08/2027 | [5 empty] | 02/10/2027
RPL7 | GSIDF7A1 | L4 – Network | 0 | Upcoming | 02/11/2027 | 02/16/2027 |  |  |  |  | 02/15/2027 | [5 empty] | 02/16/2027
RPL7 | GSIDF7A1 | L5 – Punchlist | 0 | Not Started
RPL7 | GSIDF7A2 | L2 – Infrastructure | 0 | Upcoming | 08/11/2026 | 08/17/2026 |  |  |  |  | 08/14/2026 | [5 empty] | 08/17/2026
RPL7 | GSIDF7A2 | L3 – ISP | 0 | Upcoming | 09/30/2026 | 10/15/2026 |  | 10/05/2026 |  |  | 10/08/2026 |  |  | 10/12/2026 |  |  | 10/15/2026
RPL7 | GSIDF7A2 | L3 – OSP | 0 | Upcoming | 09/30/2026 | 10/07/2026 |  |  |  |  | 10/05/2026 | [5 empty] | 10/07/2026
RPL7 | GSIDF7A2 | L4 – Network | 0 | Upcoming | 10/16/2026 | 10/20/2026 |  |  |  |  | 10/19/2026 | [5 empty] | 10/20/2026
RPL7 | GSIDF7A2 | L5 – Punchlist | 0 | Not Started
RPL7 | GSIDF7B1 | L2 – Infrastructure | 0 | Upcoming | 01/11/2027 | 01/15/2027 |  |  |  |  | 01/13/2027 | [5 empty] | 01/15/2027
RPL7 | GSIDF7B1 | L3 – ISP | 0 | Upcoming | 01/20/2027 | 02/04/2027 |  | 01/25/2027 |  |  | 01/28/2027 |  |  | 02/01/2027 |  |  | 02/04/2027
RPL7 | GSIDF7B1 | L3 – OSP | 0 | Upcoming | 01/20/2027 | 01/27/2027 |  |  |  |  | 01/25/2027 | [5 empty] | 01/27/2027
RPL7 | GSIDF7B1 | L4 – Network | 0 | Upcoming | 01/28/2027 | 02/01/2027 |  |  |  |  | 01/30/2027 | [5 empty] | 02/01/2027
RPL7 | GSIDF7B1 | L5 – Punchlist | 0 | Not Started
RPL7 | GSIDF7B2 | L2 – Infrastructure | 0 | Upcoming | 08/11/2026 | 08/17/2026 |  |  |  |  | 08/14/2026 | [5 empty] | 08/17/2026
RPL7 | GSIDF7B2 | L3 – ISP | 0 | Upcoming | 09/30/2026 | 10/15/2026 |  | 10/05/2026 |  |  | 10/08/2026 |  |  | 10/12/2026 |  |  | 10/15/2026
RPL7 | GSIDF7B2 | L3 – OSP | 0 | Upcoming | 09/30/2026 | 10/07/2026 |  |  |  |  | 10/05/2026 | [5 empty] | 10/07/2026
RPL7 | GSIDF7B2 | L4 – Network | 0 | Upcoming | 10/16/2026 | 10/20/2026 |  |  |  |  | 10/19/2026 | [5 empty] | 10/20/2026
RPL7 | GSIDF7B2 | L5 – Punchlist | 0 | Not Started
RPL7 | GSIDF7C1 | L2 – Infrastructure | 0 | Upcoming | 05/26/2027 | 06/02/2027 |  |  |  |  | 05/31/2027 | [5 empty] | 06/02/2027
RPL7 | GSIDF7C1 | L3 – ISP | 0 | Upcoming | 05/14/2027 | 06/01/2027 |  | 05/19/2027 |  |  | 05/24/2027 |  |  | 05/28/2027 |  |  | 06/01/2027
RPL7 | GSIDF7C1 | L3 – OSP | 0 | Upcoming | 05/14/2027 | 05/21/2027 |  |  |  |  | 05/18/2027 | [5 empty] | 05/21/2027
RPL7 | GSIDF7C1 | L4 – Network | 0 | Upcoming | 05/24/2027 | 05/26/2027 |  |  |  |  | 05/25/2027 | [5 empty] | 05/26/2027
RPL7 | GSIDF7C1 | L5 – Punchlist | 0 | Not Started
RPL7 | GSIDF7C2 | L2 – Infrastructure | 0 | Upcoming | 10/19/2026 | 10/23/2026 |  |  |  |  | 10/21/2026 | [5 empty] | 10/23/2026
RPL7 | GSIDF7C2 | L3 – ISP | 0 | Upcoming | 10/30/2026 | 11/17/2026 |  | 11/04/2026 |  |  | 11/09/2026 |  |  | 11/13/2026 |  |  | 11/17/2026
RPL7 | GSIDF7C2 | L3 – OSP | 0 | Upcoming | 10/30/2026 | 11/06/2026 |  |  |  |  | 11/03/2026 | [5 empty] | 11/06/2026
RPL7 | GSIDF7C2 | L4 – Network | 0 | Upcoming | 11/09/2026 | 11/12/2026 |  |  |  |  | 11/11/2026 | [5 empty] | 11/12/2026
RPL7 | GSIDF7C2 | L5 – Punchlist | 0 | Not Started
RPL7 | GSIDF7C3 | L2 – Infrastructure | 0 | Not Started
RPL7 | GSIDF7C3 | L3 – ISP | 0 | Not Started
RPL7 | GSIDF7C3 | L3 – OSP | 0 | Not Started
RPL7 | GSIDF7C3 | L4 – Network | 0 | Not Started
RPL7 | GSIDF7C3 | L5 – Punchlist | 0 | Not Started
RPL7 | GSIDF7D1 | L2 – Infrastructure | 0 | Upcoming | 05/10/2027 | 05/14/2027 |  |  |  |  | 05/12/2027 | [5 empty] | 05/14/2027
RPL7 | GSIDF7D1 | L3 – ISP | 0 | Upcoming | 04/28/2027 | 05/13/2027 |  | 05/03/2027 |  |  | 05/06/2027 |  |  | 05/10/2027 |  |  | 05/13/2027
RPL7 | GSIDF7D1 | L3 – OSP | 0 | Upcoming | 04/28/2027 | 05/05/2027 |  |  |  |  | 05/03/2027 | [5 empty] | 05/05/2027
RPL7 | GSIDF7D1 | L4 – Network | 0 | Upcoming | 05/06/2027 | 05/10/2027 |  |  |  |  | 05/08/2027 | [5 empty] | 05/10/2027
RPL7 | GSIDF7D1 | L5 – Punchlist | 0 | Not Started
RPL7 | GSIDF7D2 | L2 – Infrastructure | 0 | Upcoming | 10/26/2026 | 10/30/2026 |  |  |  |  | 10/28/2026 | [5 empty] | 10/30/2026
RPL7 | GSIDF7D2 | L3 – ISP | 0 | Upcoming | 11/06/2026 | 11/24/2026 |  | 11/11/2026 |  |  | 11/16/2026 |  |  | 11/20/2026 |  |  | 11/24/2026
RPL7 | GSIDF7D2 | L3 – OSP | 0 | Upcoming | 11/06/2026 | 11/16/2026 |  | 11/09/2026 |  |  | 11/11/2026 |  |  | 11/14/2026 |  |  | 11/16/2026
RPL7 | GSIDF7D2 | L4 – Network | 0 | Upcoming | 11/17/2026 | 11/19/2026 |  |  |  |  | 11/18/2026 | [5 empty] | 11/19/2026
RPL7 | GSIDF7D2 | L5 – Punchlist | 0 | Not Started
RPL7 | GSIDF7D3 | L2 – Infrastructure | 0 | Not Started
RPL7 | GSIDF7D3 | L3 – ISP | 0 | Not Started
RPL7 | GSIDF7D3 | L3 – OSP | 0 | Not Started
RPL7 | GSIDF7D3 | L4 – Network | 0 | Not Started
RPL7 | GSIDF7D3 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHA MP01/02 MFD1 | L2 – Infrastructure | 0 | Upcoming | 12/11/2026 | 01/11/2027 |  | 12/19/2026 |  |  | 12/28/2026 |  |  | 01/04/2027 |  |  | 01/11/2027
RPL7 | RPL7 DHA MP01/02 MFD1 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHA MP01/02 MFD1 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHA MP01/02 MFD1 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHA MP01/02 MFD1 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHA MP03/04 MFD2 | L2 – Infrastructure | 0 | Upcoming | 01/12/2027 | 02/09/2027 |  | 01/19/2027 |  |  | 01/26/2027 |  |  | 02/02/2027 |  |  | 02/09/2027
RPL7 | RPL7 DHA MP03/04 MFD2 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHA MP03/04 MFD2 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHA MP03/04 MFD2 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHA MP03/04 MFD2 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHA MP05/06 MFD3 | L2 – Infrastructure | 0 | Upcoming | 02/03/2027 | 03/03/2027 |  | 02/10/2027 |  |  | 02/17/2027 |  |  | 02/24/2027 |  |  | 03/03/2027
RPL7 | RPL7 DHA MP05/06 MFD3 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHA MP05/06 MFD3 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHA MP05/06 MFD3 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHA MP05/06 MFD3 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHA MP07/08 MFD4 | L2 – Infrastructure | 0 | Upcoming | 02/25/2027 | 03/24/2027 |  | 03/04/2027 |  |  | 03/11/2027 |  |  | 03/18/2027 |  |  | 03/24/2027
RPL7 | RPL7 DHA MP07/08 MFD4 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHA MP07/08 MFD4 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHA MP07/08 MFD4 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHA MP07/08 MFD4 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHA MP09/10 MFD5 | L2 – Infrastructure | 0 | Upcoming | 03/22/2027 | 04/19/2027 |  | 03/29/2027 |  |  | 04/05/2027 |  |  | 04/12/2027 |  |  | 04/19/2027
RPL7 | RPL7 DHA MP09/10 MFD5 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHA MP09/10 MFD5 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHA MP09/10 MFD5 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHA MP09/10 MFD5 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHB MP11/12 MFD1 | L2 – Infrastructure | 0 | Upcoming | 11/25/2026 | 12/24/2026 |  | 12/03/2026 |  |  | 12/10/2026 |  |  | 12/17/2026 |  |  | 12/24/2026
RPL7 | RPL7 DHB MP11/12 MFD1 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHB MP11/12 MFD1 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHB MP11/12 MFD1 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHB MP11/12 MFD1 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHB MP13/14 MFD2 | L2 – Infrastructure | 0 | Upcoming | 12/28/2026 | 01/26/2027 |  | 01/05/2027 |  |  | 01/12/2027 |  |  | 01/19/2027 |  |  | 01/26/2027
RPL7 | RPL7 DHB MP13/14 MFD2 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHB MP13/14 MFD2 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHB MP13/14 MFD2 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHB MP13/14 MFD2 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHB MP15/16 MFD3 | L2 – Infrastructure | 0 | Upcoming | 01/20/2027 | 02/17/2027 |  | 01/27/2027 |  |  | 02/03/2027 |  |  | 02/10/2027 |  |  | 02/17/2027
RPL7 | RPL7 DHB MP15/16 MFD3 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHB MP15/16 MFD3 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHB MP15/16 MFD3 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHB MP15/16 MFD3 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHB MP17/18 MFD4 | L2 – Infrastructure | 0 | Upcoming | 02/10/2027 | 03/10/2027 |  | 02/17/2027 |  |  | 02/24/2027 |  |  | 03/03/2027 |  |  | 03/10/2027
RPL7 | RPL7 DHB MP17/18 MFD4 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHB MP17/18 MFD4 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHB MP17/18 MFD4 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHB MP17/18 MFD4 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHB MP19/20 MFD5 | L2 – Infrastructure | 0 | Upcoming | 03/08/2027 | 04/05/2027 |  | 03/15/2027 |  |  | 03/22/2027 |  |  | 03/29/2027 |  |  | 04/05/2027
RPL7 | RPL7 DHB MP19/20 MFD5 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHB MP19/20 MFD5 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHB MP19/20 MFD5 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHB MP19/20 MFD5 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHC MP21/22 MFD1 | L2 – Infrastructure | 0 | Upcoming | 04/09/2027 | 05/06/2027 |  | 04/16/2027 |  |  | 04/23/2027 |  |  | 04/30/2027 |  |  | 05/06/2027
RPL7 | RPL7 DHC MP21/22 MFD1 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHC MP21/22 MFD1 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHC MP21/22 MFD1 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHC MP21/22 MFD1 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHC MP23/24 MFD2 | L2 – Infrastructure | 0 | Upcoming | 04/30/2027 | 05/27/2027 |  | 05/07/2027 |  |  | 05/14/2027 |  |  | 05/21/2027 |  |  | 05/27/2027
RPL7 | RPL7 DHC MP23/24 MFD2 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHC MP23/24 MFD2 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHC MP23/24 MFD2 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHC MP23/24 MFD2 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHC MP25/26 MFD3 | L2 – Infrastructure | 0 | Upcoming | 05/14/2027 | 06/11/2027 |  | 05/21/2027 |  |  | 05/28/2027 |  |  | 06/04/2027 |  |  | 06/11/2027
RPL7 | RPL7 DHC MP25/26 MFD3 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHC MP25/26 MFD3 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHC MP25/26 MFD3 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHC MP25/26 MFD3 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHC MP27/28 MFD4 | L2 – Infrastructure | 0 | Upcoming | 05/26/2027 | 06/23/2027 |  | 06/02/2027 |  |  | 06/09/2027 |  |  | 06/16/2027 |  |  | 06/23/2027
RPL7 | RPL7 DHC MP27/28 MFD4 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHC MP27/28 MFD4 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHC MP27/28 MFD4 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHC MP27/28 MFD4 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHD MP29/30 MFD1 | L2 – Infrastructure | 0 | Upcoming | 03/23/2027 | 04/20/2027 |  | 03/30/2027 |  |  | 04/06/2027 |  |  | 04/13/2027 |  |  | 04/20/2027
RPL7 | RPL7 DHD MP29/30 MFD1 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHD MP29/30 MFD1 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHD MP29/30 MFD1 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHD MP29/30 MFD1 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHD MP31/32 MFD2 | L2 – Infrastructure | 0 | Upcoming | 04/14/2027 | 05/11/2027 |  | 04/21/2027 |  |  | 04/28/2027 |  |  | 05/05/2027 |  |  | 05/11/2027
RPL7 | RPL7 DHD MP31/32 MFD2 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHD MP31/32 MFD2 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHD MP31/32 MFD2 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHD MP31/32 MFD2 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHD MP33/34 MFD3 | L2 – Infrastructure | 0 | Upcoming | 04/28/2027 | 05/25/2027 |  | 05/05/2027 |  |  | 05/12/2027 |  |  | 05/19/2027 |  |  | 05/25/2027
RPL7 | RPL7 DHD MP33/34 MFD3 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHD MP33/34 MFD3 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHD MP33/34 MFD3 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHD MP33/34 MFD3 | L5 – Punchlist | 0 | Not Started
RPL7 | RPL7 DHD MP35/36 MFD4 | L2 – Infrastructure | 0 | Upcoming | 05/12/2027 | 06/09/2027 |  | 05/19/2027 |  |  | 05/26/2027 |  |  | 06/02/2027 |  |  | 06/09/2027
RPL7 | RPL7 DHD MP35/36 MFD4 | L3 – ISP | 0 | Not Started
RPL7 | RPL7 DHD MP35/36 MFD4 | L3 – OSP | 0 | Not Started
RPL7 | RPL7 DHD MP35/36 MFD4 | L4 – Network | 0 | Not Started
RPL7 | RPL7 DHD MP35/36 MFD4 | L5 – Punchlist | 0 | Not Started
RPL6 | 6GSEF1 | L2 – Infrastructure | 0 | Upcoming | 06/09/2026 | 06/11/2026 |  |  |  |  | 06/10/2026 | [5 empty] | 06/11/2026
RPL6 | 6GSEF1 | L3 – ISP | 0 | Not Started
RPL6 | 6GSEF1 | L3 – OSP | 0 | Upcoming | 10/08/2026 | 10/13/2026 |  |  |  |  | 10/12/2026 | [5 empty] | 10/13/2026
RPL6 | 6GSEF1 | L4 – Network | 0 | Not Started
RPL6 | 6GSEF1 | L5 – Punchlist | 0 | Not Started
RPL6 | 6GSEF2 | L2 – Infrastructure | 0 | Upcoming | 06/09/2026 | 06/11/2026 |  |  |  |  | 06/10/2026 | [5 empty] | 06/11/2026
RPL6 | 6GSEF2 | L3 – ISP | 0 | Not Started
RPL6 | 6GSEF2 | L3 – OSP | 0 | Upcoming | 10/08/2026 | 10/12/2026 |  |  |  |  | 10/10/2026 | [5 empty] | 10/12/2026
RPL6 | 6GSEF2 | L4 – Network | 0 | Not Started
RPL6 | 6GSEF2 | L5 – Punchlist | 0 | Not Started
RPL6 | 6GSMDF1 | L2 – Infrastructure | 0 | Upcoming | 06/16/2026 | 06/16/2026 |  |  |  |  | 06/16/2026 | [5 empty] | 06/17/2026
RPL6 | 6GSMDF1 | L3 – ISP | 0 | Not Started
RPL6 | 6GSMDF1 | L3 – OSP | 0 | Upcoming | 06/17/2026 | 06/19/2026 |  |  |  |  | 06/18/2026 | [5 empty] | 06/19/2026
RPL6 | 6GSMDF1 | L4 – Network | 0 | Not Started
RPL6 | 6GSMDF1 | L5 – Punchlist | 0 | Not Started
RPL6 | 6GSMDF2 | L2 – Infrastructure | 0 | Upcoming | 06/09/2026 | 06/09/2026 |  |  |  |  | 06/09/2026 | [5 empty] | 06/10/2026
RPL6 | 6GSMDF2 | L3 – ISP | 0 | Not Started
RPL6 | 6GSMDF2 | L3 – OSP | 0 | Upcoming | 06/12/2026 | 06/17/2026 |  |  |  |  | 06/15/2026 | [5 empty] | 06/17/2026
RPL6 | 6GSMDF2 | L4 – Network | 0 | Not Started
RPL6 | 6GSMDF2 | L5 – Punchlist | 0 | Not Started
RPL6 | GSIDF6A1 | L2 – Infrastructure | 0 | Upcoming | 11/25/2026 | 12/02/2026 |  |  |  |  | 11/30/2026 | [5 empty] | 12/02/2026
RPL6 | GSIDF6A1 | L3 – ISP | 0 | Upcoming | 11/09/2026 | 11/20/2026 |  | 11/12/2026 |  |  | 11/16/2026 |  |  | 11/18/2026 |  |  | 11/20/2026
RPL6 | GSIDF6A1 | L3 – OSP | 0 | Upcoming | 11/09/2026 | 11/17/2026 |  | 11/11/2026 |  |  | 11/13/2026 |  |  | 11/16/2026 |  |  | 11/17/2026
RPL6 | GSIDF6A1 | L4 – Network | 0 | Upcoming | 11/18/2026 | 11/19/2026 |  |  |  |  | 11/19/2026 | [5 empty] | 11/20/2026
RPL6 | GSIDF6A1 | L5 – Punchlist | 0 | Not Started
RPL6 | GSIDF6A2 | L2 – Infrastructure | 0 | Upcoming | 07/27/2026 | 07/29/2026 |  |  |  |  | 07/28/2026 | [5 empty] | 07/29/2026
RPL6 | GSIDF6A2 | L3 – ISP | 0 | Upcoming | 07/16/2026 | 07/28/2026 |  | 07/20/2026 |  |  | 07/22/2026 |  |  | 07/25/2026 |  |  | 07/28/2026
RPL6 | GSIDF6A2 | L3 – OSP | 0 | Upcoming | 07/16/2026 | 07/23/2026 |  |  |  |  | 07/20/2026 | [5 empty] | 07/23/2026
RPL6 | GSIDF6A2 | L4 – Network | 0 | Upcoming | 07/29/2026 | 07/30/2026 |  |  |  |  | 07/30/2026 | [5 empty] | 07/31/2026
RPL6 | GSIDF6A2 | L5 – Punchlist | 0 | Not Started
RPL6 | GSIDF6B1 | L2 – Infrastructure | 0 | Upcoming | 11/10/2026 | 11/16/2026 |  |  |  |  | 11/13/2026 | [5 empty] | 11/16/2026
RPL6 | GSIDF6B1 | L3 – ISP | 0 | Upcoming | 10/26/2026 | 11/05/2026 |  | 10/29/2026 |  |  | 10/31/2026 |  |  | 11/03/2026 |  |  | 11/05/2026
RPL6 | GSIDF6B1 | L3 – OSP | 0 | Upcoming | 10/26/2026 | 11/02/2026 |  |  |  |  | 10/30/2026 | [5 empty] | 11/02/2026
RPL6 | GSIDF6B1 | L4 – Network | 0 | Upcoming | 11/03/2026 | 11/04/2026 |  |  |  |  | 11/04/2026 | [5 empty] | 11/05/2026
RPL6 | GSIDF6B1 | L5 – Punchlist | 0 | Not Started
RPL6 | GSIDF6B2 | L2 – Infrastructure | 0 | Upcoming | 07/27/2026 | 07/29/2026 |  |  |  |  | 07/28/2026 | [5 empty] | 07/29/2026
RPL6 | GSIDF6B2 | L3 – ISP | 0 | Upcoming | 07/16/2026 | 07/28/2026 |  | 07/20/2026 |  |  | 07/22/2026 |  |  | 07/25/2026 |  |  | 07/28/2026
RPL6 | GSIDF6B2 | L3 – OSP | 0 | Upcoming | 07/16/2026 | 07/23/2026 |  |  |  |  | 07/20/2026 | [5 empty] | 07/23/2026
RPL6 | GSIDF6B2 | L4 – Network | 0 | Upcoming | 07/29/2026 | 07/30/2026 |  |  |  |  | 07/30/2026 | [5 empty] | 07/31/2026
RPL6 | GSIDF6B2 | L5 – Punchlist | 0 | Not Started
RPL6 | GSIDF6C1 | L2 – Infrastructure | 0 | Upcoming | 02/25/2027 | 03/02/2027 |  |  |  |  | 03/01/2027 | [5 empty] | 03/02/2027
RPL6 | GSIDF6C1 | L3 – ISP | 0 | Upcoming | 02/09/2027 | 02/22/2027 |  | 02/13/2027 |  |  | 02/16/2027 |  |  | 02/19/2027 |  |  | 02/22/2027
RPL6 | GSIDF6C1 | L3 – OSP | 0 | Upcoming | 02/09/2027 | 02/17/2027 |  | 02/11/2027 |  |  | 02/13/2027 |  |  | 02/15/2027 |  |  | 02/17/2027
RPL6 | GSIDF6C1 | L4 – Network | 0 | Upcoming | 02/18/2027 | 02/19/2027 |  |  |  |  | 02/19/2027 | [5 empty] | 02/20/2027
RPL6 | GSIDF6C1 | L5 – Punchlist | 0 | Not Started
RPL6 | GSIDF6C2 | L2 – Infrastructure | 0 | Upcoming | 09/08/2026 | 09/08/2026 |  |  |  |  | 09/08/2026 | [5 empty] | 09/09/2026
RPL6 | GSIDF6C2 | L3 – ISP | 0 | Upcoming | 08/28/2026 | 09/10/2026 |  | 09/01/2026 |  |  | 09/04/2026 |  |  | 09/07/2026 |  |  | 09/10/2026
RPL6 | GSIDF6C2 | L3 – OSP | 0 | Upcoming | 08/28/2026 | 09/04/2026 |  |  |  |  | 09/01/2026 | [5 empty] | 09/04/2026
RPL6 | GSIDF6C2 | L4 – Network | 0 | Upcoming | 09/08/2026 | 09/09/2026 |  |  |  |  | 09/09/2026 | [5 empty] | 09/10/2026
RPL6 | GSIDF6C2 | L5 – Punchlist | 0 | Not Started
RPL6 | GSIDF6C3 | L2 – Infrastructure | 0 | Not Started
RPL6 | GSIDF6C3 | L3 – ISP | 0 | Not Started
RPL6 | GSIDF6C3 | L3 – OSP | 0 | Not Started
RPL6 | GSIDF6C3 | L4 – Network | 0 | Not Started
RPL6 | GSIDF6C3 | L5 – Punchlist | 0 | Not Started
RPL6 | GSIDF6D1 | L2 – Infrastructure | 0 | Upcoming | 02/10/2027 | 02/16/2027 |  |  |  |  | 02/13/2027 | [5 empty] | 02/16/2027
RPL6 | GSIDF6D1 | L3 – ISP | 0 | Upcoming | 01/26/2027 | 02/05/2027 |  | 01/29/2027 |  |  | 02/01/2027 |  |  | 02/03/2027 |  |  | 02/05/2027
RPL6 | GSIDF6D1 | L3 – OSP | 0 | Upcoming | 01/26/2027 | 02/02/2027 |  |  |  |  | 01/30/2027 | [5 empty] | 02/02/2027
RPL6 | GSIDF6D1 | L4 – Network | 0 | Upcoming | 02/03/2027 | 02/04/2027 |  |  |  |  | 02/04/2027 | [5 empty] | 02/05/2027
RPL6 | GSIDF6D1 | L5 – Punchlist | 0 | Not Started
RPL6 | GSIDF6D2 | L2 – Infrastructure | 0 | Upcoming | 09/15/2026 | 09/15/2026 |  |  |  |  | 09/15/2026 | [5 empty] | 09/16/2026
RPL6 | GSIDF6D2 | L3 – ISP | 0 | Upcoming | 09/04/2026 | 09/17/2026 |  | 09/08/2026 |  |  | 09/11/2026 |  |  | 09/14/2026 |  |  | 09/17/2026
RPL6 | GSIDF6D2 | L3 – OSP | 0 | Upcoming | 09/04/2026 | 09/14/2026 |  | 09/07/2026 |  |  | 09/09/2026 |  |  | 09/12/2026 |  |  | 09/14/2026
RPL6 | GSIDF6D2 | L4 – Network | 0 | Upcoming | 09/15/2026 | 09/16/2026 |  |  |  |  | 09/16/2026 | [5 empty] | 09/17/2026
RPL6 | GSIDF6D2 | L5 – Punchlist | 0 | Not Started
RPL6 | GSIDF6D3 | L2 – Infrastructure | 0 | Not Started
RPL6 | GSIDF6D3 | L3 – ISP | 0 | Not Started
RPL6 | GSIDF6D3 | L3 – OSP | 0 | Not Started
RPL6 | GSIDF6D3 | L4 – Network | 0 | Not Started
RPL6 | GSIDF6D3 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHA MP01/02 MFD1 | L2 – Infrastructure | 0 | Upcoming | 10/05/2026 | 10/30/2026 |  | 10/12/2026 |  |  | 10/19/2026 |  |  | 10/24/2026 |  |  | 10/30/2026
RPL6 | RPL6 DHA MP01/02 MFD1 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHA MP01/02 MFD1 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHA MP01/02 MFD1 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHA MP01/02 MFD1 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHA MP03/04 MFD2 | L2 – Infrastructure | 0 | Upcoming | 10/26/2026 | 11/23/2026 |  | 11/02/2026 |  |  | 11/09/2026 |  |  | 11/16/2026 |  |  | 11/23/2026
RPL6 | RPL6 DHA MP03/04 MFD2 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHA MP03/04 MFD2 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHA MP03/04 MFD2 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHA MP03/04 MFD2 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHA MP05/06 MFD3 | L2 – Infrastructure | 0 | Upcoming | 11/12/2026 | 12/11/2026 |  | 11/20/2026 |  |  | 11/27/2026 |  |  | 12/04/2026 |  |  | 12/11/2026
RPL6 | RPL6 DHA MP05/06 MFD3 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHA MP05/06 MFD3 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHA MP05/06 MFD3 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHA MP05/06 MFD3 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHA MP07/08 MFD4 | L2 – Infrastructure | 0 | Upcoming | 12/03/2026 | 12/31/2026 |  | 12/10/2026 |  |  | 12/17/2026 |  |  | 12/24/2026 |  |  | 12/31/2026
RPL6 | RPL6 DHA MP07/08 MFD4 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHA MP07/08 MFD4 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHA MP07/08 MFD4 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHA MP07/08 MFD4 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHA MP09/10 MFD5 | L2 – Infrastructure | 0 | Upcoming | 12/24/2026 | 01/25/2027 |  | 01/01/2027 |  |  | 01/09/2027 |  |  | 01/18/2027 |  |  | 01/25/2027
RPL6 | RPL6 DHA MP09/10 MFD5 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHA MP09/10 MFD5 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHA MP09/10 MFD5 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHA MP09/10 MFD5 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHB MP11/12 MFD1 | L2 – Infrastructure | 0 | Upcoming | 09/21/2026 | 10/16/2026 |  | 09/28/2026 |  |  | 10/05/2026 |  |  | 10/10/2026 |  |  | 10/16/2026
RPL6 | RPL6 DHB MP11/12 MFD1 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHB MP11/12 MFD1 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHB MP11/12 MFD1 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHB MP11/12 MFD1 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHB MP13/14 MFD2 | L2 – Infrastructure | 0 | Upcoming | 10/07/2026 | 11/03/2026 |  | 10/14/2026 |  |  | 10/21/2026 |  |  | 10/28/2026 |  |  | 11/03/2026
RPL6 | RPL6 DHB MP13/14 MFD2 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHB MP13/14 MFD2 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHB MP13/14 MFD2 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHB MP13/14 MFD2 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHB MP15/16 MFD3 | L2 – Infrastructure | 0 | Upcoming | 10/28/2026 | 11/25/2026 |  | 11/04/2026 |  |  | 11/11/2026 |  |  | 11/18/2026 |  |  | 11/25/2026
RPL6 | RPL6 DHB MP15/16 MFD3 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHB MP15/16 MFD3 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHB MP15/16 MFD3 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHB MP15/16 MFD3 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHB MP17/18 MFD4 | L2 – Infrastructure | 0 | Upcoming | 11/17/2026 | 12/16/2026 |  | 11/25/2026 |  |  | 12/02/2026 |  |  | 12/09/2026 |  |  | 12/16/2026
RPL6 | RPL6 DHB MP17/18 MFD4 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHB MP17/18 MFD4 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHB MP17/18 MFD4 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHB MP17/18 MFD4 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHB MP19/20 MFD5 | L2 – Infrastructure | 0 | Upcoming | 12/10/2026 | 01/08/2027 |  | 12/18/2026 |  |  | 12/25/2026 |  |  | 01/01/2027 |  |  | 01/08/2027
RPL6 | RPL6 DHB MP19/20 MFD5 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHB MP19/20 MFD5 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHB MP19/20 MFD5 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHB MP19/20 MFD5 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHC MP21/22 MFD1 | L2 – Infrastructure | 0 | Upcoming | 01/19/2027 | 02/16/2027 |  | 01/26/2027 |  |  | 02/02/2027 |  |  | 02/09/2027 |  |  | 02/16/2027
RPL6 | RPL6 DHC MP21/22 MFD1 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHC MP21/22 MFD1 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHC MP21/22 MFD1 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHC MP21/22 MFD1 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHC MP23/24 MFD2 | L2 – Infrastructure | 0 | Upcoming | 01/28/2027 | 02/25/2027 |  | 02/04/2027 |  |  | 02/11/2027 |  |  | 02/18/2027 |  |  | 02/25/2027
RPL6 | RPL6 DHC MP23/24 MFD2 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHC MP23/24 MFD2 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHC MP23/24 MFD2 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHC MP23/24 MFD2 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHC MP25/26 MFD3 | L2 – Infrastructure | 0 | Upcoming | 02/11/2027 | 03/11/2027 |  | 02/18/2027 |  |  | 02/25/2027 |  |  | 03/04/2027 |  |  | 03/11/2027
RPL6 | RPL6 DHC MP25/26 MFD3 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHC MP25/26 MFD3 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHC MP25/26 MFD3 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHC MP25/26 MFD3 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHC MP27/28 MFD4 | L2 – Infrastructure | 0 | Upcoming | 02/26/2027 | 03/25/2027 |  | 03/05/2027 |  |  | 03/12/2027 |  |  | 03/19/2027 |  |  | 03/25/2027
RPL6 | RPL6 DHC MP27/28 MFD4 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHC MP27/28 MFD4 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHC MP27/28 MFD4 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHC MP27/28 MFD4 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHD MP29/30 MFD1 | L2 – Infrastructure | 0 | Upcoming | 01/04/2027 | 02/01/2027 |  | 01/11/2027 |  |  | 01/18/2027 |  |  | 01/25/2027 |  |  | 02/01/2027
RPL6 | RPL6 DHD MP29/30 MFD1 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHD MP29/30 MFD1 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHD MP29/30 MFD1 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHD MP29/30 MFD1 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHD MP31/32 MFD2 | L2 – Infrastructure | 0 | Upcoming | 01/13/2027 | 02/10/2027 |  | 01/20/2027 |  |  | 01/27/2027 |  |  | 02/03/2027 |  |  | 02/10/2027
RPL6 | RPL6 DHD MP31/32 MFD2 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHD MP31/32 MFD2 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHD MP31/32 MFD2 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHD MP31/32 MFD2 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHD MP33/34 MFD3 | L2 – Infrastructure | 0 | Upcoming | 01/28/2027 | 02/25/2027 |  | 02/04/2027 |  |  | 02/11/2027 |  |  | 02/18/2027 |  |  | 02/25/2027
RPL6 | RPL6 DHD MP33/34 MFD3 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHD MP33/34 MFD3 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHD MP33/34 MFD3 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHD MP33/34 MFD3 | L5 – Punchlist | 0 | Not Started
RPL6 | RPL6 DHD MP35/36 MFD4 | L2 – Infrastructure | 0 | Upcoming | 02/11/2027 | 03/11/2027 |  | 02/18/2027 |  |  | 02/25/2027 |  |  | 03/04/2027 |  |  | 03/11/2027
RPL6 | RPL6 DHD MP35/36 MFD4 | L3 – ISP | 0 | Not Started
RPL6 | RPL6 DHD MP35/36 MFD4 | L3 – OSP | 0 | Not Started
RPL6 | RPL6 DHD MP35/36 MFD4 | L4 – Network | 0 | Not Started
RPL6 | RPL6 DHD MP35/36 MFD4 | L5 – Punchlist | 0 | Not Started
EXTERNAL | AdminIDF1 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | AdminIDF1 | L3 – ISP | 0 | Not Started
EXTERNAL | AdminIDF1 | L3 – OSP | 0 | Not Started
EXTERNAL | AdminIDF1 | L4 – Network | 0 | Not Started
EXTERNAL | AdminIDF1 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GHIDF1 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GHIDF1 | L3 – ISP | 0 | Not Started
EXTERNAL | GHIDF1 | L3 – OSP | 0 | Not Started
EXTERNAL | GHIDF1 | L4 – Network | 0 | Not Started
EXTERNAL | GHIDF1 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GHIDF2 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GHIDF2 | L3 – ISP | 0 | Not Started
EXTERNAL | GHIDF2 | L3 – OSP | 0 | Not Started
EXTERNAL | GHIDF2 | L4 – Network | 0 | Not Started
EXTERNAL | GHIDF2 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GHIDF3 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GHIDF3 | L3 – ISP | 0 | Not Started
EXTERNAL | GHIDF3 | L3 – OSP | 0 | Not Started
EXTERNAL | GHIDF3 | L4 – Network | 0 | Not Started
EXTERNAL | GHIDF3 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDF9X01 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GSIDF9X01 | L3 – ISP | 0 | Upcoming | 01/04/2027 | 01/20/2027 |  | 01/08/2027 |  |  | 01/12/2027 |  |  | 01/16/2027 |  |  | 01/20/2027
EXTERNAL | GSIDF9X01 | L3 – OSP | 0 | Upcoming | 07/07/2027 | 07/14/2027 |  |  |  |  | 07/12/2027 | [5 empty] | 07/14/2027
EXTERNAL | GSIDF9X01 | L4 – Network | 0 | Upcoming | 07/15/2027 | 07/19/2027 |  |  |  |  | 07/17/2027 | [5 empty] | 07/19/2027
EXTERNAL | GSIDF9X01 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDF9X02 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GSIDF9X02 | L3 – ISP | 0 | Upcoming | 01/11/2027 | 01/27/2027 |  | 01/15/2027 |  |  | 01/19/2027 |  |  | 01/23/2027 |  |  | 01/27/2027
EXTERNAL | GSIDF9X02 | L3 – OSP | 0 | Upcoming | 07/07/2027 | 07/14/2027 |  |  |  |  | 07/12/2027 | [5 empty] | 07/14/2027
EXTERNAL | GSIDF9X02 | L4 – Network | 0 | Upcoming | 07/15/2027 | 07/19/2027 |  |  |  |  | 07/17/2027 | [5 empty] | 07/19/2027
EXTERNAL | GSIDF9X02 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDF9X03 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GSIDF9X03 | L3 – ISP | 0 | Upcoming | 01/19/2027 | 02/03/2027 |  | 01/23/2027 |  |  | 01/27/2027 |  |  | 02/01/2027 |  |  | 02/03/2027
EXTERNAL | GSIDF9X03 | L3 – OSP | 0 | Upcoming | 07/07/2027 | 07/14/2027 |  |  |  |  | 07/12/2027 | [5 empty] | 07/14/2027
EXTERNAL | GSIDF9X03 | L4 – Network | 0 | Upcoming | 07/15/2027 | 07/19/2027 |  |  |  |  | 07/17/2027 | [5 empty] | 07/19/2027
EXTERNAL | GSIDF9X03 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDF9X04 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GSIDF9X04 | L3 – ISP | 0 | Upcoming | 03/03/2027 | 03/18/2027 |  | 03/08/2027 |  |  | 03/11/2027 |  |  | 03/15/2027 |  |  | 03/18/2027
EXTERNAL | GSIDF9X04 | L3 – OSP | 0 | Upcoming | 07/07/2027 | 07/22/2027 |  | 07/12/2027 |  |  | 07/15/2027 |  |  | 07/19/2027 |  |  | 07/22/2027
EXTERNAL | GSIDF9X04 | L4 – Network | 0 | Upcoming | 07/23/2027 | 07/27/2027 |  |  |  |  | 07/26/2027 | [5 empty] | 07/27/2027
EXTERNAL | GSIDF9X04 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX01 | L2 – Infrastructure | 0 | Upcoming | 05/04/2026 | 05/08/2026 |  |  |  |  | 05/06/2026 | [5 empty] | 05/08/2026
EXTERNAL | GSIDFNX01 | L3 – ISP | 0 | Upcoming | 05/18/2026 | 05/20/2026 |  |  |  |  | 05/19/2026 | [5 empty] | 05/20/2026
EXTERNAL | GSIDFNX01 | L3 – OSP | 0 | Upcoming | 05/11/2026 | 05/15/2026 |  |  |  |  | 05/13/2026 | [5 empty] | 05/15/2026
EXTERNAL | GSIDFNX01 | L4 – Network | 0 | Upcoming | 05/18/2026 | 05/20/2026 |  |  |  |  | 05/19/2026 | [5 empty] | 05/20/2026
EXTERNAL | GSIDFNX01 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX02 | L2 – Infrastructure | 0 | Upcoming | 05/04/2026 | 05/08/2026 |  |  |  |  | 05/06/2026 | [5 empty] | 05/08/2026
EXTERNAL | GSIDFNX02 | L3 – ISP | 0 | Upcoming | 05/18/2026 | 05/20/2026 |  |  |  |  | 05/19/2026 | [5 empty] | 05/20/2026
EXTERNAL | GSIDFNX02 | L3 – OSP | 0 | Upcoming | 05/11/2026 | 05/15/2026 |  |  |  |  | 05/13/2026 | [5 empty] | 05/15/2026
EXTERNAL | GSIDFNX02 | L4 – Network | 0 | Upcoming | 05/18/2026 | 05/20/2026 |  |  |  |  | 05/19/2026 | [5 empty] | 05/20/2026
EXTERNAL | GSIDFNX02 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX03 | L2 – Infrastructure | 0 | Upcoming | 07/16/2026 | 07/22/2026 |  |  |  |  | 07/20/2026 | [5 empty] | 07/22/2026
EXTERNAL | GSIDFNX03 | L3 – ISP | 0 | Upcoming | 08/06/2026 | 08/10/2026 |  |  |  |  | 08/08/2026 | [5 empty] | 08/10/2026
EXTERNAL | GSIDFNX03 | L3 – OSP | 0 | Upcoming | 07/23/2026 | 08/05/2026 |  | 07/27/2026 |  |  | 07/30/2026 |  |  | 08/03/2026 |  |  | 08/05/2026
EXTERNAL | GSIDFNX03 | L4 – Network | 0 | Upcoming | 08/06/2026 | 08/10/2026 |  |  |  |  | 08/08/2026 | [5 empty] | 08/10/2026
EXTERNAL | GSIDFNX03 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX04 | L2 – Infrastructure | 0 | Upcoming | 07/16/2026 | 07/22/2026 |  |  |  |  | 07/20/2026 | [5 empty] | 07/22/2026
EXTERNAL | GSIDFNX04 | L3 – ISP | 0 | Upcoming | 08/06/2026 | 08/10/2026 |  |  |  |  | 08/08/2026 | [5 empty] | 08/10/2026
EXTERNAL | GSIDFNX04 | L3 – OSP | 0 | Upcoming | 07/23/2026 | 08/05/2026 |  | 07/27/2026 |  |  | 07/30/2026 |  |  | 08/03/2026 |  |  | 08/05/2026
EXTERNAL | GSIDFNX04 | L4 – Network | 0 | Upcoming | 08/06/2026 | 08/10/2026 |  |  |  |  | 08/08/2026 | [5 empty] | 08/10/2026
EXTERNAL | GSIDFNX04 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX05 | L2 – Infrastructure | 0 | Upcoming | 06/02/2026 | 06/08/2026 |  |  |  |  | 06/05/2026 | [5 empty] | 06/08/2026
EXTERNAL | GSIDFNX05 | L3 – ISP | 0 | Upcoming | 06/16/2026 | 06/18/2026 |  |  |  |  | 06/17/2026 | [5 empty] | 06/18/2026
EXTERNAL | GSIDFNX05 | L3 – OSP | 0 | Upcoming | 06/09/2026 | 06/15/2026 |  |  |  |  | 06/12/2026 | [5 empty] | 06/15/2026
EXTERNAL | GSIDFNX05 | L4 – Network | 0 | Upcoming | 06/16/2026 | 06/18/2026 |  |  |  |  | 06/17/2026 | [5 empty] | 06/18/2026
EXTERNAL | GSIDFNX05 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX06 | L2 – Infrastructure | 0 | Upcoming | 05/20/2026 | 05/27/2026 |  |  |  |  | 05/25/2026 | [5 empty] | 05/27/2026
EXTERNAL | GSIDFNX06 | L3 – ISP | 0 | Upcoming | 06/04/2026 | 06/08/2026 |  |  |  |  | 06/06/2026 | [5 empty] | 06/08/2026
EXTERNAL | GSIDFNX06 | L3 – OSP | 0 | Upcoming | 05/28/2026 | 06/03/2026 |  |  |  |  | 06/01/2026 | [5 empty] | 06/03/2026
EXTERNAL | GSIDFNX06 | L4 – Network | 0 | Upcoming | 06/04/2026 | 06/08/2026 |  |  |  |  | 06/06/2026 | [5 empty] | 06/08/2026
EXTERNAL | GSIDFNX06 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX07 | L2 – Infrastructure | 0 | Upcoming | 05/20/2026 | 05/27/2026 |  |  |  |  | 05/25/2026 | [5 empty] | 05/27/2026
EXTERNAL | GSIDFNX07 | L3 – ISP | 0 | Upcoming | 06/04/2026 | 06/08/2026 |  |  |  |  | 06/06/2026 | [5 empty] | 06/08/2026
EXTERNAL | GSIDFNX07 | L3 – OSP | 0 | Upcoming | 05/28/2026 | 06/03/2026 |  |  |  |  | 06/01/2026 | [5 empty] | 06/03/2026
EXTERNAL | GSIDFNX07 | L4 – Network | 0 | Upcoming | 06/04/2026 | 06/08/2026 |  |  |  |  | 06/06/2026 | [5 empty] | 06/08/2026
EXTERNAL | GSIDFNX07 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX08 | L2 – Infrastructure | 0 | Upcoming | 07/23/2026 | 07/29/2026 |  |  |  |  | 07/27/2026 | [5 empty] | 07/29/2026
EXTERNAL | GSIDFNX08 | L3 – ISP | 0 | Upcoming | 08/13/2026 | 08/17/2026 |  |  |  |  | 08/15/2026 | [5 empty] | 08/17/2026
EXTERNAL | GSIDFNX08 | L3 – OSP | 0 | Upcoming | 07/30/2026 | 08/12/2026 |  | 08/03/2026 |  |  | 08/06/2026 |  |  | 08/10/2026 |  |  | 08/12/2026
EXTERNAL | GSIDFNX08 | L4 – Network | 0 | Upcoming | 08/13/2026 | 08/17/2026 |  |  |  |  | 08/15/2026 | [5 empty] | 08/17/2026
EXTERNAL | GSIDFNX08 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX09 | L2 – Infrastructure | 0 | Upcoming | 07/23/2026 | 07/29/2026 |  |  |  |  | 07/27/2026 | [5 empty] | 07/29/2026
EXTERNAL | GSIDFNX09 | L3 – ISP | 0 | Upcoming | 08/13/2026 | 08/17/2026 |  |  |  |  | 08/15/2026 | [5 empty] | 08/17/2026
EXTERNAL | GSIDFNX09 | L3 – OSP | 0 | Upcoming | 07/30/2026 | 08/12/2026 |  | 08/03/2026 |  |  | 08/06/2026 |  |  | 08/10/2026 |  |  | 08/12/2026
EXTERNAL | GSIDFNX09 | L4 – Network | 0 | Upcoming | 08/13/2026 | 08/17/2026 |  |  |  |  | 08/15/2026 | [5 empty] | 08/17/2026
EXTERNAL | GSIDFNX09 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX10 | L2 – Infrastructure | 0 | Upcoming | 06/08/2026 | 06/12/2026 |  |  |  |  | 06/10/2026 | [5 empty] | 06/12/2026
EXTERNAL | GSIDFNX10 | L3 – ISP | 0 | Upcoming | 07/07/2026 | 07/09/2026 | 06/18/2026 |  |  |  | 07/08/2026 | [5 empty] | 07/09/2026
EXTERNAL | GSIDFNX10 | L3 – OSP | 0 | Upcoming | 06/15/2026 | 07/06/2026 |  | 06/22/2026 |  |  | 06/26/2026 |  |  | 07/01/2026 |  |  | 07/06/2026
EXTERNAL | GSIDFNX10 | L4 – Network | 0 | Upcoming | 07/07/2026 | 07/09/2026 |  |  |  |  | 07/08/2026 | [5 empty] | 07/09/2026
EXTERNAL | GSIDFNX10 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX11 | L2 – Infrastructure | 0 | Past Due | 04/13/2026 | 04/17/2026 |  |  |  |  | 04/15/2026 |  | Link |  |  |  | 04/17/2026 |  | Link | Link
EXTERNAL | GSIDFNX11 | L3 – ISP | 0 | Upcoming | 05/11/2026 | 05/13/2026 |  |  |  |  | 05/12/2026 | [5 empty] | 05/13/2026 |  |  | Link
EXTERNAL | GSIDFNX11 | L3 – OSP | 0 | Upcoming | 04/20/2026 | 05/08/2026 |  | 04/25/2026 |  |  | 04/29/2026 |  |  | 05/04/2026 |  |  | 05/08/2026
EXTERNAL | GSIDFNX11 | L4 – Network | 0 | Upcoming | 05/11/2026 | 05/13/2026 |  |  |  |  | 05/12/2026 | [5 empty] | 05/13/2026
EXTERNAL | GSIDFNX11 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX12 | L2 – Infrastructure | 0 | Past Due | 04/13/2026 | 04/17/2026 |  |  |  |  | 04/15/2026 |  | Link |  |  |  | 04/17/2026 |  | Link
EXTERNAL | GSIDFNX12 | L3 – ISP | 0 | Upcoming | 05/11/2026 | 05/22/2026 |  | 05/14/2026 |  |  | 05/18/2026 |  |  | 05/20/2026 |  |  | 05/22/2026
EXTERNAL | GSIDFNX12 | L3 – OSP | 0 | Upcoming | 04/20/2026 | 05/08/2026 |  | 04/25/2026 |  |  | 04/29/2026 |  |  | 05/04/2026 |  |  | 05/08/2026
EXTERNAL | GSIDFNX12 | L4 – Network | 0 | Upcoming | 05/11/2026 | 05/13/2026 |  |  |  |  | 05/12/2026 | [5 empty] | 05/13/2026
EXTERNAL | GSIDFNX12 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX13 | L2 – Infrastructure | 0 | Past Due | 04/13/2026 | 04/17/2026 |  |  |  |  | 04/15/2026 |  | Link |  |  |  | 04/17/2026 |  | Link
EXTERNAL | GSIDFNX13 | L3 – ISP | 0 | Upcoming | 04/28/2026 | 05/11/2026 |  | 05/02/2026 |  |  | 05/05/2026 |  |  | 05/08/2026 |  |  | 05/11/2026
EXTERNAL | GSIDFNX13 | L3 – OSP | 0 | Upcoming | 04/20/2026 | 04/27/2026 |  |  |  |  | 04/24/2026 | [5 empty] | 04/27/2026
EXTERNAL | GSIDFNX13 | L4 – Network | 0 | Upcoming | 04/28/2026 | 04/30/2026 |  |  |  |  | 04/29/2026 | [5 empty] | 04/30/2026
EXTERNAL | GSIDFNX13 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX14 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GSIDFNX14 | L3 – ISP | 0 | Not Started
EXTERNAL | GSIDFNX14 | L3 – OSP | 0 | Not Started
EXTERNAL | GSIDFNX14 | L4 – Network | 0 | Not Started
EXTERNAL | GSIDFNX14 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX15 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GSIDFNX15 | L3 – ISP | 0 | Not Started
EXTERNAL | GSIDFNX15 | L3 – OSP | 0 | Not Started
EXTERNAL | GSIDFNX15 | L4 – Network | 0 | Not Started
EXTERNAL | GSIDFNX15 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX16 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GSIDFNX16 | L3 – ISP | 0 | Not Started
EXTERNAL | GSIDFNX16 | L3 – OSP | 0 | Not Started
EXTERNAL | GSIDFNX16 | L4 – Network | 0 | Not Started
EXTERNAL | GSIDFNX16 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX17 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GSIDFNX17 | L3 – ISP | 0 | Not Started
EXTERNAL | GSIDFNX17 | L3 – OSP | 0 | Not Started
EXTERNAL | GSIDFNX17 | L4 – Network | 0 | Not Started
EXTERNAL | GSIDFNX17 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX18 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GSIDFNX18 | L3 – ISP | 0 | Not Started
EXTERNAL | GSIDFNX18 | L3 – OSP | 0 | Not Started
EXTERNAL | GSIDFNX18 | L4 – Network | 0 | Not Started
EXTERNAL | GSIDFNX18 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX19 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GSIDFNX19 | L3 – ISP | 0 | Not Started
EXTERNAL | GSIDFNX19 | L3 – OSP | 0 | Not Started
EXTERNAL | GSIDFNX19 | L4 – Network | 0 | Not Started
EXTERNAL | GSIDFNX19 | L5 – Punchlist | 0 | Not Started
EXTERNAL | GSIDFNX20 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | GSIDFNX20 | L3 – ISP | 0 | Not Started
EXTERNAL | GSIDFNX20 | L3 – OSP | 0 | Not Started
EXTERNAL | GSIDFNX20 | L4 – Network | 0 | Not Started
EXTERNAL | GSIDFNX20 | L5 – Punchlist | 0 | Not Started
EXTERNAL | SUBIDFNX01 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | SUBIDFNX01 | L3 – ISP | 0 | Not Started
EXTERNAL | SUBIDFNX01 | L3 – OSP | 0 | Not Started
EXTERNAL | SUBIDFNX01 | L4 – Network | 0 | Not Started
EXTERNAL | SUBIDFNX01 | L5 – Punchlist | 0 | Not Started
EXTERNAL | SUBIDFNX02 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | SUBIDFNX02 | L3 – ISP | 0 | Not Started
EXTERNAL | SUBIDFNX02 | L3 – OSP | 0 | Not Started
EXTERNAL | SUBIDFNX02 | L4 – Network | 0 | Not Started
EXTERNAL | SUBIDFNX02 | L5 – Punchlist | 0 | Not Started
EXTERNAL | TWRIDFNX01 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | TWRIDFNX01 | L3 – ISP | 0 | Not Started
EXTERNAL | TWRIDFNX01 | L3 – OSP | 0 | Not Started
EXTERNAL | TWRIDFNX01 | L4 – Network | 0 | Not Started
EXTERNAL | TWRIDFNX01 | L5 – Punchlist | 0 | Not Started
EXTERNAL | TWRIDFNX02 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | TWRIDFNX02 | L3 – ISP | 0 | Not Started
EXTERNAL | TWRIDFNX02 | L3 – OSP | 0 | Not Started
EXTERNAL | TWRIDFNX02 | L4 – Network | 0 | Not Started
EXTERNAL | TWRIDFNX02 | L5 – Punchlist | 0 | Not Started
EXTERNAL | WHIDF1 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | WHIDF1 | L3 – ISP | 0 | Not Started
EXTERNAL | WHIDF1 | L3 – OSP | 0 | Not Started
EXTERNAL | WHIDF1 | L4 – Network | 0 | Not Started
EXTERNAL | WHIDF1 | L5 – Punchlist | 0 | Not Started
EXTERNAL | WHIDF2 | L2 – Infrastructure | 0 | Not Started
EXTERNAL | WHIDF2 | L3 – ISP | 0 | Not Started
EXTERNAL | WHIDF2 | L3 – OSP | 0 | Not Started
EXTERNAL | WHIDF2 | L4 – Network | 0 | Not Started
EXTERNAL | WHIDF2 | L5 – Punchlist | 0 | Not Started