## OFCI Status
OFCI Tracking Status (as of 06/17/2026)
Total: 2840 Delivered: 1044 Partial: 54 Upcoming: 1228 Past Due: 455 Pending: 59 Delivered w/o L1: 466
Description | Part # | MPN | PO # | Bldg | Vendor | Need By | VCD | Delta (days) | Actual | Qty Received | Qty Ordered | Status
Fiber - Pigtail - OFNP - 192f | 23-013635 | CB-PT-192SMPLRS020 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2025-12-14 | 2026-06-25 | 8 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Pigtail - OFNP - 192f | 23-013635 | CB-PT-192SMPLRS020 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2025-12-23 | 2026-06-25 | 8 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Pigtail - OFNP - 192f | 23-013635 | CB-PT-192SMPLRS020 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2025-12-30 | 2026-06-25 | 8 | 2026-05-21 | 8 | 57 | Partial
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 |  |  | 2026-04-01 | 6000 | 6000 | Delivered
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 |  |  | 2026-04-01 | 6000 | 6000 | Delivered
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 |  |  | 2026-04-01 | 6000 | 6000 | Delivered
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 |  |  | 2026-04-01 | 6000 | 6000 | Delivered
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 |  |  | 2026-04-01 | 6000 | 6000 | Delivered
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 |  |  | 2026-04-01 | 6000 | 6000 | Delivered
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 |  |  | 2026-04-01 | 6000 | 6000 | Delivered
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 |  |  | 2026-04-01 | 6000 | 6000 | Delivered
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 |  |  | 2026-04-01 | 6000 | 6000 | Delivered
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 |  |  | 2026-04-01 | 6000 | 6000 | Delivered
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 192f | 23-110357 | AT-3GE8Y3X-192 | 70001631913 | RPL10 | LIGHTERA LLC | 2026-02-27 | 2026-03-31 | -78 |  | 0 | 6000 | Past Due
Fiber - Extender Trunk - OFNP - 96f | 23-103162 | CB-FB-ST-4SM24076 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-02-27 | -110 | 2026-05-06 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNP - 96f | 23-103162 | CB-FB-ST-4SM24076 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-02-27 | -110 | 2026-05-06 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNP - 96f | 23-103165 | CB-FB-ST-4SM24081 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-02-27 | -110 | 2026-05-06 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNP - 96f | 23-103166 | CB-FB-ST-4SM24069 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-02-27 | -110 | 2026-05-06 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNP - 96f | 23-103159 | CB-FB-ST-4SM24084 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 | 2026-05-06 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNP - 96f | 23-103158 | CB-FB-ST-4SM24067 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 | 2026-05-06 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNP - 96f | 23-009401 | CB-FB-ST-4SM24188 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 |  | 0 | 4 | Past Due
Fiber - Extender Trunk - OFNP - 96f | 23-009895 | CB-FB-ST-4SM24193 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNP - 96f | 23-009401 | CB-FB-ST-4SM24188 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 | 2026-05-06 | 1 | 3 | Partial
Fiber - Extender Trunk - OFNP - 96f | 23-010312 | CB-FB-ST-4SM24208 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 | 2026-05-06 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNP - 96f | 23-010312 | CB-FB-ST-4SM24208 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 | 2026-05-06 | 2 | 2 | Delivered
Fiber - Pigtail - OFNP - 96f | 23-013796 | CB-PT-96SMPLRS285 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 1 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013785 | CB-PT-96SMPLRS230 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 | 2026-05-27 | 1 | 1 | Delivered
Fiber - Pigtail - OFNP - 96f | 23-013746 | CB-PT-96SMPLRS035 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-10 | -7 |  | 0 | 1 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013758 | CB-PT-96SMPLRS095 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-10 | -7 | 2026-05-27 | 1 | 1 | Delivered
Fiber - Pigtail - OFNP - 96f | 23-013748 | CB-PT-96SMPLRS045 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-10 | -7 | 2026-05-22 | 2 | 2 | Delivered
Fiber - Pigtail - OFNP - 96f | 23-013748 | CB-PT-96SMPLRS045 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-10 | -7 | 2026-05-22 | 144 | 144 | Delivered
Fiber - Pigtail - OFNP - 96f | 23-013748 | CB-PT-96SMPLRS045 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-10 | -7 | 2026-05-27 | 1 | 1 | Delivered
Fiber - Pigtail - OFNP - 96f | 23-013784 | CB-PT-96SMPLRS225 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 2 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013757 | CB-PT-96SMPLRS090 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-10 | -7 | 2026-05-27 | 1 | 1 | Delivered
Fiber - Pigtail - OFNP - 96f | 23-013755 | CB-PT-96SMPLRS080 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-10 | -7 | 2026-05-27 | 1 | 2 | Partial
Fiber - Pigtail - OFNP - 96f | 23-013776 | CB-PT-96SMPLRS185 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 2 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013774 | CB-PT-96SMPLRS175 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-10 | -7 |  | 0 | 1 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013769 | CB-PT-96SMPLRS150 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 1 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013745 | CB-PT-96SMPLRS030 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-10 | -7 |  | 0 | 1 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013797 | CB-PT-96SMPLRS290 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-10 | -7 | 2026-06-01 | 1 | 1 | Delivered
Fiber - Pigtail - OFNP - 192f | 23-013636 | CB-PT-192SMPLRS025 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-24 | 7 | 2026-05-26 | 6 | 6 | Delivered
Fiber - Pigtail - OFNP - 192f | 23-013639 | CB-PT-192SMPLRS040 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-25 | 8 |  | 0 | 4 | Past Due
Fiber - Pigtail - OFNP - 192f | 23-013638 | CB-PT-192SMPLRS035 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-05-27 | -21 |  | 0 | 2 | Past Due
Fiber - Pigtail - OFNP - 192f | 23-013635 | CB-PT-192SMPLRS020 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-25 | 8 |  | 0 | 16 | Past Due
Fiber - Pigtail - OFNP - 192f | 23-013635 | CB-PT-192SMPLRS020 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-25 | 8 | 2026-06-04 | 12 | 12 | Delivered
Fiber - Pigtail - OFNP - 192f | 23-013648 | CB-PT-192SMPLRS085 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-02 | -15 | 2026-06-01 | 2 | 2 | Delivered
Fiber - Pigtail - OFNP - 192f | 23-013652 | CB-PT-192SMPLRS105 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-25 | 8 | 2026-06-09 | 2 | 2 | Delivered
Fiber - Pigtail - OFNP - 48f | 23-014401 | CB-PT-48SMPL200 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 1 | Past Due
Fiber - Pigtail - OFNP - 48f | 23-100602 | CB-PT-48SMPL015 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-17 | 0 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Pigtail - OFNP - 48f | 23-101392 | CB-PT-48SMPL035 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 1 | Past Due
Fiber - Pigtail - OFNP - 48f | 23-101327 | CB-PT-48SMPL045 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 1 | Past Due
Fiber - Pigtail - OFNP - 48f | 23-014369 | CB-PT-48SMPL040 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 2 | Past Due
Fiber - Pigtail - OFNP - 48f | 23-101368 | CB-PT-48SMPL025 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 | 2026-05-27 | 1 | 2 | Partial
Fiber - Pigtail - OFNP - 48f | 23-101368 | CB-PT-48SMPL025 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 2 | Past Due
Fiber - Pigtail - OFNP - 48f | 23-101399 | CB-PT-48SMPL105 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 2 | Past Due
Fiber - Pigtail - OFNP - 48f | 23-014413 | CB-PT-48SMPL260 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-17 | 0 |  | 0 | 1 | Past Due
Fiber - Pigtail - OFNP - 48f | 23-014428 | CB-PT-48SMPL335 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 1 | Past Due
Fiber - Pigtail - OFNP - 48f | 23-014416 | CB-PT-48SMPL275 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-06-11 | -6 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNP - 96f | 23-009175 | CB-FB-ST-4SM24044 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-02-27 | -110 |  | 0 | 2 | Past Due
Fiber - Trunk - OFNP - 96f | 23-009175 | CB-FB-ST-4SM24044 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-02-27 | -110 |  | 0 | 2 | Past Due
Fiber - Trunk - OFNP - 96f | 23-006370 | CB-FB-ST-4SM24088 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-02-27 | -110 | 2026-05-06 | 2 | 2 | Delivered
Fiber - Trunk - OFNP - 96f | 23-006365 | CB-FB-ST-4SM24063 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-02-27 | -110 | 2026-05-06 | 3 | 3 | Delivered
Fiber - Trunk - OFNP - 96f | 23-006367 | CB-FB-ST-4SM24073 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-02-27 | -110 | 2026-05-06 | 2 | 2 | Delivered
Fiber - Trunk - OFNP - 96f | 23-006363 | CB-FB-ST-4SM24053 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-02-27 | -110 | 2026-05-06 | 3 | 3 | Delivered
Fiber - Trunk - OFNP - 96f | 23-006362 | CB-FB-ST-4SM24048 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 |  | 0 | 2 | Past Due
Fiber - Trunk - OFNP - 96f | 23-006364 | CB-FB-ST-4SM24058 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 | 2026-05-06 | 4 | 4 | Delivered
Fiber - Trunk - OFNP - 96f | 23-010313 | CB-FB-ST-4SM24223 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 | 2026-05-06 | 3 | 3 | Delivered
Fiber - Trunk - OFNP - 96f | 23-009404 | CB-FB-ST-4SM24213 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 | 2026-05-06 | 4 | 4 | Delivered
Fiber - Trunk - OFNP - 96f | 23-009402 | CB-FB-ST-4SM24198 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 |  | 0 | 2 | Past Due
Fiber - Trunk - OFNP - 96f | 23-010362 | CB-FB-ST-4SM24228 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 | 2026-05-06 | 1 | 1 | Delivered
Fiber - Trunk - OFNP - 96f | 23-009403 | CB-FB-ST-4SM24203 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 | 2026-05-06 | 2 | 2 | Delivered
Fiber - Trunk - OFNP - 96f | 23-010146 | CB-FB-ST-4SM24183 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 | 2026-03-07 | -102 |  | 0 | 3 | Past Due
| 23-014367 | CB-PT-48SMPL030 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-03-07 |  |  |  | 0 | 1 | Past Due
Hardware - MBOX | 23-009793 | MC-1RUC-4X-LC-24MP-SM-01 | 70001491816 | RPL10 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-03-21 | 2026-08-07 | 51 |  | 0 | 8 | Past Due
Hardware - MBOX | 23-009793 | MC-1RUC-4X-LC-24MP-SM-01 | 70001491816 | RPL10 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-03-21 | 2026-08-07 | 51 |  | 0 | 112 | Past Due
Hardware - MBOX | 23-105487 | MC-1RUC-4X-LC-24MMC-SM-01 | 70001536816 | RPL10 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-03-21 | 2026-08-21 | 65 |  | 0 | 8 | Past Due
Hardware - MBOX | 23-105487 | MC-1RUC-4X-LC-24MMC-SM-01 | 70001536816 | RPL10 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-03-21 | 2026-08-21 | 65 |  | 0 | 112 | Past Due
PDU Basic | 03-000904 | STV-FB118WA | 70001457474 | RPL10 | ANIXTER INC | 2026-03-21 | 2026-03-20 | -89 |  | 0 | 300 | Past Due
Fiber - Blunt - OSP - 864f | 23-103287 | R40864S906FAP10000 | 70001655913 | RPL6 | STL OPTICAL CONNECTIVITY NA LLC | 2026-03-31 | 2026-04-08 | -70 |  | 0 | 6000 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013744 | CB-PT-96SMPLRS025 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-07-02 | 15 |  | 0 | 32 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013745 | CB-PT-96SMPLRS030 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-06-30 | 13 |  | 0 | 8 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013746 | CB-PT-96SMPLRS035 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-06-30 | 13 |  | 0 | 8 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013747 | CB-PT-96SMPLRS040 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-06-29 | 12 |  | 0 | 4 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013748 | CB-PT-96SMPLRS045 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-06-29 | 12 |  | 0 | 40 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013749 | CB-PT-96SMPLRS050 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-06-30 | 13 |  | 0 | 12 | Past Due
Fiber - Pigtail - OFNP - 96f | 23-013750 | CB-PT-96SMPLRS055 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-06-30 | 13 |  | 0 | 8 | Past Due
Fiber - Pigtail - OFNP - 192f | 23-013635 | CB-PT-192SMPLRS020 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-07-09 | 22 |  | 0 | 34 | Past Due
Fiber - Pigtail - OFNP - 192f | 23-013636 | CB-PT-192SMPLRS025 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-12-09 | 175 | 2026-05-26 | 18 | 18 | Delivered
Fiber - Pigtail - OFNP - 192f | 23-013637 | CB-PT-192SMPLRS030 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-12-09 | 175 |  | 0 | 8 | Past Due
Fiber - Pigtail - OFNP - 192f | 23-013639 | CB-PT-192SMPLRS040 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-12-09 | 175 |  | 0 | 8 | Past Due
Fiber - Pigtail - OFNP - 192f | 23-013640 | CB-PT-192SMPLRS045 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-12-09 | 175 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Pigtail - OFNP - 192f | 23-013641 | CB-PT-192SMPLRS050 | 70001638516 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-01 | 2026-12-09 | 175 |  | 0 | 2 | Past Due
Fiber - Blunt - OSP - 192f | 23-014491 | GCYFY-192B6a1 | 70001678969 | RPL6 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-04-01 | 2026-07-10 | 23 |  | 0 | 5300 | Past Due
Fiber - Blunt - OSP - 192f | 23-014491 | GCYFY-192B6a1 | 70001678969 | RPL6 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-04-01 | 2026-07-10 | 23 |  | 0 | 5900 | Past Due
Fiber - Blunt - OSP - 192f | 23-014491 | GCYFY-192B6a1 | 70001678969 | RPL6 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-04-01 | 2026-07-10 | 23 |  | 0 | 4600 | Past Due
Fiber - Blunt - OSP - 864f | 23-103287 | GCYDXY(AB-ASR)-12F-864B6A2 200Î¼m | 70001678969 | RPL6 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-04-01 | 2026-07-10 | 23 |  | 0 | 6000 | Past Due
Fiber - Blunt - OSP - 48f | 23-107025 | GCYFC-048B6al 200um | 70001678969 | RPL6 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-04-01 | 2026-07-10 | 23 |  | 0 | 5200 | Past Due
Fiber - Fanout - OFNP - 8f | 23-013173 | CB-FB-A08002 | 70001457473 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-04-07 | 2026-04-07 | -71 | 2026-05-06 | 96 | 96 | Delivered
Copper - Patch Cord - CM | 23-017853 | FB-PC6-CM-BL-05M | 70001457472 | RPL10 | COMMSCOPE TECHNOLOGIES LLC | 2026-04-07 | 2026-04-27 | -51 |  | 0 | 3 | Past Due
Copper - Patch Cord - CM | 23-017854 | FB-PC6-CM-BL-06M | 70001457472 | RPL10 | COMMSCOPE TECHNOLOGIES LLC | 2026-04-07 | 2026-04-27 | -51 |  | 0 | 4 | Past Due
Copper - Patch Cord - CM | 23-017857 | FB-PC6-CM-BL-09M | 70001457472 | RPL10 | COMMSCOPE TECHNOLOGIES LLC | 2026-04-07 | 2026-04-27 | -51 |  | 0 | 1 | Past Due
Copper - Patch Cord - CM | 23-017861 | FB-PC6-CM-BL-13M | 70001457472 | RPL10 | COMMSCOPE TECHNOLOGIES LLC | 2026-04-07 | 2026-04-27 | -51 | 2026-05-15 | 4 | 4 | Delivered
Hardware - MBOX | 23-107115 | MC-10IN1RU-2X-LC-24MMC-SM-01 | 70001665079 | RPL10 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-02 | 2026-10-23 | 128 |  | 0 | 5376 | Past Due
Hardware - FAP | 23-107113 | MC-10IN1RU-FAPB-2P-MMC-01 | 70001665079 | RPL10 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-02 | 2026-08-06 | 50 |  | 0 | 10608 | Past Due
Hardware - FAP | 23-108524 | MC-10IN1RU-2X-5SP-PON-01 | 70001665079 | RPL10 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-02 | 2026-08-28 | 72 |  | 0 | 192 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104911 | CB-FE-HT-096MCM-041 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104914 | CB-FE-HT-096MCM-097 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 3 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104947 | CB-FE-HT-096MCM-103 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110410 | CB-FE-HT-096MCM-418 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110411 | CB-FE-HT-096MCM-313 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 3 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110417 | CB-FE-HT-096MCM-300 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110418 | CB-FE-HT-096MCM-339 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110420 | CB-FE-HT-096MCM-396 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110426 | CB-FE-HT-096MCM-425 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110427 | CB-FE-HT-096MCM-414 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 3 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110429 | CB-FE-HT-096MCM-358 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110431 | CB-FE-HT-096MCM-352 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 3 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110434 | CB-FE-HT-096MCM-370 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110435 | CB-FE-HT-096MCM-345 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110436 | CB-FE-HT-096MCM-393 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-20 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110437 | CB-FE-HT-096MCM-376 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110438 | CB-FE-HT-096MCM-319 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110440 | CB-FE-HT-096MCM-326 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110443 | CB-FE-HT-096MCM-320 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110444 | CB-FE-HT-096MCM-406 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110447 | CB-FE-HT-096MCM-421 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110448 | CB-FE-HT-096MCM-419 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110449 | CB-FE-HT-096MCM-432 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110452 | CB-FE-HT-096MCM-412 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110453 | CB-FE-HT-096MCM-337 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110456 | CB-FE-HT-096MCM-420 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110457 | CB-FE-HT-096MCM-388 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110458 | CB-FE-HT-096MCM-381 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-26 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110476 | CB-FE-HT-096MCM-365 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110487 | CB-FE-HT-096MCM-362 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102971 | CB-FE-HT-192MCM-021 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 192 | 192 | Delivered
Fiber - Trunk - OFNR - 192f | 23-105731 | CB-FE-HT-192MCM-038 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-21 | -27 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-105732 | CB-FE-HT-192MCM-023 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-05 | 48 | 48 | Delivered
Fiber - Trunk - OFNR - 192f | 23-105736 | CB-FE-HT-192MCM-025 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 24 | 24 | Delivered
Fiber - Trunk - OFNR - 192f | 23-105738 | CB-FE-HT-192MCM-029 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106815 | CB-FE-HT-192MCM-203 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106819 | CB-FE-HT-192MCM-197 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106820 | CB-FE-HT-192MCM-191 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106822 | CB-FE-HT-192MCM-167 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106825 | CB-FE-HT-192MCM-209 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106828 | CB-FE-HT-192MCM-183 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106830 | CB-FE-HT-192MCM-187 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-15 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106835 | CB-FE-HT-192MCM-219 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-15 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106842 | CB-FE-HT-192MCM-145 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106844 | CB-FE-HT-192MCM-185 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 |  | 0 | 4 | Past Due
Fiber - Trunk - OFNR - 192f | 23-106846 | CB-FE-HT-192MCM-151 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106855 | CB-FE-HT-192MCM-225 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-15 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106860 | CB-FE-HT-192MCM-179 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106866 | CB-FE-HT-192MCM-157 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-15 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106867 | CB-FE-HT-192MCM-173 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-21 | -27 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106871 | CB-FE-HT-192MCM-213 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-21 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-108723 | CB-FE-HT-192MCM-024 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 24 | 24 | Delivered
Fiber - Trunk - OFNR - 192f | 23-108726 | CB-FE-HT-192MCM-042 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-108728 | CB-FE-HT-192MCM-088 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-18 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-108729 | CB-FE-HT-192MCM-018 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 48 | 48 | Delivered
Fiber - Trunk - OFNR - 192f | 23-108730 | CB-FE-HT-192MCM-048 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110413 | CB-FE-HT-192MCM-200 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110414 | CB-FE-HT-192MCM-170 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110415 | CB-FE-HT-192MCM-136 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110416 | CB-FE-HT-192MCM-206 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-19 | 6 | 6 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110419 | CB-FE-HT-192MCM-148 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-18 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110421 | CB-FE-HT-192MCM-061 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110423 | CB-FE-HT-192MCM-079 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110425 | CB-FE-HT-192MCM-051 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-22 | 6 | 6 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110432 | CB-FE-HT-192MCM-098 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110441 | CB-FE-HT-192MCM-142 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110445 | CB-FE-HT-192MCM-100 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110446 | CB-FE-HT-192MCM-071 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110450 | CB-FE-HT-192MCM-085 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110451 | CB-FE-HT-192MCM-194 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-28 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110454 | CB-FE-HT-192MCM-110 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110455 | CB-FE-HT-192MCM-120 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104232 | CB-FE-HT-288MCM-070 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104264 | CB-FE-HT-288MCM-082 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-21 | -27 | 2026-05-18 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104278 | CB-FE-HT-288MCM-074 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104298 | CB-FE-HT-288MCM-099 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104302 | CB-FE-HT-288MCM-087 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104311 | CB-FE-HT-288MCM-089 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105459 | CB-FE-HT-288MCM-153 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-26 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105460 | CB-FE-HT-288MCM-113 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-21 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105461 | CB-FE-HT-288MCM-133 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 12 | 12 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105463 | CB-FE-HT-288MCM-147 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105464 | CB-FE-HT-288MCM-191 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-29 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105467 | CB-FE-HT-288MCM-190 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105468 | CB-FE-HT-288MCM-120 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-20 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105470 | CB-FE-HT-288MCM-142 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-21 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105472 | CB-FE-HT-288MCM-166 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105473 | CB-FE-HT-288MCM-187 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 |  | 0 | 4 | Past Due
Fiber - Trunk - OFNR - 288f | 23-105474 | CB-FE-HT-288MCM-154 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-22 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105475 | CB-FE-HT-288MCM-228 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-27 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105476 | CB-FE-HT-288MCM-114 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105478 | CB-FE-HT-288MCM-110 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105480 | CB-FE-HT-288MCM-157 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-27 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105481 | CB-FE-HT-288MCM-215 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-22 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105482 | CB-FE-HT-288MCM-199 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105485 | CB-FE-HT-288MCM-135 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105495 | CB-FE-HT-288MCM-298 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-21 | -27 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105497 | CB-FE-HT-288MCM-288 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-27 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105499 | CB-FE-HT-288MCM-273 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105500 | CB-FE-HT-288MCM-263 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-21 | -27 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105501 | CB-FE-HT-288MCM-275 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-21 | -27 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105502 | CB-FE-HT-288MCM-300 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105507 | CB-FE-HT-288MCM-261 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-21 | -27 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105508 | CB-FE-HT-288MCM-286 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106767 | CB-FE-HT-288MCM-115 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106770 | CB-FE-HT-288MCM-269 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106771 | CB-FE-HT-288MCM-107 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106777 | CB-FE-HT-288MCM-104 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106778 | CB-FE-HT-288MCM-257 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106780 | CB-FE-HT-288MCM-143 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-29 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106781 | CB-FE-HT-288MCM-137 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 16 | 8 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106782 | CB-FE-HT-288MCM-129 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106785 | CB-FE-HT-288MCM-195 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-22 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106786 | CB-FE-HT-288MCM-127 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106788 | CB-FE-HT-288MCM-247 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106791 | CB-FE-HT-288MCM-112 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106793 | CB-FE-HT-288MCM-265 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106796 | CB-FE-HT-288MCM-207 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106801 | CB-FE-HT-288MCM-193 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-27 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106802 | CB-FE-HT-288MCM-152 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-21 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106804 | CB-FE-HT-288MCM-121 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-106805 | CB-FE-HT-288MCM-245 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100910 | CB-FE-HT-384MCM-064 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-06-04 | -13 | 2026-05-14 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100923 | CB-FE-HT-384MCM-012 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-28 | 72 | 72 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100947 | CB-FE-HT-384MCM-010 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 24 | 24 | Delivered
Fiber - Trunk - OFNR - 384f | 23-102998 | CB-FE-HT-384MCM-021 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-14 | 168 | 168 | Delivered
Fiber - Trunk - OFNR - 384f | 23-103005 | CB-FE-HT-384MCM-013 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-06-04 | -13 | 2026-05-28 | 96 | 96 | Delivered
Fiber - Trunk - OFNR - 384f | 23-105926 | CB-FE-HT-384MCM-195 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-27 | -21 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-108943 | CB-FE-HT-384MCM-009 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-28 | 80 | 72 | Delivered
Fiber - Trunk - OFNR - 384f | 23-108944 | CB-FE-HT-384MCM-011 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-21 | -27 | 2026-05-28 | 24 | 24 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110412 | CB-FE-HT-384MCM-202 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110424 | CB-FE-HT-384MCM-039 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-20 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110430 | CB-FE-HT-384MCM-200 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-22 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110439 | CB-FE-HT-384MCM-194 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-28 | -20 | 2026-05-22 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110474 | CB-FE-HT-384MCM-037 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 12 | 12 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110568 | CB-FE-HT-288MCM-105 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110604 | CB-FE-HT-288MCM-220 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-28 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110608 | CB-FE-HT-288MCM-156 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110609 | CB-FE-HT-288MCM-125 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-28 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110610 | CB-FE-HT-288MCM-165 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-28 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110619 | CB-FE-HT-288MCM-155 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110623 | CB-FE-HT-288MCM-128 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-28 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110631 | CB-FE-HT-288MCM-186 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110255 | CB-FE-HT-288MCM-131 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110637 | CB-FE-HT-288MCM-148 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110650 | CB-FE-HT-288MCM-244 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-28 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110651 | CB-FE-HT-288MCM-216 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110653 | CB-FE-HT-288MCM-158 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-28 | 2 | 8 | Partial
Fiber - Trunk - OFNR - 384f | 23-110655 | CB-FE-HT-288MCM-181 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110660 | CB-FE-HT-288MCM-171 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110661 | CB-FE-HT-288MCM-185 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 8 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-103986 | CB-FE-ET-096MCFMCM-037 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 12 | 12 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-103990 | CB-FE-ET-096MCFMCM-011 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-14 | 24 | 24 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-103994 | CB-FE-ET-096MCFMCM-039 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-103995 | CB-FE-ET-096MCFMCM-013 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-20 | 36 | 36 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-104250 | CB-FE-HT-096MCM-040 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106317 | CB-FE-ET-096MCFMCM-041 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106873 | CB-FE-HT-096MCM-171 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106874 | CB-FE-HT-096MCM-163 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106875 | CB-FE-HT-096MCM-159 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106876 | CB-FE-HT-096MCM-157 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106881 | CB-FE-HT-096MCM-183 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106883 | CB-FE-HT-096MCM-172 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106887 | CB-FE-HT-096MCM-141 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106889 | CB-FE-HT-096MCM-132 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106893 | CB-FE-HT-096MCM-170 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106894 | CB-FE-HT-096MCM-147 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106897 | CB-FE-HT-096MCM-138 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106902 | CB-FE-HT-096MCM-178 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106904 | CB-FE-HT-096MCM-165 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106909 | CB-FE-HT-096MCM-135 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106912 | CB-FE-HT-096MCM-133 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106919 | CB-FE-HT-096MCM-177 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 4 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106920 | CB-FE-HT-096MCM-152 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106921 | CB-FE-HT-096MCM-189 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106923 | CB-FE-HT-096MCM-182 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106934 | CB-FE-HT-096MCM-195 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106937 | CB-FE-HT-096MCM-158 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106941 | CB-FE-HT-096MCM-166 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106950 | CB-FE-HT-096MCM-194 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106951 | CB-FE-HT-096MCM-176 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106955 | CB-FE-HT-096MCM-140 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106957 | CB-FE-HT-096MCM-151 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106959 | CB-FE-HT-096MCM-164 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106965 | CB-FE-HT-096MCM-134 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106974 | CB-FE-HT-096MCM-153 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106978 | CB-FE-HT-096MCM-146 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106981 | CB-FE-HT-096MCM-145 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 4 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106983 | CB-FE-HT-096MCM-139 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108625 | CB-FE-HT-096MCM-333 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108632 | CB-FE-HT-096MCM-321 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 3 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108633 | CB-FE-HT-096MCM-389 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108636 | CB-FE-HT-096MCM-338 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108642 | CB-FE-HT-096MCM-327 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108643 | CB-FE-HT-096MCM-301 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108645 | CB-FE-HT-096MCM-278 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108646 | CB-FE-HT-096MCM-325 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108647 | CB-FE-HT-096MCM-290 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108648 | CB-FE-HT-096MCM-296 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-19 | 3 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108649 | CB-FE-HT-096MCM-288 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108650 | CB-FE-HT-096MCM-308 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108651 | CB-FE-HT-096MCM-277 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108653 | CB-FE-HT-096MCM-283 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108654 | CB-FE-HT-096MCM-377 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 4 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108655 | CB-FE-HT-096MCM-306 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108659 | CB-FE-HT-096MCM-302 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108663 | CB-FE-HT-096MCM-309 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108665 | CB-FE-HT-096MCM-363 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108666 | CB-FE-HT-096MCM-364 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108674 | CB-FE-HT-096MCM-295 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108676 | CB-FE-HT-096MCM-289 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108677 | CB-FE-HT-096MCM-284 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108678 | CB-FE-HT-096MCM-332 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108682 | CB-FE-HT-096MCM-294 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108684 | CB-FE-HT-096MCM-344 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-22 | 3 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108686 | CB-FE-HT-096MCM-314 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108692 | CB-FE-HT-096MCM-371 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108693 | CB-FE-HT-096MCM-350 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108695 | CB-FE-HT-096MCM-383 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 4 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108697 | CB-FE-HT-096MCM-307 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-103530 | CB-FE-ET-096MCFMCM-012 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-22 | 24 | 24 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-103531 | CB-FE-ET-096MCFMCM-014 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-06-03 | -14 | 2026-05-21 | 12 | 12 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-103978 | CB-FE-ET-096MCFMCM-036 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 21 | 21 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-103979 | CB-FE-ET-096MCFMCM-035 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 38 | 38 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-103980 | CB-FE-ET-096MCFMCM-034 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-21 | 22 | 22 | Delivered
Fiber - Extender Trunk - OFNR - 192f | 23-104512 | CB-FE-ET-192MCFMCM-022 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-29 | -49 | 2026-05-05 | 6 | 6 | Delivered
Fiber - Extender Trunk - OFNR - 192f | 23-104533 | CB-FE-ET-192MCFMCM-026 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-29 | -49 | 2026-05-05 | 18 | 18 | Delivered
Fiber - Extender Trunk - OFNR - 192f | 23-104540 | CB-FE-ET-192MCFMCM-028 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-29 | -49 | 2026-05-05 | 12 | 12 | Delivered
Fiber - Extender Trunk - OFNR - 192f | 23-106633 | CB-FE-ET-192MCFMCM-023 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-29 | -49 | 2026-05-05 | 12 | 12 | Delivered
Fiber - Extender Trunk - OFNR - 192f | 23-106634 | CB-FE-ET-192MCFMCM-025 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-29 | -49 | 2026-05-05 | 24 | 24 | Delivered
Fiber - Extender Trunk - OFNR - 192f | 23-106638 | CB-FE-ET-192MCFMCM-027 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-29 | -49 | 2026-05-05 | 12 | 12 | Delivered
Fiber - Extender Trunk - OFNR - 192f | 23-100895 | CB-FE-ET-192MCFMCM-010 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-29 | -49 | 2026-05-05 | 8 | 8 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110564 | CB-FE-ET-384MCFMCM-322 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110571 | CB-FE-ET-384MCFMCM-207 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 5 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110576 | CB-FE-ET-384MCFMCM-335 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110585 | CB-FE-ET-384MCFMCM-245 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110586 | CB-FE-ET-384MCFMCM-293 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110588 | CB-FE-ET-384MCFMCM-238 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110589 | CB-FE-ET-384MCFMCM-243 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110592 | CB-FE-ET-384MCFMCM-117 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 88 | 6 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110600 | CB-FE-ET-384MCFMCM-195 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110606 | CB-FE-ET-384MCFMCM-081 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110611 | CB-FE-ET-384MCFMCM-150 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110612 | CB-FE-ET-384MCFMCM-181 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110614 | CB-FE-ET-384MCFMCM-165 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 6 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110616 | CB-FE-ET-384MCFMCM-170 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110617 | CB-FE-ET-384MCFMCM-289 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110625 | CB-FE-ET-384MCFMCM-209 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110626 | CB-FE-ET-384MCFMCM-157 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110628 | CB-FE-ET-384MCFMCM-250 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-21 | 6 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110639 | CB-FE-ET-384MCFMCM-215 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110640 | CB-FE-ET-384MCFMCM-235 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110644 | CB-FE-ET-384MCFMCM-278 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 4 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110649 | CB-FE-ET-384MCFMCM-174 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110652 | CB-FE-ET-384MCFMCM-177 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110656 | CB-FE-ET-384MCFMCM-318 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110659 | CB-FE-ET-384MCFMCM-326 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110662 | CB-FE-ET-384MCFMCM-229 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110663 | CB-FE-ET-384MCFMCM-219 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-19 | -29 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-105746 | CB-FE-ET-384MCFMCM-011 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 32 | 32 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110509 | CB-FE-ET-384MCFMCM-091 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 6 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110511 | CB-FE-ET-384MCFMCM-125 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 384f | 23-110522 | CB-FE-ET-384MCFMCM-188 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-08 | 31 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110523 | CB-FE-ET-384MCFMCM-204 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-27 | 6 | 6 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110526 | CB-FE-ET-384MCFMCM-314 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110530 | CB-FE-ET-384MCFMCM-206 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110531 | CB-FE-ET-384MCFMCM-239 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110533 | CB-FE-ET-384MCFMCM-203 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110535 | CB-FE-ET-384MCFMCM-144 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 |  | 0 | 4 | Past Due
Fiber - Extender Trunk - OFNR - 384f | 23-110536 | CB-FE-ET-384MCFMCM-268 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110537 | CB-FE-ET-384MCFMCM-162 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110538 | CB-FE-ET-384MCFMCM-339 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110539 | CB-FE-ET-384MCFMCM-315 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110540 | CB-FE-ET-384MCFMCM-231 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110542 | CB-FE-ET-384MCFMCM-115 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110543 | CB-FE-ET-384MCFMCM-260 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110544 | CB-FE-ET-384MCFMCM-237 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110546 | CB-FE-ET-384MCFMCM-109 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110547 | CB-FE-ET-384MCFMCM-303 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110550 | CB-FE-ET-384MCFMCM-264 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110551 | CB-FE-ET-384MCFMCM-213 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110552 | CB-FE-ET-384MCFMCM-184 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110553 | CB-FE-ET-384MCFMCM-340 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110554 | CB-FE-ET-384MCFMCM-232 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110555 | CB-FE-ET-384MCFMCM-240 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110556 | CB-FE-ET-384MCFMCM-187 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-14 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110557 | CB-FE-ET-384MCFMCM-227 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110558 | CB-FE-ET-384MCFMCM-253 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110562 | CB-FE-ET-384MCFMCM-351 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-14 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110563 | CB-FE-ET-384MCFMCM-087 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100657 | CB-FE-ET-384MCFMCM-134 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100660 | CB-FE-ET-384MCFMCM-082 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100663 | CB-FE-ET-384MCFMCM-044 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100680 | CB-FE-ET-384MCFMCM-084 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100681 | CB-FE-ET-384MCFMCM-074 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100682 | CB-FE-ET-384MCFMCM-126 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100701 | CB-FE-ET-384MCFMCM-072 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100702 | CB-FE-ET-384MCFMCM-106 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100713 | CB-FE-ET-384MCFMCM-070 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100715 | CB-FE-ET-384MCFMCM-062 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100717 | CB-FE-ET-384MCFMCM-092 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-22 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100719 | CB-FE-ET-384MCFMCM-122 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100723 | CB-FE-ET-384MCFMCM-112 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100731 | CB-FE-ET-384MCFMCM-130 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100746 | CB-FE-ET-384MCFMCM-140 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100753 | CB-FE-ET-384MCFMCM-012 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-20 | 38 | 38 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100754 | CB-FE-ET-384MCFMCM-138 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100768 | CB-FE-ET-384MCFMCM-132 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100771 | CB-FE-ET-384MCFMCM-124 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100775 | CB-FE-ET-384MCFMCM-014 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-21 | 16 | 16 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100776 | CB-FE-ET-384MCFMCM-142 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 6 | 6 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100777 | CB-FE-ET-384MCFMCM-078 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100778 | CB-FE-ET-384MCFMCM-080 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100783 | CB-FE-ET-384MCFMCM-218 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100784 | CB-FE-ET-384MCFMCM-172 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100786 | CB-FE-ET-384MCFMCM-152 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100787 | CB-FE-ET-384MCFMCM-094 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100788 | CB-FE-ET-384MCFMCM-196 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100789 | CB-FE-ET-384MCFMCM-158 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 384f | 23-100790 | CB-FE-ET-384MCFMCM-202 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-18 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100792 | CB-FE-ET-384MCFMCM-192 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-19 | 6 | 6 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100794 | CB-FE-ET-384MCFMCM-128 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-26 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100795 | CB-FE-ET-384MCFMCM-248 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100799 | CB-FE-ET-384MCFMCM-104 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-26 | -22 | 2026-05-27 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-103080 | CB-FE-ET-384MCFMCM-013 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-15 | 42 | 42 | Delivered
Fiber - Multi Drop - OFNR - 288f | 23-109848 | MTA-MD288S12A01 | 70001665075 | RPL10 | AFL TELECOMMUNICATIONS LLC | 2026-05-02 | 2026-05-01 | -47 |  | 0 | 256 | Past Due
Fiber - Multi Drop - OFNR - 288f | 23-109849 | MTA-MD288S12B01 | 70001665075 | RPL10 | AFL TELECOMMUNICATIONS LLC | 2026-05-02 | 2026-05-01 | -47 |  | 0 | 256 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-103414 | CB-FE-HT-024MCM-011 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-18 | 32 | 32 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103729 | CB-FE-HT-024MCM-021 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-18 | 92 | 92 | Delivered
MCR Accessories | 23-014994 | 1A52EDW00-600-G | 70001665074 | RPL10 | ANIXTER INC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 48 | 48 | Delivered
MCR Accessories | 23-014995 | 1A52EE000-600-G | 70001665074 | RPL10 | ANIXTER INC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 256 | 256 | Delivered
MCR Accessories | 23-015676 | 1A52HH700-600-G | 70001665074 | RPL10 | ANIXTER INC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 48 | 48 | Delivered
MCR Accessories | 23-015677 | 1A52HGJ00-600-G | 70001665074 | RPL10 | ANIXTER INC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 128 | 128 | Delivered
MCR Accessories | 23-015924 | 1A52JMH00-600-G | 70001665074 | RPL10 | ANIXTER INC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 96 | 96 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-102780 | CB-FB-SM2LCU039 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-11 | -37 | 2026-05-01 | 1152 | 1152 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103384 | CB-FE-HT-024MCM-019 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 91 | 91 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103395 | CB-FE-ET-024MCFMCM-011 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 16 | 16 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103404 | CB-FE-HT-024MCM-017 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-14 | 47 | 47 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103412 | CB-FE-HT-024MCM-018 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 |  | 0 | 55 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-103418 | CB-FE-HT-024MCM-020 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 79 | 79 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103426 | CB-FE-HT-024MCM-008 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 64 | 64 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103722 | CB-FE-HT-024MCM-022 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 71 | 71 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103723 | CB-FE-ET-024MCFMCM-026 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 24 | 24 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103725 | CB-FE-HT-024MCM-024 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 22 | 22 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103726 | CB-FE-HT-024MCM-025 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103727 | CB-FE-ET-024MCFMCM-028 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 12 | 12 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103730 | CB-FE-ET-024MCFMCM-023 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 12 | 12 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103731 | CB-FE-HT-024MCM-023 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 56 | 56 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103732 | CB-FE-HT-024MCM-026 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 3 | 3 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103733 | CB-FE-ET-024MCFMCM-027 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 12 | 12 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103735 | CB-FE-ET-024MCFMCM-029 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 6 | 6 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103736 | CB-FE-ET-024MCFMCM-024 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 18 | 18 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103737 | CB-FE-ET-024MCFMCM-022 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 12 | 12 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105511 | CB-FB-1SCALCU016 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 176 | 576 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105512 | CB-FB-1SCALCU035 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 160 | 384 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105513 | CB-FB-1SCALCU031 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 176 | 432 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105518 | CB-FB-1SCALCU008 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 108 | 96 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105521 | CB-FB-1SCALCU025 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 160 | 432 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105522 | CB-FB-1SCALCU018 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 212 | 528 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105525 | CB-FB-1SCALCU030 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 196 | 720 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105526 | CB-FB-1SCALCU028 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 156 | 576 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105527 | CB-FB-1SCALCU009 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 92 | 624 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105530 | CB-FB-1SCALCU017 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 196 | 624 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105531 | CB-FB-1SCALCU032 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 196 | 720 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105532 | CB-FB-1SCALCU037 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 176 | 288 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105533 | CB-FB-1SCALCU022 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 196 | 624 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105534 | CB-FB-1SCALCU040 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 204 | 192 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105535 | CB-FB-1SCALCU011 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 144 | 528 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105536 | CB-FB-1SCALCU029 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 180 | 432 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105538 | CB-FB-1SCALCU026 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 196 | 720 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105539 | CB-FB-1SCALCU010 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 72 | 432 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105540 | CB-FB-1SCALCU015 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 200 | 528 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105541 | CB-FB-1SCALCU038 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 148 | 432 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105542 | CB-FB-1SCALCU027 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 212 | 576 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105543 | CB-FB-1SCALCU012 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 236 | 720 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105544 | CB-FB-1SCALCU024 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 176 | 576 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105545 | CB-FB-1SCALCU006 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 156 | 48 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105546 | CB-FB-1SCALCU019 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 160 | 576 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105547 | CB-FB-1SCALCU034 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 160 | 528 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105548 | CB-FB-1SCALCU036 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 232 | 912 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105549 | CB-FB-1SCALCU013 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 236 | 768 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105550 | CB-FB-1SCALCU021 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 160 | 528 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105551 | CB-FB-1SCALCU023 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 212 | 576 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105552 | CB-FB-1SCALCU039 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 272 | 336 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105553 | CB-FB-1SCALCU033 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 212 | 576 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105556 | CB-FB-1SCALCU005 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-06-12 | 96 | 96 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105557 | CB-FB-1SCALCU007 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 144 | 336 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105558 | CB-FB-1SCALCU020 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 176 | 576 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105559 | CB-FB-1SCALCU014 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 248 | 624 | Partial
Fiber - Patch Cord - OFNR - 2f | 23-106599 | CB-FE-ET-024MCFMCM-038 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-30 | -48 | 2026-05-08 | 8 | 8 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110572 | CB-FE-ET-384MCFMCM-372 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 384f | 23-110577 | CB-FE-ET-384MCFMCM-252 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110578 | CB-FE-ET-384MCFMCM-113 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-04 | -44 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110579 | CB-FE-ET-384MCFMCM-290 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-01 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110580 | CB-FE-ET-384MCFMCM-107 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110581 | CB-FE-ET-384MCFMCM-099 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110582 | CB-FE-ET-384MCFMCM-159 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110583 | CB-FE-ET-384MCFMCM-182 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-04 | -44 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110587 | CB-FE-ET-384MCFMCM-216 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-07 | -41 | 2026-05-05 | 8 | 8 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110590 | CB-FE-ET-384MCFMCM-360 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-01 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110596 | CB-FE-ET-384MCFMCM-281 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-01 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110602 | CB-FE-ET-384MCFMCM-156 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110605 | CB-FE-ET-384MCFMCM-097 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110607 | CB-FE-ET-384MCFMCM-256 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-01 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110620 | CB-FE-ET-384MCFMCM-220 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110627 | CB-FE-ET-384MCFMCM-228 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-01 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110632 | CB-FE-ET-384MCFMCM-127 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 384f | 23-110633 | CB-FE-ET-384MCFMCM-212 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110635 | CB-FE-ET-384MCFMCM-364 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-01 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110641 | CB-FE-ET-384MCFMCM-376 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-01 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110657 | CB-FE-ET-384MCFMCM-167 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-01 | 6 | 6 | Delivered
Fiber - Extender Trunk - OFNR - 192f | 23-104527 | CB-FE-ET-192MCFMCM-038 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-29 | -49 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100901 | CB-FE-HT-384MCM-032 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 |  | 0 | 4 | Past Due
Fiber - Trunk - OFNR - 384f | 23-100908 | CB-FE-HT-384MCM-008 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 96 | 96 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100909 | CB-FE-HT-384MCM-020 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-01 | 24 | 24 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100925 | CB-FE-HT-384MCM-076 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 |  | 0 | 8 | Past Due
Fiber - Trunk - OFNR - 384f | 23-100928 | CB-FE-HT-384MCM-018 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-12 | -36 | 2026-05-05 | 48 | 48 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100929 | CB-FE-HT-384MCM-040 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-12 | -36 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100935 | CB-FE-HT-384MCM-036 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 192f | 23-101115 | CB-FE-HT-192MCM-007 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 96 | 96 | Delivered
Fiber - Trunk - OFNR - 192f | 23-101125 | CB-FE-HT-192MCM-008 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 96 | 96 | Delivered
Fiber - Trunk - OFNR - 384f | 23-102845 | CB-FE-HT-384MCM-019 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 24 | 24 | Delivered
Fiber - Trunk - OFNR - 384f | 23-102853 | CB-FE-HT-384MCM-023 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-07 | -41 | 2026-05-05 | 24 | 24 | Delivered
Fiber - Trunk - OFNR - 384f | 23-102960 | CB-FE-HT-384MCM-071 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 |  | 0 | 4 | Past Due
Fiber - Trunk - OFNR - 192f | 23-102975 | CB-FE-HT-192MCM-032 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102979 | CB-FE-HT-192MCM-019 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 48 | 48 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102980 | CB-FE-HT-192MCM-058 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 |  | 0 | 4 | Past Due
Fiber - Trunk - OFNR - 192f | 23-102981 | CB-FE-HT-192MCM-012 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-26 | 192 | 96 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102988 | CB-FE-HT-192MCM-044 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-05 | -43 | 2026-05-01 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 384f | 23-103001 | CB-FE-HT-384MCM-141 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 32 | 32 | Delivered
Fiber - Trunk - OFNR - 384f | 23-103009 | CB-FE-HT-384MCM-033 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 6 | 6 | Delivered
Fiber - Trunk - OFNR - 192f | 23-103180 | CB-FE-HT-192MCM-107 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-103181 | CB-FE-HT-192MCM-101 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 6 | 6 | Delivered
Fiber - Trunk - OFNR - 192f | 23-103190 | CB-FE-HT-192MCM-119 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 192f | 23-103202 | CB-FE-HT-192MCM-050 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-07 | -41 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103407 | CB-FE-HT-024MCM-012 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-14 | 64 | 64 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103424 | CB-FE-HT-024MCM-015 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-06 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104255 | CB-FE-HT-096MCM-023 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-06 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104280 | CB-FE-HT-288MCM-095 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104289 | CB-FE-HT-288MCM-092 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-05 | 8 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104297 | CB-FE-HT-288MCM-100 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-05 | -43 | 2026-05-01 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104891 | CB-FE-HT-096MCM-084 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-04 | -44 | 2026-05-05 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104894 | CB-FE-HT-096MCM-079 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-15 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104935 | CB-FE-HT-096MCM-110 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-18 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104938 | CB-FE-HT-096MCM-090 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-06 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105439 | CB-FE-HT-288MCM-123 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105441 | CB-FE-HT-288MCM-108 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105442 | CB-FE-HT-288MCM-111 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105443 | CB-FE-HT-288MCM-122 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105455 | CB-FE-HT-288MCM-102 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 8 | 8 | Delivered
Fiber - Extender Trunk - OFNR - 192f | 23-104500 | CB-FE-ET-192MCFMCM-024 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-04-29 | -49 | 2026-05-05 | 10 | 12 | Partial
Fiber - Extender Trunk - OFNR - 96f | 23-106928 | CB-FE-HT-096MCM-184 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-02 | -46 | 2026-05-06 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110470 | CB-FE-HT-192MCM-160 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-12 | -36 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110473 | CB-FE-HT-096MCM-387 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-05 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110477 | CB-FE-HT-096MCM-395 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-05 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110479 | CB-FE-HT-192MCM-228 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110480 | CB-FE-HT-096MCM-402 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-05 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110481 | CB-FE-HT-096MCM-424 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-05 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110482 | CB-FE-HT-096MCM-394 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-22 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110484 | CB-FE-HT-096MCM-401 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-05 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110489 | CB-FE-HT-192MCM-216 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110491 | CB-FE-HT-192MCM-116 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110494 | CB-FE-HT-192MCM-188 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110495 | CB-FE-HT-192MCM-176 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110496 | CB-FE-HT-192MCM-104 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110497 | CB-FE-HT-096MCM-413 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-05 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110501 | CB-FE-HT-192MCM-154 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110504 | CB-FE-HT-096MCM-382 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-05 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110505 | CB-FE-HT-192MCM-164 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-07 | -41 |  | 0 | 4 | Past Due
Fiber - Trunk - OFNR - 96f | 23-110506 | CB-FE-HT-096MCM-407 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-05 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110508 | CB-FE-HT-192MCM-139 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110256 | CB-FE-HT-288MCM-136 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110528 | CB-FE-HT-288MCM-222 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110529 | CB-FE-HT-288MCM-160 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-12 | -36 |  | 0 | 8 | Past Due
Fiber - Trunk - OFNR - 384f | 23-110534 | CB-FE-HT-288MCM-117 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110559 | CB-FE-HT-288MCM-140 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-12 | -36 | 2026-05-05 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110561 | CB-FE-HT-288MCM-232 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110565 | CB-FE-HT-288MCM-172 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-04 | -44 | 2026-04-29 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110570 | CB-FE-HT-288MCM-168 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110593 | CB-FE-HT-288MCM-252 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110594 | CB-FE-HT-288MCM-240 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-06 | -42 | 2026-05-01 | 4 | 4 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103417 | CB-FE-HT-024MCM-016 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-08 | 16 | 16 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103422 | CB-FE-HT-024MCM-013 | 70001631926 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 32 | 32 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110566 | CB-FE-ET-384MCFMCM-285 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110567 | CB-FE-ET-384MCFMCM-131 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110569 | CB-FE-ET-384MCFMCM-241 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110573 | CB-FE-ET-384MCFMCM-327 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110574 | CB-FE-ET-384MCFMCM-151 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110575 | CB-FE-ET-384MCFMCM-163 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110591 | CB-FE-ET-384MCFMCM-175 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110595 | CB-FE-ET-384MCFMCM-265 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110597 | CB-FE-ET-384MCFMCM-330 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110598 | CB-FE-ET-384MCFMCM-137 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110599 | CB-FE-ET-384MCFMCM-169 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110601 | CB-FE-ET-384MCFMCM-147 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110603 | CB-FE-ET-384MCFMCM-305 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110613 | CB-FE-ET-384MCFMCM-154 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 6 | 6 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110615 | CB-FE-ET-384MCFMCM-269 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110618 | CB-FE-ET-384MCFMCM-200 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110621 | CB-FE-ET-384MCFMCM-057 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-12 | -36 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110622 | CB-FE-ET-384MCFMCM-179 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 6 | 6 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110624 | CB-FE-ET-384MCFMCM-310 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110629 | CB-FE-ET-384MCFMCM-225 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110630 | CB-FE-ET-384MCFMCM-190 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110634 | CB-FE-ET-384MCFMCM-129 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110638 | CB-FE-ET-384MCFMCM-257 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110642 | CB-FE-ET-384MCFMCM-262 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110643 | CB-FE-ET-384MCFMCM-103 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110645 | CB-FE-ET-384MCFMCM-298 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110646 | CB-FE-ET-384MCFMCM-153 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110647 | CB-FE-ET-384MCFMCM-347 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110648 | CB-FE-ET-384MCFMCM-105 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110654 | CB-FE-ET-384MCFMCM-119 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110658 | CB-FE-ET-384MCFMCM-343 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100917 | CB-FE-HT-384MCM-034 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 6 | 6 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100918 | CB-FE-HT-384MCM-070 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 16 | 16 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100937 | CB-FE-HT-384MCM-038 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100938 | CB-FE-HT-384MCM-024 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-08 | -40 | 2026-05-05 | 48 | 48 | Delivered
Fiber - Trunk - OFNR - 384f | 23-102831 | CB-FE-HT-384MCM-025 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 24 | 24 | Delivered
Fiber - Trunk - OFNR - 384f | 23-102833 | CB-FE-HT-384MCM-017 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-21 | 32 | 24 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102972 | CB-FE-HT-192MCM-011 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-29 | 192 | 96 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102973 | CB-FE-HT-192MCM-094 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102983 | CB-FE-HT-192MCM-045 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102989 | CB-FE-HT-192MCM-082 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-103197 | CB-FE-HT-192MCM-113 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-103199 | CB-FE-HT-192MCM-064 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104242 | CB-FE-HT-288MCM-067 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104269 | CB-FE-HT-288MCM-079 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104276 | CB-FE-HT-288MCM-077 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104281 | CB-FE-HT-288MCM-086 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-104295 | CB-FE-HT-288MCM-098 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104863 | CB-FE-HT-096MCM-058 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 3 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104865 | CB-FE-HT-096MCM-046 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104869 | CB-FE-HT-096MCM-071 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-18 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104871 | CB-FE-HT-096MCM-085 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-18 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104874 | CB-FE-HT-096MCM-060 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104875 | CB-FE-HT-096MCM-076 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104879 | CB-FE-HT-096MCM-072 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104880 | CB-FE-HT-096MCM-051 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104881 | CB-FE-HT-096MCM-082 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104883 | CB-FE-HT-096MCM-077 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-15 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104884 | CB-FE-HT-096MCM-052 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104887 | CB-FE-HT-096MCM-066 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104889 | CB-FE-HT-096MCM-089 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104890 | CB-FE-HT-096MCM-083 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-18 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104895 | CB-FE-HT-096MCM-065 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-15 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104896 | CB-FE-HT-096MCM-050 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104897 | CB-FE-HT-096MCM-070 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104899 | CB-FE-HT-096MCM-064 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104900 | CB-FE-HT-096MCM-053 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104901 | CB-FE-HT-096MCM-078 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104906 | CB-FE-HT-096MCM-047 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104909 | CB-FE-HT-096MCM-059 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104913 | CB-FE-HT-096MCM-095 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104915 | CB-FE-HT-096MCM-122 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104919 | CB-FE-HT-096MCM-116 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-18 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104921 | CB-FE-HT-096MCM-108 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-14 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104922 | CB-FE-HT-096MCM-128 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-15 | 3 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104925 | CB-FE-HT-096MCM-107 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-20 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104926 | CB-FE-HT-096MCM-102 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-15 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104927 | CB-FE-HT-096MCM-101 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104929 | CB-FE-HT-096MCM-114 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-15 | 3 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104934 | CB-FE-HT-096MCM-115 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104936 | CB-FE-HT-096MCM-109 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104939 | CB-FE-HT-096MCM-126 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-19 | -29 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104940 | CB-FE-HT-096MCM-096 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-19 | -29 | 2026-05-15 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104941 | CB-FE-HT-096MCM-121 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-19 | -29 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104943 | CB-FE-HT-096MCM-120 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-19 | -29 | 2026-05-15 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104945 | CB-FE-HT-096MCM-091 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-15 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104948 | CB-FE-HT-096MCM-127 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-15 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 384f | 23-105334 | CB-FE-HT-384MCM-139 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105437 | CB-FE-HT-288MCM-145 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 12 | 12 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105438 | CB-FE-HT-288MCM-150 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105444 | CB-FE-HT-288MCM-211 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105445 | CB-FE-HT-288MCM-178 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105446 | CB-FE-HT-288MCM-179 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105447 | CB-FE-HT-288MCM-141 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 288f | 23-105457 | CB-FE-HT-288MCM-203 | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 8 | 8 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106910 | CB-FE-HT-096MCM-188 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-11 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108638 | CB-FE-HT-096MCM-357 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108698 | CB-FE-HT-096MCM-390 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110512 | CB-FE-ET-384MCFMCM-277 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-07 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110513 | CB-FE-ET-384MCFMCM-145 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110514 | CB-FE-ET-384MCFMCM-194 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110515 | CB-FE-ET-384MCFMCM-149 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110518 | CB-FE-ET-384MCFMCM-049 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110519 | CB-FE-ET-384MCFMCM-133 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-21 | 5 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110520 | CB-FE-ET-384MCFMCM-273 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-110524 | CB-FE-ET-384MCFMCM-301 | 70001631930 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 192f | 23-108725 | CB-FE-HT-192MCM-035 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-14 | -34 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110428 | CB-FE-HT-096MCM-431 | 70001631931 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-15 | -33 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110459 | CB-FE-HT-192MCM-222 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110460 | CB-FE-HT-384MCM-142 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110461 | CB-FE-HT-192MCM-091 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 |  | 0 | 4 | Past Due
Fiber - Trunk - OFNR - 96f | 23-110462 | CB-FE-HT-096MCM-369 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110464 | CB-FE-HT-192MCM-122 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 |  | 0 | 4 | Past Due
Fiber - Trunk - OFNR - 192f | 23-110465 | CB-FE-HT-192MCM-067 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110466 | CB-FE-HT-096MCM-334 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110467 | CB-FE-HT-096MCM-315 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110468 | CB-FE-HT-096MCM-408 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110469 | CB-FE-HT-384MCM-035 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110471 | CB-FE-HT-192MCM-158 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110472 | CB-FE-HT-096MCM-375 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-05 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110475 | CB-FE-HT-096MCM-400 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-21 | 3 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110478 | CB-FE-HT-096MCM-356 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110483 | CB-FE-HT-192MCM-138 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110486 | CB-FE-HT-384MCM-207 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110488 | CB-FE-HT-096MCM-351 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110490 | CB-FE-HT-192MCM-055 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110492 | CB-FE-HT-192MCM-073 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110498 | CB-FE-HT-384MCM-201 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 10 | 10 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110500 | CB-FE-HT-096MCM-340 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110503 | CB-FE-HT-096MCM-331 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110507 | CB-FE-HT-096MCM-346 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-13 | -35 | 2026-05-08 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110517 | CB-FE-HT-288MCM-174 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 12 | 12 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110525 | CB-FE-HT-288MCM-182 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110541 | CB-FE-HT-288MCM-170 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110548 | CB-FE-HT-288MCM-210 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-08 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110549 | CB-FE-HT-288MCM-162 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 8 | 8 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110560 | CB-FE-HT-288MCM-183 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
Fiber - Trunk - OFNR - 384f | 23-110584 | CB-FE-HT-288MCM-234 | 70001631933 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-02 | 2026-05-18 | -30 | 2026-05-05 | 4 | 4 | Delivered
MCR | 23-014539 | 1A310PC00-600-G | 70001665073 | RPL10 | INGRASYS TECHNOLOGY USA INC | 2026-05-02 | 2026-05-04 | -44 | 2026-05-11 | 128 | 128 | Delivered
Hardware - OPE | 23-107481 | 1A72KQF00-600-G | 70001665080 | RPL10 | INGRASYS TECHNOLOGY USA INC | 2026-05-02 | 2026-05-20 | -28 | 2026-05-19 | 324 | 400 | Partial
Hardware - OPE | 23-107481 | FC-10IN-47RUFAP-SET | 70001665081 | RPL10 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-02 | 2026-11-15 | 151 |  | 0 | 400 | Past Due
Hardware - MBOX | 23-107115 | MC-10IN1RU-2X-LC-24MMC-SM-01 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-11 | 86 |  | 0 | 64 | Past Due
Hardware - FAP | 23-107113 | MC-10IN1RU-FAPB-2P-MMC-01 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-09 | -8 | 2026-05-20 | 2905 | 2905 | Delivered
Hardware - FAP | 23-108524 | MC-10IN1RU-2X-5SP-PON-01 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-08-21 | 65 |  | 0 | 144 | Past Due
Hardware - FAP | 23-101177 | FP-F-01RU128MCA | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-14 | 77 | 77 | Delivered
Fiber - Trunk - OFNR - 96f | 23-110422 | TAT-96-MM24PMM24P-A2J-323 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-110485 | TAT-96-MM24PMM24P-A2J-264 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-110493 | TAT-96-MM24PMM24P-A2J-311 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-110499 | TAT-96-MM24PMM24P-A2J-267 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104863 | CB-FE-HT-096MCM-058 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104869 | CB-FE-HT-096MCM-071 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104871 | CB-FE-HT-096MCM-085 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104876 | CB-FE-HT-096MCM-061 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104878 | CB-FE-HT-096MCM-081 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104883 | CB-FE-HT-096MCM-077 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104886 | CB-FE-HT-096MCM-087 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104889 | CB-FE-HT-096MCM-089 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104890 | CB-FE-HT-096MCM-083 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104894 | CB-FE-HT-096MCM-079 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104895 | CB-FE-HT-096MCM-065 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104902 | CB-FE-HT-096MCM-086 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-14 | 2 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104907 | CB-FE-HT-096MCM-067 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104912 | CB-FE-HT-096MCM-073 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104914 | CB-FE-HT-096MCM-097 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104915 | CB-FE-HT-096MCM-122 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104917 | CB-FE-HT-096MCM-092 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104919 | CB-FE-HT-096MCM-116 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104920 | CB-FE-HT-096MCM-111 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104921 | CB-FE-HT-096MCM-108 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104922 | CB-FE-HT-096MCM-128 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-06-05 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104923 | CB-FE-HT-096MCM-098 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104924 | CB-FE-HT-096MCM-106 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104926 | CB-FE-HT-096MCM-102 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104929 | CB-FE-HT-096MCM-114 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104930 | CB-FE-HT-096MCM-093 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104931 | CB-FE-HT-096MCM-104 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 2 | 2 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104933 | CB-FE-HT-096MCM-117 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104935 | CB-FE-HT-096MCM-110 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104940 | CB-FE-HT-096MCM-096 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104942 | CB-FE-HT-096MCM-123 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104943 | CB-FE-HT-096MCM-120 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104944 | CB-FE-HT-096MCM-112 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104945 | CB-FE-HT-096MCM-091 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104948 | CB-FE-HT-096MCM-127 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104949 | CB-FE-HT-096MCM-124 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 96f | 23-104951 | CB-FE-HT-096MCM-099 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-18 | 1 | 1 | Delivered
Fiber - Trunk - OFNR - 192f | 23-101115 | TAT-192-MM24PMM24P-A2J-007 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 18 | 18 | Delivered
Fiber - Trunk - OFNR - 192f | 23-101125 | TAT-192-MM24PMM24P-A2J-008 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 54 | Past Due
Fiber - Trunk - OFNR - 192f | 23-102971 | TAT-192-MM24PMM24P-A2J-021 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 38 | 18 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102979 | TAT-192-MM24PMM24P-A2J-019 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 48 | 36 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102986 | TAT-192-MM24PMM24P-A2J-013 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 134 | 36 | Delivered
Fiber - Trunk - OFNR - 192f | 23-105735 | TAT-192-MM24PMM24P-A2J-015 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 18 | Past Due
Fiber - Trunk - OFNR - 192f | 23-106870 | TAT-192-MM24PMM24P-A2J-022 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 86 | 18 | Delivered
Fiber - Trunk - OFNR - 192f | 23-108729 | TAT-192-MM24PMM24P-A2J-018 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 32 | 36 | Partial
Fiber - Trunk - OFNR - 192f | 23-110433 | TAT-192-MM24PMM24P-A2J-016 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 18 | Past Due
Fiber - Trunk - OFNR - 192f | 23-110502 | TAT-192-MM24PMM24P-A2J-014 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 132 | 36 | Delivered
Fiber - Trunk - OFNR - 192f | 23-101115 | CB-FE-HT-192MCM-007 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-28 | 36 | 36 | Delivered
Fiber - Trunk - OFNR - 192f | 23-101125 | CB-FE-HT-192MCM-008 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 36 | 36 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102971 | CB-FE-HT-192MCM-021 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 18 | Past Due
Fiber - Trunk - OFNR - 192f | 23-102979 | CB-FE-HT-192MCM-019 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-29 | 36 | 36 | Delivered
Fiber - Trunk - OFNR - 192f | 23-102986 | CB-FE-HT-192MCM-013 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-28 | 36 | 36 | Delivered
Fiber - Trunk - OFNR - 192f | 23-105735 | CB-FE-HT-192MCM-015 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-27 | 18 | 18 | Delivered
Fiber - Trunk - OFNR - 192f | 23-106870 | CB-FE-HT-192MCM-022 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 18 | Past Due
Fiber - Trunk - OFNR - 192f | 23-108729 | CB-FE-HT-192MCM-018 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-21 | 36 | 36 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110433 | CB-FE-HT-192MCM-016 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-21 | 18 | 18 | Delivered
Fiber - Trunk - OFNR - 192f | 23-110502 | CB-FE-HT-192MCM-014 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 36 | Past Due
Fiber - Trunk - OFNR - 384f | 23-100901 | TAT-384-MM24PMM24P-A2J-032 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-17 | 30 |  | 0 | 10 | Past Due
Fiber - Trunk - OFNR - 384f | 23-100908 | TAT-384-MM24PMM24P-A2J-008 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-17 | 30 |  | 0 | 18 | Past Due
Fiber - Trunk - OFNR - 384f | 23-100928 | TAT-384-MM24PMM24P-A2J-018 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-29 | -19 | 2026-06-12 | 8 | 16 | Partial
Fiber - Trunk - OFNR - 384f | 23-100937 | TAT-384-MM24PMM24P-A2J-038 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 10 | Past Due
Fiber - Trunk - OFNR - 384f | 23-100945 | TAT-384-MM24PMM24P-A2J-022 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-17 | 30 |  | 2 | 18 | Partial
Fiber - Trunk - OFNR - 384f | 23-100946 | TAT-384-MM24PMM24P-A2J-016 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-17 | 30 |  | 0 | 38 | Past Due
Fiber - Trunk - OFNR - 384f | 23-102833 | TAT-384-MM24PMM24P-A2J-017 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-10 | 23 |  | 0 | 16 | Past Due
Fiber - Trunk - OFNR - 384f | 23-102845 | TAT-384-MM24PMM24P-A2J-019 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-10 | 23 |  | 0 | 36 | Past Due
Fiber - Trunk - OFNR - 384f | 23-102998 | TAT-384-MM24PMM24P-A2J-021 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-29 | -19 |  | 0 | 8 | Past Due
Fiber - Trunk - OFNR - 384f | 23-103009 | TAT-384-MM24PMM24P-A2J-033 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-29 | -19 |  | 0 | 10 | Past Due
Fiber - Trunk - OFNR - 384f | 23-103099 | TAT-384-MM24PMM24P-A2J-027 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-29 | -19 |  | 0 | 10 | Past Due
Fiber - Trunk - OFNR - 384f | 23-106006 | TAT-384-MM24PMM24P-A2J-015 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-10 | 23 |  | 0 | 44 | Past Due
Fiber - Trunk - OFNR - 384f | 23-108943 | TAT-384-MM24PMM24P-A2J-009 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-17 | 30 |  | 0 | 36 | Past Due
Fiber - Trunk - OFNR - 384f | 23-110442 | TAT-384-MM24PMM24P-A2J-007 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-29 | -19 |  | 0 | 18 | Past Due
Fiber - Trunk - OFNR - 384f | 23-100908 | CB-FE-HT-384MCM-008 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-27 | 36 | 36 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100912 | CB-FE-HT-384MCM-014 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 28 | Past Due
Fiber - Trunk - OFNR - 384f | 23-100928 | CB-FE-HT-384MCM-018 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-29 | 54 | 54 | Delivered
Fiber - Trunk - OFNR - 384f | 23-100946 | CB-FE-HT-384MCM-016 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-29 | 54 | 54 | Delivered
Fiber - Trunk - OFNR - 384f | 23-102833 | CB-FE-HT-384MCM-017 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 8 | Past Due
Fiber - Trunk - OFNR - 384f | 23-102845 | CB-FE-HT-384MCM-019 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-28 | 10 | 10 | Delivered
Fiber - Trunk - OFNR - 384f | 23-102998 | CB-FE-HT-384MCM-021 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 36 | 36 | Delivered
Fiber - Trunk - OFNR - 384f | 23-106006 | CB-FE-HT-384MCM-015 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-27 | 108 | 36 | Delivered
Fiber - Trunk - OFNR - 384f | 23-108943 | CB-FE-HT-384MCM-009 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 8 | Past Due
Fiber - Trunk - OFNR - 384f | 23-110442 | CB-FE-HT-384MCM-007 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-14 | 18 | 18 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106877 | TAT-96-MM24PMM24P-A2J-174 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106879 | TAT-96-MM24PMM24P-A2J-226 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106893 | TAT-96-MM24PMM24P-A2J-170 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106899 | TAT-96-MM24PMM24P-A2J-137 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106905 | TAT-96-MM24PMM24P-A2J-131 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106906 | TAT-96-MM24PMM24P-A2J-220 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106912 | TAT-96-MM24PMM24P-A2J-133 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106913 | TAT-96-MM24PMM24P-A2J-255 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106920 | TAT-96-MM24PMM24P-A2J-152 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106924 | TAT-96-MM24PMM24P-A2J-251 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106926 | TAT-96-MM24PMM24P-A2J-143 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106927 | TAT-96-MM24PMM24P-A2J-199 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106930 | TAT-96-MM24PMM24P-A2J-232 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106937 | TAT-96-MM24PMM24P-A2J-158 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106938 | TAT-96-MM24PMM24P-A2J-193 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106939 | TAT-96-MM24PMM24P-A2J-245 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106940 | TAT-96-MM24PMM24P-A2J-243 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106942 | TAT-96-MM24PMM24P-A2J-162 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106944 | TAT-96-MM24PMM24P-A2J-149 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106947 | TAT-96-MM24PMM24P-A2J-236 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106949 | TAT-96-MM24PMM24P-A2J-230 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106951 | TAT-96-MM24PMM24P-A2J-176 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106953 | TAT-96-MM24PMM24P-A2J-214 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106959 | TAT-96-MM24PMM24P-A2J-164 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106963 | TAT-96-MM24PMM24P-A2J-208 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106967 | TAT-96-MM24PMM24P-A2J-187 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106968 | TAT-96-MM24PMM24P-A2J-168 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106972 | TAT-96-MM24PMM24P-A2J-249 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106979 | TAT-96-MM24PMM24P-A2J-180 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106981 | TAT-96-MM24PMM24P-A2J-145 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106983 | TAT-96-MM24PMM24P-A2J-139 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106986 | TAT-96-MM24PMM24P-A2J-155 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106996 | TAT-96-MM24PMM24P-A2J-239 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108622 | TAT-96-MM24PMM24P-A2J-280 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108623 | TAT-96-MM24PMM24P-A2J-299 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108624 | TAT-96-MM24PMM24P-A2J-317 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108629 | TAT-96-MM24PMM24P-A2J-286 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108639 | TAT-96-MM24PMM24P-A2J-305 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108643 | TAT-96-MM24PMM24P-A2J-301 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108649 | TAT-96-MM24PMM24P-A2J-288 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108660 | TAT-96-MM24PMM24P-A2J-257 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108662 | TAT-96-MM24PMM24P-A2J-270 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108670 | TAT-96-MM24PMM24P-A2J-292 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108674 | TAT-96-MM24PMM24P-A2J-295 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108683 | TAT-96-MM24PMM24P-A2J-282 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108688 | TAT-96-MM24PMM24P-A2J-276 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108689 | TAT-96-MM24PMM24P-A2J-274 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108694 | TAT-96-MM24PMM24P-A2J-261 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-15 | -2 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108626 | CB-FE-HT-096MCM-279 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108631 | CB-FE-HT-096MCM-322 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108637 | CB-FE-HT-096MCM-129 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108640 | CB-FE-HT-096MCM-291 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-29 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108641 | CB-FE-HT-096MCM-303 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108642 | CB-FE-HT-096MCM-327 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108645 | CB-FE-HT-096MCM-278 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108647 | CB-FE-HT-096MCM-290 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108648 | CB-FE-HT-096MCM-296 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-108661 | CB-FE-HT-096MCM-272 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108663 | CB-FE-HT-096MCM-309 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108671 | CB-FE-HT-096MCM-259 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108675 | CB-FE-HT-096MCM-316 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108677 | CB-FE-HT-096MCM-284 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108679 | CB-FE-HT-096MCM-297 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108680 | CB-FE-HT-096MCM-266 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-28 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108690 | CB-FE-HT-096MCM-260 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108696 | CB-FE-HT-096MCM-285 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-108699 | CB-FE-HT-096MCM-265 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106883 | CB-FE-HT-096MCM-172 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106884 | CB-FE-HT-096MCM-240 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106887 | CB-FE-HT-096MCM-141 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106894 | CB-FE-HT-096MCM-147 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106895 | CB-FE-HT-096MCM-173 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106900 | CB-FE-HT-096MCM-234 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-27 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106901 | CB-FE-HT-096MCM-148 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106902 | CB-FE-HT-096MCM-178 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106909 | CB-FE-HT-096MCM-135 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106914 | CB-FE-HT-096MCM-197 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-28 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106917 | CB-FE-HT-096MCM-191 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-20 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106922 | CB-FE-HT-096MCM-216 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-20 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106925 | CB-FE-HT-096MCM-223 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-27 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106928 | CB-FE-HT-096MCM-184 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-20 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106929 | CB-FE-HT-096MCM-179 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106933 | CB-FE-HT-096MCM-160 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106936 | CB-FE-HT-096MCM-167 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-28 | 4 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106941 | CB-FE-HT-096MCM-166 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106943 | CB-FE-HT-096MCM-203 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106945 | CB-FE-HT-096MCM-154 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-14 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106948 | CB-FE-HT-096MCM-142 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 | 2026-05-15 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106954 | CB-FE-HT-096MCM-241 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106969 | CB-FE-HT-096MCM-235 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-27 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106970 | CB-FE-HT-096MCM-229 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-27 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106974 | CB-FE-HT-096MCM-153 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-20 | -28 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106975 | CB-FE-HT-096MCM-254 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-06-02 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 96f | 23-106977 | CB-FE-HT-096MCM-247 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 96f | 23-106998 | CB-FE-HT-096MCM-253 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-20 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109714 | TAT-288-MM24PMM24R-A2E-229 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109716 | TAT-288-MM24PMM24R-A2E-087 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109719 | TAT-288-MM24PMM24R-A2E-058 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109720 | TAT-288-MM24PMM24R-A2E-128 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109721 | TAT-288-MM24PMM24R-A2E-197 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109722 | TAT-288-MM24PMM24R-A2E-259 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109725 | TAT-288-MM24PMM24R-A2E-121 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109726 | TAT-288-MM24PMM24R-A2E-221 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109727 | TAT-288-MM24PMM24R-A2E-272 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109729 | TAT-288-MM24PMM24R-A2E-268 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109730 | TAT-288-MM24PMM24R-A2E-080 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109731 | TAT-288-MM24PMM24R-A2E-204 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109733 | TAT-288-MM24PMM24R-A2E-285 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109734 | TAT-288-MM24PMM24R-A2E-117 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109735 | TAT-288-MM24PMM24R-A2E-234 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109737 | TAT-288-MM24PMM24R-A2E-161 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109739 | TAT-288-MM24PMM24R-A2E-293 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109740 | TAT-288-MM24PMM24R-A2E-279 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109741 | TAT-288-MM24PMM24R-A2E-206 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109742 | TAT-288-MM24PMM24R-A2E-198 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109744 | TAT-288-MM24PMM24R-A2E-078 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 1 | 2 | Partial
Fiber - Extender Trunk - OFNR - 288f | 23-109745 | TAT-288-MM24PMM24R-A2E-132 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 3 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109746 | TAT-288-MM24PMM24R-A2E-210 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109748 | TAT-288-MM24PMM24R-A2E-103 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109749 | TAT-288-MM24PMM24R-A2E-067 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109750 | TAT-288-MM24PMM24R-A2E-205 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109751 | TAT-288-MM24PMM24R-A2E-280 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109752 | TAT-288-MM24PMM24R-A2E-086 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109753 | TAT-288-MM24PMM24R-A2E-162 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109754 | TAT-288-MM24PMM24R-A2E-247 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109755 | TAT-288-MM24PMM24R-A2E-173 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109756 | TAT-288-MM24PMM24R-A2E-209 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109759 | TAT-288-MM24PMM24R-A2E-267 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109760 | TAT-288-MM24PMM24R-A2E-246 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109761 | TAT-288-MM24PMM24R-A2E-174 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 3 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109762 | TAT-288-MM24PMM24R-A2E-235 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109767 | TAT-288-MM24PMM24R-A2E-230 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109770 | TAT-288-MM24PMM24R-A2E-242 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109772 | TAT-288-MM24PMM24R-A2E-092 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 3 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109773 | TAT-288-MM24PMM24R-A2E-148 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109774 | TAT-288-MM24PMM24R-A2E-271 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109775 | TAT-288-MM24PMM24R-A2E-066 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 1 | 2 | Partial
Fiber - Extender Trunk - OFNR - 288f | 23-109776 | TAT-288-MM24PMM24R-A2E-112 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109777 | TAT-288-MM24PMM24R-A2E-091 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 3 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109778 | TAT-288-MM24PMM24R-A2E-243 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109780 | TAT-288-MM24PMM24R-A2E-124 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 3 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109781 | TAT-288-MM24PMM24R-A2E-146 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109789 | TAT-288-MM24PMM24R-A2E-116 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109790 | TAT-288-MM24PMM24R-A2E-095 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109791 | TAT-288-MM24PMM24R-A2E-292 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109792 | TAT-288-MM24PMM24R-A2E-201 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109793 | TAT-288-MM24PMM24R-A2E-149 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109794 | TAT-288-MM24PMM24R-A2E-177 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109795 | TAT-288-MM24PMM24R-A2E-188 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109797 | TAT-288-MM24PMM24R-A2E-065 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109798 | TAT-288-MM24PMM24R-A2E-083 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109799 | TAT-288-MM24PMM24R-A2E-070 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109801 | TAT-288-MM24PMM24R-A2E-144 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109803 | TAT-288-MM24PMM24R-A2E-137 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109804 | TAT-288-MM24PMM24R-A2E-212 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109805 | TAT-288-MM24PMM24R-A2E-100 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109806 | TAT-288-MM24PMM24R-A2E-119 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109807 | TAT-288-MM24PMM24R-A2E-189 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109808 | TAT-288-MM24PMM24R-A2E-059 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109809 | TAT-288-MM24PMM24R-A2E-096 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109810 | TAT-288-MM24PMM24R-A2E-129 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109813 | TAT-288-MM24PMM24R-A2E-071 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109814 | TAT-288-MM24PMM24R-A2E-136 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-09 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109815 | TAT-288-MM24PMM24R-A2E-109 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109816 | TAT-288-MM24PMM24R-A2E-217 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109819 | TAT-288-MM24PMM24R-A2E-255 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109820 | TAT-288-MM24PMM24R-A2E-125 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 3 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109822 | TAT-288-MM24PMM24R-A2E-099 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105238 | TAT-288-MM24PMM24R-A2E-111 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105239 | TAT-288-MM24PMM24R-A2E-133 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 3 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-105240 | TAT-288-MM24PMM24R-A2E-211 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105241 | TAT-288-MM24PMM24R-A2E-122 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105242 | TAT-288-MM24PMM24R-A2E-199 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105243 | TAT-288-MM24PMM24R-A2E-113 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105248 | TAT-288-MM24PMM24R-A2E-134 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-105249 | TAT-288-MM24PMM24R-A2E-138 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-105250 | TAT-288-MM24PMM24R-A2E-154 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105252 | TAT-288-MM24PMM24R-A2E-187 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-105254 | TAT-288-MM24PMM24R-A2E-135 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-105255 | TAT-288-MM24PMM24R-A2E-153 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105256 | TAT-288-MM24PMM24R-A2E-110 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 2 | Partial
Fiber - Extender Trunk - OFNR - 288f | 23-105257 | TAT-288-MM24PMM24R-A2E-175 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-105258 | TAT-288-MM24PMM24R-A2E-145 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105263 | TAT-288-MM24PMM24R-A2E-147 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105264 | TAT-288-MM24PMM24R-A2E-163 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105265 | TAT-288-MM24PMM24R-A2E-123 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105266 | TAT-288-MM24PMM24R-A2E-150 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105269 | TAT-288-MM24PMM24R-A2E-157 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 3 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105272 | TAT-288-MM24PMM24R-A2E-141 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105276 | TAT-288-MM24PMM24R-A2E-166 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105281 | TAT-288-MM24PMM24R-A2E-120 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 3 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109697 | TAT-288-MM24PMM24R-A2E-104 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109700 | TAT-288-MM24PMM24R-A2E-186 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 2 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109701 | TAT-288-MM24PMM24R-A2E-158 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 3 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109702 | TAT-288-MM24PMM24R-A2E-084 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109703 | TAT-288-MM24PMM24R-A2E-088 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109706 | TAT-288-MM24PMM24R-A2E-222 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109707 | TAT-288-MM24PMM24R-A2E-176 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109708 | TAT-288-MM24PMM24R-A2E-167 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-03 | 16 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109709 | TAT-288-MM24PMM24R-A2E-218 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109710 | TAT-288-MM24PMM24R-A2E-260 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109711 | TAT-288-MM24PMM24R-A2E-200 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109712 | TAT-288-MM24PMM24R-A2E-284 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109713 | TAT-288-MM24PMM24R-A2E-254 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109698 | CB-FE-ET-288MCFMCM-131 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109699 | CB-FE-ET-288MCFMCM-195 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109700 | CB-FE-ET-288MCFMCM-186 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109701 | CB-FE-ET-288MCFMCM-158 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-27 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109704 | CB-FE-ET-288MCFMCM-068 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109705 | CB-FE-ET-288MCFMCM-207 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109706 | CB-FE-ET-288MCFMCM-222 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 3 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109707 | CB-FE-ET-288MCFMCM-176 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-29 | 5 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109709 | CB-FE-ET-288MCFMCM-218 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109715 | CB-FE-ET-288MCFMCM-160 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109717 | CB-FE-ET-288MCFMCM-155 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-28 | 5 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109718 | CB-FE-ET-288MCFMCM-194 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109721 | CB-FE-ET-288MCFMCM-197 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109723 | CB-FE-ET-288MCFMCM-288 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109724 | CB-FE-ET-288MCFMCM-106 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109725 | CB-FE-ET-288MCFMCM-121 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109726 | CB-FE-ET-288MCFMCM-221 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109728 | CB-FE-ET-288MCFMCM-168 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-26 | 8 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109730 | CB-FE-ET-288MCFMCM-080 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109732 | CB-FE-ET-288MCFMCM-185 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 4 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109735 | CB-FE-ET-288MCFMCM-234 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109736 | CB-FE-ET-288MCFMCM-102 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109737 | CB-FE-ET-288MCFMCM-161 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-29 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109738 | CB-FE-ET-288MCFMCM-152 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-26 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109741 | CB-FE-ET-288MCFMCM-206 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109742 | CB-FE-ET-288MCFMCM-198 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109743 | CB-FE-ET-288MCFMCM-077 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109744 | CB-FE-ET-288MCFMCM-078 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109745 | CB-FE-ET-288MCFMCM-132 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-28 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109746 | CB-FE-ET-288MCFMCM-210 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109747 | CB-FE-ET-288MCFMCM-156 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109748 | CB-FE-ET-288MCFMCM-103 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109749 | CB-FE-ET-288MCFMCM-067 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109750 | CB-FE-ET-288MCFMCM-205 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109754 | CB-FE-ET-288MCFMCM-247 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-28 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109755 | CB-FE-ET-288MCFMCM-173 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-29 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109756 | CB-FE-ET-288MCFMCM-209 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109757 | CB-FE-ET-288MCFMCM-169 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109758 | CB-FE-ET-288MCFMCM-093 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109760 | CB-FE-ET-288MCFMCM-246 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-29 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109761 | CB-FE-ET-288MCFMCM-174 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109762 | CB-FE-ET-288MCFMCM-235 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-28 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109763 | CB-FE-ET-288MCFMCM-165 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109764 | CB-FE-ET-288MCFMCM-193 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109765 | CB-FE-ET-288MCFMCM-252 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-29 | 2 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109766 | CB-FE-ET-288MCFMCM-182 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109767 | CB-FE-ET-288MCFMCM-230 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109769 | CB-FE-ET-288MCFMCM-181 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109770 | CB-FE-ET-288MCFMCM-242 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-29 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109771 | CB-FE-ET-288MCFMCM-264 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-26 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109772 | CB-FE-ET-288MCFMCM-092 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-29 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109773 | CB-FE-ET-288MCFMCM-148 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109775 | CB-FE-ET-288MCFMCM-066 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109776 | CB-FE-ET-288MCFMCM-112 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109777 | CB-FE-ET-288MCFMCM-091 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109778 | CB-FE-ET-288MCFMCM-243 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-29 | 4 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109779 | CB-FE-ET-288MCFMCM-196 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109780 | CB-FE-ET-288MCFMCM-124 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109781 | CB-FE-ET-288MCFMCM-146 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109782 | CB-FE-ET-288MCFMCM-220 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-26 | 24 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109793 | CB-FE-ET-288MCFMCM-149 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109794 | CB-FE-ET-288MCFMCM-177 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 8 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109795 | CB-FE-ET-288MCFMCM-188 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109796 | CB-FE-ET-288MCFMCM-248 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109801 | CB-FE-ET-288MCFMCM-144 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109802 | CB-FE-ET-288MCFMCM-081 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109803 | CB-FE-ET-288MCFMCM-137 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109806 | CB-FE-ET-288MCFMCM-119 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 4 | 4 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109807 | CB-FE-ET-288MCFMCM-189 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-29 | 8 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109811 | CB-FE-ET-288MCFMCM-105 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109812 | CB-FE-ET-288MCFMCM-208 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-21 | 3 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109814 | CB-FE-ET-288MCFMCM-136 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109816 | CB-FE-ET-288MCFMCM-217 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-29 | 5 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109817 | CB-FE-ET-288MCFMCM-090 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-18 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109818 | CB-FE-ET-288MCFMCM-231 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-20 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109821 | CB-FE-ET-288MCFMCM-107 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105233 | CB-FE-ET-288MCFMCM-263 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-26 | 4 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105234 | CB-FE-ET-288MCFMCM-202 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-28 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105235 | CB-FE-ET-288MCFMCM-223 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 |  | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105237 | CB-FE-ET-288MCFMCM-261 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-27 | 1 | 2 | Partial
Fiber - Extender Trunk - OFNR - 288f | 23-105238 | CB-FE-ET-288MCFMCM-111 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105239 | CB-FE-ET-288MCFMCM-133 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-29 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105241 | CB-FE-ET-288MCFMCM-122 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-28 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105244 | CB-FE-ET-288MCFMCM-190 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-28 | 7 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105248 | CB-FE-ET-288MCFMCM-134 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-21 | 5 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105251 | CB-FE-ET-288MCFMCM-275 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-22 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105253 | CB-FE-ET-288MCFMCM-287 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-22 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105258 | CB-FE-ET-288MCFMCM-145 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-28 | 3 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105259 | CB-FE-ET-288MCFMCM-273 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-22 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105260 | CB-FE-ET-288MCFMCM-108 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105261 | CB-FE-ET-288MCFMCM-178 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 6 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105263 | CB-FE-ET-288MCFMCM-147 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-22 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105265 | CB-FE-ET-288MCFMCM-123 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-29 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105267 | CB-FE-ET-288MCFMCM-249 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-20 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105268 | CB-FE-ET-288MCFMCM-203 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105269 | CB-FE-ET-288MCFMCM-157 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 3 | 3 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105271 | CB-FE-ET-288MCFMCM-159 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-29 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105273 | CB-FE-ET-288MCFMCM-274 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-27 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105276 | CB-FE-ET-288MCFMCM-166 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-22 | 3 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105278 | CB-FE-ET-288MCFMCM-151 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-27 | 3 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105279 | CB-FE-ET-288MCFMCM-251 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-26 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105280 | CB-FE-ET-288MCFMCM-286 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-05-29 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-105281 | CB-FE-ET-288MCFMCM-120 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-27 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100650 | TAT-384-MM24PMM24R-A2E-010 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-07-10 | 23 |  | 0 | 18 | Past Due
Fiber - Extender Trunk - OFNR - 384f | 23-100696 | TAT-384-MM24PMM24R-A2E-008 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-29 | -19 |  | 0 | 18 | Past Due
Fiber - Extender Trunk - OFNR - 384f | 23-100797 | TAT-384-MM24PMM24R-A2E-040 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-29 | -19 |  | 0 | 18 | Past Due
Fiber - Extender Trunk - OFNR - 384f | 23-100696 | CB-FE-ET-384MCFMCM-008 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-21 | 8 | 8 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-100797 | CB-FE-ET-384MCFMCM-040 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-28 | 18 | 18 | Delivered
Fiber - Extender Trunk - OFNR - 384f | 23-105744 | CB-FE-ET-384MCFMCM-009 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-03 | -14 | 2026-05-29 | 28 | 28 | Delivered
Fiber - Fanout - OFNR - 4f | 23-109850 | TAF-5-MM5RSCU-A2M1-0006 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 4 | Past Due
Fiber - Fanout - OFNR - 4f | 23-109851 | TAF-5-MM5RSCU-A2M1-0007 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 4 | Past Due
Fiber - Fanout - OFNR - 4f | 23-109850 | CB-FE-HH-24MCF5SCU-006 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 |  | 0 | 4 | Past Due
Fiber - Fanout - OFNR - 4f | 23-109851 | CB-FE-HH-24MCF5SCU-007 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 |  | 0 | 4 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104000 | CB-FE-PT-FR-384MCMB-125 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 |  | 0 | 4 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104003 | CB-FE-PT-FR-384MCMB-130 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 |  | 0 | 5 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104008 | CB-FE-PT-FR-384MCMB-180 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 |  | 0 | 6 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104011 | CB-FE-PT-FR-384MCMB-105 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 |  | 0 | 4 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104014 | CB-FE-PT-FR-384MCMB-150 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104016 | CB-FE-PT-FR-384MCMB-200 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104020 | CB-FE-PT-FR-384MCMB-075 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104026 | CB-FE-PT-FR-384MCMB-135 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104036 | CB-FE-PT-FR-384MCMB-205 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 5 | 5 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104041 | CB-FE-PT-FR-384MCMB-165 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 5 | 5 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104057 | CB-FE-PT-FR-384MCMB-230 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 3 | 3 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104065 | CB-FE-PT-FR-384MCMB-185 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104069 | CB-FE-PT-FR-384MCMB-140 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 6 | 6 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104074 | CB-FE-PT-FR-384MCMB-215 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 3 | 3 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104076 | CB-FE-PT-FR-384MCMB-155 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 6 | 6 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104077 | CB-FE-PT-FR-384MCMB-115 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 2 | 6 | Partial
Fiber - Pigtail - OFNR - 384f | 23-104081 | CB-FE-PT-FR-384MCMB-120 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 4 | 4 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104083 | CB-FE-PT-FR-384MCMB-160 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104084 | CB-FE-PT-FR-384MCMB-090 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 4 | 4 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104086 | CB-FE-PT-FR-384MCMB-240 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104087 | CB-FE-PT-FR-384MCMB-170 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104093 | CB-FE-PT-FR-384MCMB-190 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 5 | 5 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104096 | CB-FE-PT-FR-384MCMB-175 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 1 | 3 | Partial
Fiber - Pigtail - OFNR - 384f | 23-104097 | CB-FE-PT-FR-384MCMB-310 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Pigtail - OFNP - 384f | 23-104021 | CB-FE-PT-FR-384MCMB-055 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Pigtail - OFNP - 384f | 23-104024 | CB-FE-PT-FR-384MCMB-220 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Pigtail - OFNP - 384f | 23-104033 | CB-FE-PT-FR-384MCMB-065 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 2 | 2 | Delivered
Fiber - Pigtail - OFNP - 384f | 23-104037 | CB-FE-PT-FR-384MCMB-210 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 1 | 1 | Delivered
Fiber - Pigtail - OFNP - 384f | 23-104042 | CB-FE-PT-FR-384MCMB-100 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 4 | 4 | Delivered
Fiber - Pigtail - OFNP - 384f | 23-104049 | CB-FE-PT-FR-384MCMB-145 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 | 2026-05-21 | 4 | 4 | Delivered
Fiber - Pigtail - OFNP - 384f | 23-104095 | CB-FE-PT-FR-384MCMB-195 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 |  | 0 | 1 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-102777 | TA-2-ULCUULCU-SMPY25B-040 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 |  | 0 | 960 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-102780 | CB-FB-SM2LCU039 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-22 | 720 | 720 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103409 | TA-24-MM24PMM24R-A2E-005 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 16 | 16 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103415 | TA-24-MM24PMM24R-A2E-007 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 128 | 128 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-103428 | TA-24-MM24PMM24R-A2E-010 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 144 | 144 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005700 | CB-FB-SM2LCU009 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 320 | 320 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005701 | CB-FB-SM2LCU010 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 960 | 960 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005702 | CB-FB-SM2LCU011 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 1280 | 1280 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005704 | CB-FB-SM2LCU013 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 480 | 480 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005705 | CB-FB-SM2LCU014 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 480 | 480 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005706 | CB-FB-SM2LCU015 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 320 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005706 | CB-FB-SM2LCU015 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 320 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005707 | CB-FB-SM2LCU016 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 400 | 400 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005708 | CB-FB-SM2LCU017 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 600 | 600 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005709 | CB-FB-SM2LCU018 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 600 | 600 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005711 | CB-FB-SM2LCU020 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 840 | 1120 | Partial
Fiber - Patch Cord - OFNR - 2f | 23-005712 | CB-FB-SM2LCU021 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 840 | 840 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005713 | CB-FB-SM2LCU022 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 280 | 280 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005714 | CB-FB-SM2LCU023 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1200 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005714 | CB-FB-SM2LCU023 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1200 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005715 | CB-FB-SM2LCU024 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 1200 | 1200 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-005716 | CB-FB-SM2LCU025 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 800 | 800 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-006016 | CB-FB-SM2LCU028 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1200 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-006016 | CB-FB-SM2LCU028 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1200 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-006081 | CB-FB-SM2LCU030 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1600 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-006081 | CB-FB-SM2LCU030 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1600 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-006183 | CB-FB-SM2LCU026 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 400 | 400 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-008018 | CB-FB-SM2LCU027 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1600 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-008018 | CB-FB-SM2LCU027 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1600 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010700 | CB-FB-SM2LCU031 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-26 | 1200 | 1200 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-010701 | CB-FB-SM2LCU032 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 400 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010701 | CB-FB-SM2LCU032 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 400 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010702 | CB-FB-SM2LCU033 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 800 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010702 | CB-FB-SM2LCU033 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 800 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010703 | CB-FB-SM2LCU034 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1600 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010703 | CB-FB-SM2LCU034 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1600 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010704 | CB-FB-SM2LCU035 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-22 | 800 | 800 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-010705 | CB-FB-SM2LCU036 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-22 | 400 | 400 | Delivered
Fiber - Patch Cord - OFNR - 2f | 23-010706 | CB-FB-SM2LCU037 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1600 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010706 | CB-FB-SM2LCU037 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1600 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010707 | CB-FB-SM2LCU038 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1440 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010707 | CB-FB-SM2LCU038 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1440 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-102777 | CB-FB-SM2LCU040 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-22 | 960 | 960 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105550 | TA-1-LCUSCA-SMRY25-021 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-04 | 79 |  | 0 | 192 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105551 | TA-1-LCUSCA-SMRY25-023 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-04 | 79 |  | 0 | 244 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105552 | TA-1-LCUSCA-SMRY25-039 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 256 | 256 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105553 | TA-1-LCUSCA-SMRY25-033 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 192 | 192 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105554 | TA-1-LCUSCA-SMRY25-049 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105555 | TA-1-LCUSCA-SMRY25-050 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105556 | TA-1-LCUSCA-SMRY25-005 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-25 | 100 |  | 0 | 56 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105557 | TA-1-LCUSCA-SMRY25-007 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-04 | 79 |  | 0 | 168 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105558 | TA-1-LCUSCA-SMRY25-020 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-04 | 79 |  | 0 | 244 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105559 | TA-1-LCUSCA-SMRY25-014 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-04 | 79 |  | 0 | 180 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-109824 | TA-1-LCUSCA-SMRY25-051 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109825 | TA-1-LCUSCA-SMRY25-057 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109826 | TA-1-LCUSCA-SMRY25-069 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 |  | 0 | 20 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-109828 | TA-1-LCUSCA-SMRY25-062 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109829 | TA-1-LCUSCA-SMRY25-061 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109830 | TA-1-LCUSCA-SMRY25-073 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 |  | 0 | 16 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-109832 | TA-1-LCUSCA-SMRY25-066 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109833 | TA-1-LCUSCA-SMRY25-059 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109835 | TA-1-LCUSCA-SMRY25-068 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109836 | TA-1-LCUSCA-SMRY25-064 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109837 | TA-1-LCUSCA-SMRY25-055 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109838 | TA-1-LCUSCA-SMRY25-056 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109839 | TA-1-LCUSCA-SMRY25-058 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109841 | TA-1-LCUSCA-SMRY25-067 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109842 | TA-1-LCUSCA-SMRY25-052 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109843 | TA-1-LCUSCA-SMRY25-053 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109844 | TA-1-LCUSCA-SMRY25-065 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109845 | TA-1-LCUSCA-SMRY25-054 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109846 | TA-1-LCUSCA-SMRY25-063 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109847 | TA-1-LCUSCA-SMRY25-060 | 70001631914 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105511 | TA-1-LCUSCA-SMRY25-016 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 160 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105512 | TA-1-LCUSCA-SMRY25-035 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 216 | 216 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105513 | TA-1-LCUSCA-SMRY25-031 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 208 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105514 | TA-1-LCUSCA-SMRY25-045 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105515 | TA-1-LCUSCA-SMRY25-043 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105517 | TA-1-LCUSCA-SMRY25-042 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105518 | TA-1-LCUSCA-SMRY25-008 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-04 | 79 |  | 0 | 96 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105519 | TA-1-LCUSCA-SMRY25-048 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105520 | TA-1-LCUSCA-SMRY25-046 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105521 | TA-1-LCUSCA-SMRY25-025 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 208 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105522 | TA-1-LCUSCA-SMRY25-018 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 176 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105523 | TA-1-LCUSCA-SMRY25-047 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105525 | TA-1-LCUSCA-SMRY25-030 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 264 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105526 | TA-1-LCUSCA-SMRY25-028 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 156 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105527 | TA-1-LCUSCA-SMRY25-009 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-04 | 79 |  | 0 | 164 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105529 | TA-1-LCUSCA-SMRY25-041 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 116 | 116 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105530 | TA-1-LCUSCA-SMRY25-017 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 244 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105531 | TA-1-LCUSCA-SMRY25-032 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 212 | 212 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105532 | TA-1-LCUSCA-SMRY25-037 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 236 | 236 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105533 | TA-1-LCUSCA-SMRY25-022 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 212 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105534 | TA-1-LCUSCA-SMRY25-040 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 108 | 108 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105535 | TA-1-LCUSCA-SMRY25-011 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 144 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105536 | TA-1-LCUSCA-SMRY25-029 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 176 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105537 | TA-1-LCUSCA-SMRY25-044 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105538 | TA-1-LCUSCA-SMRY25-026 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 212 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105539 | TA-1-LCUSCA-SMRY25-010 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-04 | 79 |  | 0 | 104 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105540 | TA-1-LCUSCA-SMRY25-015 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 212 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105541 | TA-1-LCUSCA-SMRY25-038 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 144 | 144 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105542 | TA-1-LCUSCA-SMRY25-027 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 244 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105543 | TA-1-LCUSCA-SMRY25-012 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 216 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105544 | TA-1-LCUSCA-SMRY25-024 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 176 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105545 | TA-1-LCUSCA-SMRY25-006 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-04 | 79 |  | 0 | 140 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105546 | TA-1-LCUSCA-SMRY25-019 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 192 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105547 | TA-1-LCUSCA-SMRY25-034 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 248 | 248 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105548 | TA-1-LCUSCA-SMRY25-036 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-22 | -26 | 2026-05-18 | 232 | 232 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105549 | TA-1-LCUSCA-SMRY25-013 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-09-18 | 93 |  | 0 | 248 | Past Due
Fiber - Patch Cord - OFNR - 1f | 23-105535 | CB-FB-1SCALCU011 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 528 | 144 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105536 | CB-FB-1SCALCU029 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 432 | 180 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105538 | CB-FB-1SCALCU026 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 720 | 196 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105539 | CB-FB-1SCALCU010 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 432 | 72 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105540 | CB-FB-1SCALCU015 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 528 | 200 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105541 | CB-FB-1SCALCU038 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 432 | 148 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105542 | CB-FB-1SCALCU027 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 576 | 212 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105543 | CB-FB-1SCALCU012 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 720 | 236 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105544 | CB-FB-1SCALCU024 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 576 | 176 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105545 | CB-FB-1SCALCU006 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 48 | 156 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105546 | CB-FB-1SCALCU019 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 576 | 160 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105547 | CB-FB-1SCALCU034 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 528 | 160 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105548 | CB-FB-1SCALCU036 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 912 | 232 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105549 | CB-FB-1SCALCU013 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 768 | 236 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105550 | CB-FB-1SCALCU021 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 528 | 160 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105551 | CB-FB-1SCALCU023 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 576 | 212 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105552 | CB-FB-1SCALCU039 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 336 | 272 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105553 | CB-FB-1SCALCU033 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 576 | 212 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105557 | CB-FB-1SCALCU007 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 336 | 144 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105558 | CB-FB-1SCALCU020 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 576 | 176 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105559 | CB-FB-1SCALCU014 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 624 | 248 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105511 | CB-FB-1SCALCU016 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-06-12 | 576 | 176 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105512 | CB-FB-1SCALCU035 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 384 | 160 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105513 | CB-FB-1SCALCU031 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 432 | 176 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105514 | CB-FB-1SCALCU045 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-16 | -32 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105515 | CB-FB-1SCALCU043 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-16 | -32 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105517 | CB-FB-1SCALCU042 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-16 | -32 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105518 | CB-FB-1SCALCU008 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 96 | 108 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105519 | CB-FB-1SCALCU048 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-16 | -32 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105520 | CB-FB-1SCALCU046 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-16 | -32 | 2026-05-18 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105521 | CB-FB-1SCALCU025 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 432 | 160 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105522 | CB-FB-1SCALCU018 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 528 | 212 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105523 | CB-FB-1SCALCU047 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-16 | -32 | 2026-05-18 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105525 | CB-FB-1SCALCU030 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 720 | 196 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105526 | CB-FB-1SCALCU028 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 576 | 156 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105527 | CB-FB-1SCALCU009 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 624 | 92 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105529 | CB-FB-1SCALCU041 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-05-18 | 100 | 100 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105530 | CB-FB-1SCALCU017 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 624 | 196 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105531 | CB-FB-1SCALCU032 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 720 | 196 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105532 | CB-FB-1SCALCU037 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 288 | 216 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105533 | CB-FB-1SCALCU022 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 624 | 196 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105534 | CB-FB-1SCALCU040 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 | 2026-06-12 | 192 | 204 | Partial
Fiber - Patch Cord - OFNR - 1f | 23-105537 | CB-FB-1SCALCU044 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105554 | CB-FB-1SCALCU049 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-105555 | CB-FB-1SCALCU050 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109824 | CB-FB-1SCALCU051 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109825 | CB-FB-1SCALCU057 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109828 | CB-FB-1SCALCU062 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109829 | CB-FB-1SCALCU061 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109832 | CB-FB-1SCALCU066 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109833 | CB-FB-1SCALCU059 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109836 | CB-FB-1SCALCU064 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109837 | CB-FB-1SCALCU055 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109838 | CB-FB-1SCALCU056 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109839 | CB-FB-1SCALCU058 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109841 | CB-FB-1SCALCU067 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 80 | 80 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109842 | CB-FB-1SCALCU052 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109843 | CB-FB-1SCALCU053 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109844 | CB-FB-1SCALCU065 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109845 | CB-FB-1SCALCU054 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 20 | 20 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109846 | CB-FB-1SCALCU063 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 40 | 40 | Delivered
Fiber - Patch Cord - OFNR - 1f | 23-109847 | CB-FB-1SCALCU060 | 70001631919 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-13 | 20 | 20 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109696 | CB-FE-ET-288MCFMCM-262 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-04 | -13 | 2026-05-19 | 1 | 1 | Delivered
Fiber - Extender Trunk - OFNR - 288f | 23-109768 | CB-FE-ET-288MCFMCM-289 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-06-04 | -13 | 2026-05-20 | 2 | 1 | Delivered
Fiber - Pigtail - OFNR - 384f | 23-104004 | CB-FE-PT-FR-384MCMB-110 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 |  | 0 | 1 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104005 | CB-FE-PT-FR-384MCMB-095 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 |  | 0 | 2 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104006 | CB-FE-PT-FR-384MCMB-080 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 |  | 0 | 3 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104014 | CB-FE-PT-FR-384MCMB-150 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-14 | -34 |  | 0 | 5 | Past Due
Fiber - Trunk - OFNR - 96f | 23-110463 | CB-FE-HT-096MCM-271 | 70001631927 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 1 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-103409 | CB-FE-ET-024MCFMCM-005 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-21 | -27 |  | 0 | 288 | Past Due
Fiber - Trunk - OFNR - 96f | 23-104932 | CB-FE-HT-096MCM-118 | 70001645572 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 | 2026-05-08 | 1 | 1 | Delivered
| 23-109783 | TAT-288-MM24PMM24R-A2E-164 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 2 | Past Due
| 23-109784 | TAT-288-MM24PMM24R-A2E-142 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-03 | -14 |  | 0 | 1 | Past Due
TAT-288-MM24PMM24R-A2E-079 | 23-109785 | TAT-288-MM24PMM24R-A2E-079 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-03 | -14 | 2026-06-09 | 3 | 3 | Delivered
Fiber - Patch Cord - OFNR | 23-102780 | TA-2-ULCUULCU-SMPY25B-039 | 70001631918 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-06-12 | -5 | 2026-06-12 | 720 | 720 | Delivered
| 23-109691 | TAT-384-MM24PMM24R-A2E-039 | 70001631920 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2026-05-29 | -19 |  | 0 | 18 | Past Due
| 23-109691 | CB-FE-ET-384MCFMCM-039 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 |  |  |  | 0 | 18 | Past Due
| 23-109783 | CB-FE-ET-288MCFMCM-164 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 |  |  |  | 0 | 3 | Past Due
| 23-109785 | CB-FE-ET-288MCFMCM-079 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 |  |  |  | 0 | 1 | Past Due
| 23-109786 | CB-FE-ET-288MCFMCM-232 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 |  |  |  | 0 | 1 | Past Due
| 23-109787 | CB-FE-ET-288MCFMCM-180 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 |  |  |  | 0 | 1 | Past Due
Fiber - Extender Trunk - OFNR - 288f | 23-109788 | CB-FE-ET-288MCFMCM-276 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 | 2026-06-02 | 2 | 2 | Delivered
Fiber - Extender Trunk - OFNR | 23-109800 | CB-FE-ET-288MCFMCM-233 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-28 | -20 |  | 0 | 2 | Past Due
Hardware - OPE | 23-107481 | FC-10IN-47RUFAP-SET | 70001645571 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-18 | 2027-09-25 | 465 | 2026-06-15 | 100 | 432 | Partial
Fiber - Pigtail - OFNR - 384f | 23-104000 | CB-FE-PT-FR-384MCMB-125 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 4 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104003 | CB-FE-PT-FR-384MCMB-130 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 4 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104005 | CB-FE-PT-FR-384MCMB-095 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 2 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104008 | CB-FE-PT-FR-384MCMB-180 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 2 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104011 | CB-FE-PT-FR-384MCMB-105 | 70001631923 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 4 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104016 | CB-FE-PT-FR-384MCMB-200 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 1 | 1 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104026 | CB-FE-PT-FR-384MCMB-135 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 1 | 1 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104041 | CB-FE-PT-FR-384MCMB-165 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 4 | 4 | Past Due
Fiber - Pigtail - OFNP - 384f | 23-104049 | CB-FE-PT-FR-384MCMB-145 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 1 | 1 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104069 | CB-FE-PT-FR-384MCMB-140 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 6 | 6 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104074 | CB-FE-PT-FR-384MCMB-215 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 1 | 1 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104076 | CB-FE-PT-FR-384MCMB-155 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 3 | 3 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104077 | CB-FE-PT-FR-384MCMB-115 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 6 | 6 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104081 | CB-FE-PT-FR-384MCMB-120 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 1 | 1 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104083 | CB-FE-PT-FR-384MCMB-160 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 2 | 2 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104093 | CB-FE-PT-FR-384MCMB-190 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 4 | 4 | Past Due
Fiber - Pigtail - OFNR - 384f | 23-104096 | CB-FE-PT-FR-384MCMB-175 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 3 | 3 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005700 | CB-FB-SM2LCU009 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 320 | 320 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005701 | CB-FB-SM2LCU010 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 960 | 960 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005702 | CB-FB-SM2LCU011 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 1280 | 1280 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005704 | CB-FB-SM2LCU013 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 480 | 480 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005705 | CB-FB-SM2LCU014 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 480 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005707 | CB-FB-SM2LCU016 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 600 | 400 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005708 | CB-FB-SM2LCU017 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 600 | 600 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005709 | CB-FB-SM2LCU018 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 1120 | 600 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005711 | CB-FB-SM2LCU020 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1120 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005712 | CB-FB-SM2LCU021 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 280 | 840 | Partial
Fiber - Patch Cord - OFNR - 2f | 23-005713 | CB-FB-SM2LCU022 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 0 | 280 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005715 | CB-FB-SM2LCU024 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 1200 | 1200 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005716 | CB-FB-SM2LCU025 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 800 | 800 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-006183 | CB-FB-SM2LCU026 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-05-18 | -30 |  | 400 | 400 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010700 | CB-FB-SM2LCU031 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 1200 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010704 | CB-FB-SM2LCU035 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 800 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-010705 | CB-FB-SM2LCU036 | 70001631925 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-18 | 2026-11-06 | 142 |  | 0 | 400 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109184 | CB-ZZ-HT-3456MCM-272 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-26 | 2026-06-24 | 7 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109192 | CB-ZZ-HT-3456MCM-452 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-26 | 2026-07-02 | 15 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109216 | CB-ZZ-HT-3456MCM-484 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-26 | 2026-07-02 | 15 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109220 | CB-ZZ-HT-3456MCM-268 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-26 | 2026-06-25 | 8 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109221 | CB-ZZ-HT-3456MCM-440 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-26 | 2026-07-02 | 15 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109222 | CB-ZZ-HT-3456MCM-472 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-26 | 2026-07-02 | 15 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109259 | CB-ZZ-HT-3456MCM-280 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-26 | 2026-06-24 | 7 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109276 | CB-ZZ-HT-3456MCM-300 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-26 | 2026-07-02 | 15 |  | 0 | 2 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109285 | CB-ZZ-PT-3456MCMA-2250 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-05-26 | 2026-06-24 | 7 |  | 0 | 4 | Past Due
Hardware - FAP | 23-101177 | MC-1RU-FAPB-4P-MMC-01 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-06-11 | -6 | 2026-05-22 | 136 | 136 | Delivered
Hardware - FAP | 23-101177 | MC-1RU-FAPB-4P-MMC-01 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-06-11 | -6 | 2026-05-22 | 136 | 136 | Delivered
Hardware - OSE | 23-100899 | SC-MJB-FBC-288ST-KIT-01 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-06-29 | 12 |  | 0 | 18 | Past Due
Hardware - OSE | 23-100899 | SC-MJB-FBC-288ST-KIT-01 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-06-29 | 12 |  | 0 | 18 | Past Due
Hardware - OSE | 23-100899 | SC-MJB-FBC-288ST-KIT-01 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-06-29 | 12 |  | 0 | 18 | Past Due
Hardware - OSE | 23-100899 | SC-MJB-FBC-288ST-KIT-01 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-06-29 | 12 |  | 0 | 18 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109184 | TAT-3456-MM24PMM24P-A2J-272 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-07-24 | 37 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109184 | TAT-3456-MM24PMM24P-A2J-272 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-07-24 | 37 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109185 | TAT-3456-MM24PMM24P-A2J-248 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-07-24 | 37 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109185 | TAT-3456-MM24PMM24P-A2J-248 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-07-24 | 37 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109187 | TAT-3456-MM24PMM24P-A2J-320 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-07-24 | 37 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109190 | TAT-3456-MM24PMM24P-A2J-536 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109191 | TAT-3456-MM24PMM24P-A2J-316 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109191 | TAT-3456-MM24PMM24P-A2J-316 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109195 | TAT-3456-MM24PMM24P-A2J-504 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109197 | TAT-3456-MM24PMM24P-A2J-264 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109197 | TAT-3456-MM24PMM24P-A2J-264 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109199 | TAT-3456-MM24PMM24P-A2J-436 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109205 | TAT-3456-MM24PMM24P-A2J-404 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109207 | TAT-3456-MM24PMM24P-A2J-324 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109207 | TAT-3456-MM24PMM24P-A2J-324 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109208 | TAT-3456-MM24PMM24P-A2J-296 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109210 | TAT-3456-MM24PMM24P-A2J-480 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109210 | TAT-3456-MM24PMM24P-A2J-480 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109213 | TAT-3456-MM24PMM24P-A2J-512 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109213 | TAT-3456-MM24PMM24P-A2J-512 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109216 | TAT-3456-MM24PMM24P-A2J-484 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109217 | TAT-3456-MM24PMM24P-A2J-408 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109220 | TAT-3456-MM24PMM24P-A2J-268 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109223 | TAT-3456-MM24PMM24P-A2J-332 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109226 | TAT-3456-MM24PMM24P-A2J-292 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109226 | TAT-3456-MM24PMM24P-A2J-292 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109227 | TAT-3456-MM24PMM24P-A2J-456 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109227 | TAT-3456-MM24PMM24P-A2J-456 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109231 | TAT-3456-MM24PMM24P-A2J-208 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109232 | TAT-3456-MM24PMM24P-A2J-508 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109233 | TAT-3456-MM24PMM24P-A2J-216 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109234 | TAT-3456-MM24PMM24P-A2J-304 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109237 | TAT-3456-MM24PMM24P-A2J-420 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109238 | TAT-3456-MM24PMM24P-A2J-340 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109239 | TAT-3456-MM24PMM24P-A2J-232 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109245 | TAT-3456-MM24PMM24P-A2J-388 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109248 | TAT-3456-MM24PMM24P-A2J-460 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109250 | TAT-3456-MM24PMM24P-A2J-276 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109252 | TAT-3456-MM24PMM24P-A2J-308 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109252 | TAT-3456-MM24PMM24P-A2J-308 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109254 | TAT-3456-MM24PMM24P-A2J-560 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109257 | TAT-3456-MM24PMM24P-A2J-284 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109259 | TAT-3456-MM24PMM24P-A2J-280 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109261 | TAT-3456-MM24PMM24P-A2J-448 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109262 | TAT-3456-MM24PMM24P-A2J-252 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109263 | TAT-3456-MM24PMM24P-A2J-312 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109267 | TAT-3456-MM24PMM24P-A2J-424 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109268 | TAT-3456-MM24PMM24P-A2J-432 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109268 | TAT-3456-MM24PMM24P-A2J-432 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109272 | TAT-3456-MM24PMM24P-A2J-260 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109275 | TAT-3456-MM24PMM24P-A2J-256 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109278 | TAT-3456-MM24PMM24P-A2J-492 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109279 | TAT-3456-MM24PMM24P-A2J-464 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109280 | TAT-3456-MM24PMM24P-A2J-444 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109283 | TAT-3456-MM24PMM24P-A2J-348 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109290 | TA-3456-MM24P0-SMROIM-3350 | 70001665070 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2027-03-26 | 282 |  | 0 | 9 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109290 | TA-3456-MM24P0-SMROIM-3350 | 70001665070 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2027-12-31 | 562 |  | 0 | 5 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109290 | TA-3456-MM24P0-SMROIM-3350 | 70001665070 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2027-12-31 | 562 |  | 0 | 4 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109290 | TA-3456-MM24P0-SMROIM-3350 | 70001665070 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2027-12-31 | 562 |  | 0 | 3 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109290 | TA-3456-MM24P0-SMROIM-3350 | 70001665070 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2027-12-31 | 562 |  | 0 | 13 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109286 | TA-3456-MM24P0-SMROIM-3000 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2027-01-22 | 219 |  | 0 | 14 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109286 | TA-3456-MM24P0-SMROIM-3000 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2027-01-22 | 219 |  | 0 | 4 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109286 | TA-3456-MM24P0-SMROIM-3000 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2027-01-22 | 219 |  | 0 | 16 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | TA-3456-MM24P0-SMROIM-2600 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 9 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | TA-3456-MM24P0-SMROIM-2600 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 7 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | TA-3456-MM24P0-SMROIM-2600 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 2 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | TA-3456-MM24P0-SMROIM-2300 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | TA-3456-MM24P0-SMROIM-2300 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 16 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | TA-3456-MM24P0-SMROIM-2300 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 1 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | TA-3456-MM24P0-SMROIM-2300 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2027-01-22 | 219 |  | 0 | 13 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | TA-3456-MM24P0-SMROIM-2300 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2027-01-22 | 219 |  | 0 | 3 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109315 | TA-3456-MM24P0-SMROIM-2650 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 1999-12-31 | -9665 |  | 0 | 4 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109315 | TA-3456-MM24P0-SMROIM-2650 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2027-01-22 | 219 |  | 0 | 12 | Past Due
Hardware - FAP | 23-101177 | MC-1RU-FAPB-4P-MMC-01 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-06-11 | -6 |  | 136 | 136 | Past Due
Hardware - FAP | 23-101177 | MC-1RU-FAPB-4P-MMC-01 | 70001665071 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-05-27 | 2026-07-17 | 30 |  | 136 | 136 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109186 | CB-ZZ-HT-3456MCM-396 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-02 | 2026-07-10 | 23 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109205 | CB-ZZ-HT-3456MCM-404 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-02 | 2026-07-16 | 29 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109206 | CB-ZZ-HT-3456MCM-224 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-02 | 2026-07-10 | 23 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109239 | CB-ZZ-HT-3456MCM-232 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-02 | 2026-07-10 | 23 |  | 0 | 2 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109285 | CB-ZZ-PT-3456MCMA-2250 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-02 | 2026-07-09 | 22 |  | 0 | 10 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-02 | 2026-07-09 | 22 |  | 0 | 1 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109308 | CB-ZZ-PT-3456MCMA-2200 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-02 | 2026-06-23 | 6 |  | 0 | 3 | Past Due
Hardware - FAP | 23-101177 | FP-F-01RU128MCA | 70001631929 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-03 |  |  |  | 0 | 1728 | Past Due
Fiber - Blunt - OSP - 192f | 23-014491 | GCYFY-192B6a1 | 70001678965 | RPL7 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-06-07 | 2026-07-15 | 28 |  | 0 | 5000 | Past Due
Fiber - Blunt - OSP - 192f | 23-014491 | GCYFY-192B6a1 | 70001678965 | RPL7 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-06-07 | 2026-07-15 | 28 |  | 0 | 5000 | Past Due
Fiber - Blunt - OSP - 192f | 23-014491 | GCYFY-192B6a1 | 70001678965 | RPL7 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-06-07 | 2026-07-15 | 28 |  | 0 | 4000 | Past Due
Fiber - Blunt - OSP - 192f | 23-014491 | GCYFY-192B6a1 | 70001678965 | RPL7 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-06-07 | 2026-07-15 | 28 |  | 0 | 5000 | Past Due
Fiber - Blunt - OSP - 192f | 23-014491 | GCYFY-192B6a1 | 70001678965 | RPL7 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-06-07 | 2026-07-15 | 28 |  | 0 | 4500 | Past Due
Fiber - Blunt - OSP - 864f | 23-103287 | GCYDXY(AB-ASR)-12F-864B6A2 200Î¼m | 70001678965 | RPL7 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-06-07 | 2026-07-15 | 28 |  | 0 | 8500 | Past Due
Fiber - Blunt - OSP - 864f | 23-103287 | GCYDXY(AB-ASR)-12F-864B6A2 200Î¼m | 70001678965 | RPL7 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-06-07 | 2026-07-15 | 28 |  | 0 | 2200 | Past Due
Fiber - Blunt - OSP | 23-107025 | GCYFC-048B6al 200um | 70001678965 | RPL7 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-06-07 | 2026-07-15 | 28 |  | 0 | 5400 | Past Due
Fiber - Blunt - OSP | 23-103287 | GCYDXY(AB-ASR)-12F-864B6A2 200Î¼m | 70001678965 | RPL7 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-06-07 | 2026-07-15 | 28 |  | 0 | 2200 | Past Due
Fiber - Blunt - OSP | 23-103287 | GCYDXY(AB-ASR)-12F-864B6A2 200Î¼m | 70001678965 | RPL7 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-06-07 | 2026-07-15 | 28 |  | 0 | 2200 | Past Due
Fiber - Blunt - OSP | 23-107025 | GCYFC-048B6al 200um | 70001678965 | RPL7 | YANGTZE OPTICAL FIBRE AND CABLE JOINT STOCK LIMITED COMPANY | 2026-06-07 | 2026-07-15 | 28 |  | 0 | 2500 | Past Due
Hardware - FAP | 23-101177 | FP-F-01RU128MCA | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-09 | 2026-06-09 | -8 | 2026-06-01 | 136 | 136 | Delivered
Hardware - OSE | 23-100899 | FB-FC-OSEUHDKIT-FAB | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-09 | 2026-06-09 | -8 | 2026-06-12 | 36 | 18 | Delivered
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109200 | CB-ZZ-HT-3456MCM-240 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-09 | 2026-07-16 | 29 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109205 | CB-ZZ-HT-3456MCM-404 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-09 | 2026-07-16 | 29 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109206 | CB-ZZ-HT-3456MCM-224 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-09 | 2026-07-16 | 29 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109239 | CB-ZZ-HT-3456MCM-232 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-09 | 2026-07-16 | 29 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109251 | CB-ZZ-HT-3456MCM-412 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-09 | 2026-07-16 | 29 |  | 0 | 2 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109287 | CB-ZZ-PT-3456MCMA-2550 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-09 | 2026-07-15 | 28 |  | 0 | 11 | Past Due
Hardware - FAP | 23-101185 | FB-FC-1RU4X12LC | 70001678964 | RPL7 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-14 | 2026-06-15 | -2 | 2026-06-12 | 208 | 208 | Delivered
Hardware - OSE | 23-100899 | FB-FC-OSEUHDKIT-FAB | 70001678964 | RPL7 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-14 | 2026-06-15 | -2 | 2026-05-06 | 20 | 20 | Delivered
Hardware - OSE | 23-100900 | FB-FC-WSH96RIB-KIT | 70001678964 | RPL7 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-14 | 2026-06-15 | -2 | 2026-05-28 | 18 | 18 | Delivered
Fiber - Pigtail - OFNP - 192f | 23-013635 | CB-PT-192SMPLRS020 | 70001678964 | RPL7 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-14 | 2026-06-30 | 13 |  | 0 | 34 | Past Due
Fiber - Pigtail - OFNP - 192f | 23-013640 | CB-PT-192SMPLRS045 | 70001678964 | RPL7 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-14 | 2026-06-30 | 13 | 2026-06-01 | 42 | 42 | Delivered
Fiber - Pigtail - OFNP - 192f | 23-013641 | CB-PT-192SMPLRS050 | 70001678964 | RPL7 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-14 | 2026-06-30 | 13 |  | 0 | 14 | Past Due
Fiber - Pigtail - OFNP - 192f | 23-013642 | CB-PT-192SMPLRS055 | 70001678964 | RPL7 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-14 | 2026-06-22 | 5 | 2026-06-12 | 8 | 8 | Delivered
Fiber - Pigtail - OFNP | 23-013636 | CB-PT-192SMPLRS025 | 70001678964 | RPL7 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-14 | 2026-06-25 | 8 |  | 0 | 50 | Past Due
Fiber - Pigtail - OFNP | 23-013637 | CB-PT-192SMPLRS030 | 70001678964 | RPL7 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-14 | 2026-07-02 | 15 |  | 0 | 15 | Past Due
Fiber - Pigtail - OFNP | 23-013639 | CB-PT-192SMPLRS040 | 70001678964 | RPL7 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-14 | 2026-06-15 | -2 |  | 0 | 12 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005694 | CB-FB-SM2LCU003 | 70001783982 | RPL6 | ANIXTER INC | 2026-06-15 | 2026-08-14 | 58 |  | 0 | 48 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005697 | CB-FB-SM2LCU006 | 70001783982 | RPL6 | ANIXTER INC | 2026-06-15 | 2026-08-14 | 58 |  | 0 | 80 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005698 | CB-FB-SM2LCU007 | 70001783982 | RPL6 | ANIXTER INC | 2026-06-15 | 2026-08-14 | 58 |  | 0 | 307 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005699 | CB-FB-SM2LCU008 | 70001783982 | RPL6 | ANIXTER INC | 2026-06-15 | 2026-08-14 | 58 |  | 0 | 170 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005700 | CB-FB-SM2LCU009 | 70001783982 | RPL6 | ANIXTER INC | 2026-06-15 | 2026-08-14 | 58 |  | 0 | 329 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005701 | CB-FB-SM2LCU010 | 70001783982 | RPL6 | ANIXTER INC | 2026-06-15 | 2026-08-14 | 58 |  | 0 | 40 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005702 | CB-FB-SM2LCU011 | 70001783982 | RPL6 | ANIXTER INC | 2026-06-15 | 2026-08-14 | 58 |  | 0 | 93 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005703 | CB-FB-SM2LCU012 | 70001783982 | RPL6 | ANIXTER INC | 2026-06-15 | 2026-08-14 | 58 |  | 0 | 124 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005704 | CB-FB-SM2LCU013 | 70001783982 | RPL6 | ANIXTER INC | 2026-06-15 | 2026-08-14 | 58 |  | 0 | 180 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005705 | CB-FB-SM2LCU014 | 70001783982 | RPL6 | ANIXTER INC | 2026-06-15 | 2026-08-14 | 58 |  | 0 | 52 | Past Due
Fiber - Patch Cord - OFNR - 2f | 23-005707 | CB-FB-SM2LCU016 | 70001783982 | RPL6 | ANIXTER INC | 2026-06-15 | 2026-08-14 | 58 |  | 0 | 4 | Past Due
Hardware - FAP | 23-101177 | FP-F-01RU128MCA | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-16 | 2026-06-16 | -1 |  | 0 | 136 | Past Due
Hardware - OSE | 23-100899 | FB-FC-OSEUHDKIT-FAB | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-16 | 2026-06-23 | 6 |  | 0 | 18 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109222 | CB-ZZ-HT-3456MCM-472 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-16 | 2026-07-23 | 36 |  | 0 | 2 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109257 | CB-ZZ-HT-3456MCM-284 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-16 | 2026-07-23 | 36 |  | 0 | 1 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109276 | CB-ZZ-HT-3456MCM-300 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-16 | 2026-07-23 | 36 |  | 0 | 1 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109287 | CB-ZZ-PT-3456MCMA-2550 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-16 | 2026-07-22 | 35 |  | 0 | 7 | Past Due
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109307 | CB-ZZ-PT-3456MCMA-2950 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-16 | 2026-07-29 | 42 |  | 0 | 9 | Past Due
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109241 | CB-ZZ-HT-3456MCM-228 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-22 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112097 | CB-ZZ-HT-3456MCM-245 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-22 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112130 | CB-ZZ-HT-3456MCM-271 | 70001776878 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-22 |  |  |  | 0 | 1 | Upcoming
Hardware - FAP | 23-101177 | FP-F-01RU128MCA | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-23 | 2026-06-26 | 9 |  | 0 | 136 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109191 | CB-ZZ-HT-3456MCM-316 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-23 | 2026-07-30 | 43 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109195 | CB-ZZ-HT-3456MCM-504 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-23 | 2026-07-30 | 43 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109223 | CB-ZZ-HT-3456MCM-332 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-23 | 2026-07-30 | 43 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109242 | CB-ZZ-HT-3456MCM-496 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-23 | 2026-07-30 | 43 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109258 | CB-ZZ-HT-3456MCM-488 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-23 | 2026-07-30 | 43 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109276 | CB-ZZ-HT-3456MCM-300 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-23 | 2026-07-23 | 36 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109278 | CB-ZZ-HT-3456MCM-492 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-23 | 2026-07-30 | 43 |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109307 | CB-ZZ-PT-3456MCMA-2950 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-23 | 2026-08-05 | 49 |  | 0 | 9 | Upcoming
Hardware - OSE | 23-100899 | FB-FC-OSEUHDKIT-FAB | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-23 | 2026-06-23 | 6 |  | 0 | 18 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109185 | CB-ZZ-HT-3456MCM-248 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-30 | 2026-08-06 | 50 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109206 | CB-ZZ-HT-3456MCM-224 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-30 | 2026-08-06 | 50 |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109316 | CB-ZZ-PT-3456MCMA-3300 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-30 | 2026-08-26 | 70 |  | 0 | 18 | Upcoming
Hardware - OSE | 23-100899 | FB-FC-OSEUHDKIT-FAB | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-30 | 2026-06-30 | 13 |  | 0 | 18 | Upcoming
Hardware - FAP | 23-101177 | FP-F-01RU128MCA | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-06-30 | 2026-06-30 | 13 |  | 0 | 136 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-01 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-01 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-01 |  |  |  | 0 | 6 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109186 | CB-ZZ-HT-3456MCM-396 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-08-13 | 57 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109194 | CB-ZZ-HT-3456MCM-516 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-08-13 | 57 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109206 | CB-ZZ-HT-3456MCM-224 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-08-06 | 50 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109211 | CB-ZZ-HT-3456MCM-520 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-08-13 | 57 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109219 | CB-ZZ-HT-3456MCM-468 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-08-13 | 57 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109230 | CB-ZZ-HT-3456MCM-392 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-08-06 | 50 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109237 | CB-ZZ-HT-3456MCM-420 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-08-13 | 57 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109278 | CB-ZZ-HT-3456MCM-492 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-08-13 | 57 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109280 | CB-ZZ-HT-3456MCM-444 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-08-13 | 57 |  | 0 | 2 | Upcoming
Fiber - Fanout - OFNR - 8f | 23-101167 | CB-FE-HH-08MCF4LC-XDA | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-03 | 16 |  | 0 | 1038 | Upcoming
Fiber - Fanout - OFNR - 24f | 23-101499 | CB-FE-HH-24MCF12LC-FUD | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-03 | 16 |  | 0 | 1228 | Upcoming
Fiber - Fanout - OFNR - 24f | 23-103208 | CB-BE-HH-24MCF3MTP-RDSD | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-03 | 16 |  | 0 | 128 | Upcoming
Fiber - Fanout - OFNR - 4f | 23-110898 | CB-FE-HH-24MCF5SCU-011 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-10 | 23 |  | 0 | 96 | Upcoming
Fiber - Fanout - OFNR - 4f | 23-110899 | CB-FE-HH-24MCF5SCU-012 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-10 | 23 |  | 0 | 96 | Upcoming
Fiber - Fanout - OFNR - 4f | 23-110900 | CB-FE-HH-24MCF5SCU-017 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-10 | 23 |  | 0 | 96 | Upcoming
Fiber - Fanout - OFNR - 4f | 23-110901 | CB-FE-HH-24MCF5SCU-019 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-10 | 23 |  | 0 | 96 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109308 | CB-ZZ-PT-3456MCMA-2200 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-09-02 | 77 |  | 0 | 7 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005695 | CB-FB-SM2LCU004 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-14 | 27 |  | 0 | 16 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005699 | CB-FB-SM2LCU008 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-14 | 27 |  | 0 | 1152 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005700 | CB-FB-SM2LCU009 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 2018 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005701 | CB-FB-SM2LCU010 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 1442 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005702 | CB-FB-SM2LCU011 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 1538 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005703 | CB-FB-SM2LCU012 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 6914 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005704 | CB-FB-SM2LCU013 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 10193 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005705 | CB-FB-SM2LCU014 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 5760 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005706 | CB-FB-SM2LCU015 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-14 | 27 |  | 0 | 15618 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005707 | CB-FB-SM2LCU016 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 13706 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005708 | CB-FB-SM2LCU017 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 14272 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005709 | CB-FB-SM2LCU018 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 11777 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005710 | CB-FB-SM2LCU019 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 14984 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005711 | CB-FB-SM2LCU020 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 14582 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005712 | CB-FB-SM2LCU021 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 14146 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005713 | CB-FB-SM2LCU022 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 16240 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005714 | CB-FB-SM2LCU023 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-14 | 27 |  | 0 | 18512 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005715 | CB-FB-SM2LCU024 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 9632 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-005716 | CB-FB-SM2LCU025 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 15928 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-006016 | CB-FB-SM2LCU028 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 11568 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-006081 | CB-FB-SM2LCU030 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 13296 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-006183 | CB-FB-SM2LCU026 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 18312 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-008018 | CB-FB-SM2LCU027 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 15152 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-008019 | CB-FB-SM2LCU029 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 17032 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-010700 | CB-FB-SM2LCU031 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-07 | 20 |  | 0 | 12360 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-010701 | CB-FB-SM2LCU032 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-14 | 27 |  | 0 | 12720 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-010702 | CB-FB-SM2LCU033 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-14 | 27 |  | 0 | 12336 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-010703 | CB-FB-SM2LCU034 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-14 | 27 |  | 0 | 4656 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-010704 | CB-FB-SM2LCU035 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-14 | 27 |  | 0 | 3672 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-010705 | CB-FB-SM2LCU036 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-14 | 27 |  | 0 | 4898 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-010706 | CB-FB-SM2LCU037 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-14 | 27 |  | 0 | 2594 | Upcoming
Fiber - Patch Cord - OFNR - 2f | 23-010707 | CB-FB-SM2LCU038 | 70001631928 | RPL10 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-07 | 2026-07-14 | 27 |  | 0 | 2304 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-08 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-08 |  |  |  | 0 | 4 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-08 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | CB-ZZ-PT-3456MCMA-2600 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-14 | 2026-09-17 | 92 |  | 0 | 11 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109308 | CB-ZZ-PT-3456MCMA-2200 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-14 | 2026-09-10 | 85 |  | 0 | 9 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109203 | TAT-3456-MM24PMM24P-A2J-220 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-07-15 | 2026-07-06 | 19 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109275 | TAT-3456-MM24PMM24P-A2J-256 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-07-15 | 2026-07-06 | 19 |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109300 | TA-3456-MM24P0-SMROIM-2300 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-07-15 | 2026-07-23 | 36 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111962 | TAT-3456-MM24PMM24P-A2J-257 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-07-15 | 2026-07-06 | 19 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112121 | TAT-3456-MM24PMM24P-A2J-211 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-07-15 | 2026-07-06 | 19 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112135 | TAT-3456-MM24PMM24P-A2J-210 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-07-15 | 2026-07-06 | 19 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109241 | CB-ZZ-HT-3456MCM-228 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-15 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109270 | CB-ZZ-HT-3456MCM-236 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-15 |  |  |  | 0 | 4 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-15 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111973 | CB-ZZ-HT-3456MCM-267 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-15 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109220 | CB-ZZ-HT-3456MCM-268 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-15 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-15 |  |  |  | 0 | 4 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-15 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-15 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109188 | CB-ZZ-HT-3456MCM-380 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-21 | 2026-08-20 | 64 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109198 | CB-ZZ-HT-3456MCM-428 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-21 | 2026-08-27 | 71 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109205 | CB-ZZ-HT-3456MCM-404 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-21 | 2026-08-20 | 64 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109210 | CB-ZZ-HT-3456MCM-480 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-21 | 2026-08-20 | 64 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109227 | CB-ZZ-HT-3456MCM-456 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-21 | 2026-08-27 | 71 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109238 | CB-ZZ-HT-3456MCM-340 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-21 | 2026-08-20 | 64 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109245 | CB-ZZ-HT-3456MCM-388 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-21 | 2026-08-20 | 64 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109253 | CB-ZZ-HT-3456MCM-364 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-21 | 2026-08-20 | 64 |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | CB-ZZ-PT-3456MCMA-2600 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-21 | 2026-09-23 | 98 |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109300 | TA-3456-MM24P0-SMROIM-2300 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-07-22 | 2026-07-29 | 42 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111954 | TAT-3456-MM24PMM24P-A2J-253 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-07-22 | 2026-07-21 | 34 |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109308 | CB-ZZ-PT-3456MCMA-2200 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 5 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111935 | CB-ZZ-HT-3456MCM-277 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111938 | CB-ZZ-HT-3456MCM-321 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111958 | CB-ZZ-HT-3456MCM-285 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112122 | CB-ZZ-HT-3456MCM-254 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111954 | CB-ZZ-HT-3456MCM-253 | 70001776878 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111976 | CB-ZZ-HT-3456MCM-269 | 70001776878 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112095 | CB-ZZ-HT-3456MCM-295 | 70001776878 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112142 | CB-ZZ-HT-3456MCM-279 | 70001776878 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109208 | CB-ZZ-HT-3456MCM-296 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109300 | CB-ZZ-PT-3456MCMA-2300 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111935 | CB-ZZ-HT-3456MCM-277 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-22 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109308 | MTA-PT3456WR1-M2200 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-07-24 |  |  |  | 0 | 3 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109286 | CB-ZZ-PT-3456MCMA-3000 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-28 | 2026-09-30 | 105 |  | 0 | 16 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109316 | CB-ZZ-PT-3456MCMA-3300 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-07-28 | 2026-09-30 | 105 |  | 0 | 4 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109285 | CB-ZZ-PT-3456MCMA-2250 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-01 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109308 | CB-ZZ-PT-3456MCMA-2200 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-01 |  |  |  | 0 | 5 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109199 | CB-ZZ-HT-3456MCM-436 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-04 | 2026-09-11 | 86 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109204 | CB-ZZ-HT-3456MCM-360 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-04 | 2026-09-03 | 78 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109209 | CB-ZZ-HT-3456MCM-336 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-04 | 2026-09-11 | 86 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109248 | CB-ZZ-HT-3456MCM-460 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-04 | 2026-09-11 | 86 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109253 | CB-ZZ-HT-3456MCM-364 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-04 | 2026-09-03 | 78 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109263 | CB-ZZ-HT-3456MCM-312 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-04 | 2026-09-03 | 78 |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109316 | CB-ZZ-PT-3456MCMA-3300 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-04 | 2026-10-07 | 112 |  | 0 | 12 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109285 | MTA-PT3456WR1-M2250 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-08-04 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109308 | MTA-PT3456WR1-M2200 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-08-04 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109285 | CB-ZZ-PT-3456MCMA-2250 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-08 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109308 | CB-ZZ-PT-3456MCMA-2200 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-08 |  |  |  | 0 | 4 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109315 | CB-ZZ-PT-3456MCMA-2650 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-08 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109197 | CB-ZZ-HT-3456MCM-264 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-11 | 2026-09-11 | 86 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109200 | CB-ZZ-HT-3456MCM-240 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-11 | 2026-09-11 | 86 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109210 | CB-ZZ-HT-3456MCM-480 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-11 | 2026-09-17 | 92 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109212 | CB-ZZ-HT-3456MCM-532 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-11 | 2026-09-17 | 92 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109216 | CB-ZZ-HT-3456MCM-484 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-11 | 2026-09-11 | 86 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109232 | CB-ZZ-HT-3456MCM-508 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-11 | 2026-09-17 | 92 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109263 | CB-ZZ-HT-3456MCM-312 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-11 | 2026-09-11 | 86 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109264 | CB-ZZ-HT-3456MCM-288 | 70001625419 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-11 | 2026-09-11 | 86 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109234 | TAT-3456-MM24PMM24P-A2J-304 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-08-15 | 2026-08-21 | 65 |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109300 | TA-3456-MM24P0-SMROIM-2300 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-08-15 | 2026-08-24 | 68 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111787 | TAT-3456-MM24PMM24P-A2J-261 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-08-15 | 2026-08-21 | 65 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111788 | TAT-3456-MM24PMM24P-A2J-265 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-08-15 | 2026-08-21 | 65 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111819 | TAT-3456-MM24PMM24P-A2J-297 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-08-15 | 2026-08-21 | 65 |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109285 | CB-ZZ-PT-3456MCMA-2250 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-15 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111960 | CB-ZZ-HT-3456MCM-273 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-15 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112145 | CB-ZZ-HT-3456MCM-305 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-15 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | CB-ZZ-PT-3456MCMA-2600 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-15 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109315 | CB-ZZ-PT-3456MCMA-2650 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-15 |  |  |  | 0 | 3 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109315 | CB-ZZ-PT-3456MCMA-2650 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-15 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109293 | TA-3456-MM24P0-SMROIM-2600 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-08-22 | 2026-08-22 | 66 |  | 0 | 4 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | CB-ZZ-PT-3456MCMA-2600 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-22 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109315 | CB-ZZ-PT-3456MCMA-2650 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-08-22 |  |  |  | 0 | 6 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | CB-ZZ-PT-3456MCMA-2600 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-01 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | CB-ZZ-PT-3456MCMA-2600 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-01 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | CB-ZZ-PT-3456MCMA-2600 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-01 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109315 | CB-ZZ-PT-3456MCMA-2650 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-01 |  |  |  | 0 | 4 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109191 | TAT-3456-MM24PMM24P-A2J-316 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-09-07 | 2026-09-21 | 96 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109207 | TAT-3456-MM24PMM24P-A2J-324 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-09-07 | 2026-09-21 | 96 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109259 | TAT-3456-MM24PMM24P-A2J-280 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-09-07 | 2026-09-21 | 96 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109264 | TAT-3456-MM24PMM24P-A2J-288 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-09-07 | 2026-09-21 | 96 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111948 | TAT-3456-MM24PMM24P-A2J-317 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-09-07 | 2026-09-21 | 96 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112118 | TAT-3456-MM24PMM24P-A2J-329 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-09-07 | 2026-09-21 | 96 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109193 | CB-ZZ-HT-3456MCM-372 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109264 | CB-ZZ-HT-3456MCM-288 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111967 | CB-ZZ-HT-3456MCM-318 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-07 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111829 | CB-ZZ-HT-3456MCM-286 | 70001776878 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-07 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112118 | CB-ZZ-HT-3456MCM-329 | 70001776878 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109293 | TA-3456-MM24P0-SMROIM-2600 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-09-08 | 2026-09-23 | 98 |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109293 | TA-3456-MM24P0-SMROIM-2600 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-09-08 | 2026-09-10 | 85 |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | CB-ZZ-PT-3456MCMA-2600 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-08 |  |  |  | 0 | 6 | Upcoming
Fiber - Multi Drop - OFNR | 23-109848 | CB-SH12-24MCF24MCM-A1-017 | 70001721946 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-13 | 2026-09-12 | 87 |  | 0 | 2304 | Upcoming
Fiber - Multi Drop - OFNR | 23-109849 | CB-SH12-24MCF24MCM-A2-017 | 70001721946 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-13 | 2026-09-12 | 87 |  | 0 | 2304 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109287 | CB-ZZ-PT-3456MCMA-2550 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-15 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | CB-ZZ-PT-3456MCMA-2600 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-15 |  |  |  | 0 | 8 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109293 | TA-3456-MM24P0-SMROIM-2600 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-09-22 | 2026-09-21 | 96 |  | 0 | 4 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109287 | CB-ZZ-PT-3456MCMA-2550 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-22 |  |  |  | 0 | 3 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109293 | CB-ZZ-PT-3456MCMA-2600 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-22 |  |  |  | 0 | 3 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109306 | CB-ZZ-PT-3456MCMA-3050 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-09-22 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109263 | TAT-3456-MM24PMM24P-A2J-312 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-10-01 | 2026-10-21 | 126 |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109287 | TA-3456-MM24P0-SMROIM-2550 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-10-01 | 2026-10-21 | 126 |  | 0 | 3 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109293 | TA-3456-MM24P0-SMROIM-2600 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-10-01 | 2026-10-21 | 126 |  | 0 | 3 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109234 | CB-ZZ-HT-3456MCM-304 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-01 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109306 | CB-ZZ-PT-3456MCMA-3050 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-01 |  |  |  | 0 | 6 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111970 | CB-ZZ-HT-3456MCM-343 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-01 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112145 | CB-ZZ-HT-3456MCM-305 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-01 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111810 | CB-ZZ-HT-3456MCM-311 | 70001776878 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-01 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-109263 | CB-ZZ-HT-3456MCM-312 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-01 |  |  |  | 0 | 1 | Upcoming
| 23-112062 | TAT-3456-MM24PMM24P-A2J-345 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-10-07 |  |  |  | 0 | 2 | Upcoming
| 23-112074 | TAT-3456-MM24PMM24P-A2J-337 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-10-07 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112090 | TAT-3456-MM24PMM24P-A2J-355 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-10-07 | 2026-10-21 | 126 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112091 | TAT-3456-MM24PMM24P-A2J-354 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-10-07 | 2026-10-21 | 126 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112085 | CB-ZZ-HT-3456MCM-396 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112141 | CB-ZZ-HT-3456MCM-397 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109306 | CB-ZZ-PT-3456MCMA-3050 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-08 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109306 | CB-ZZ-PT-3456MCMA-3050 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-08 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109306 | MTA-PT3456WR1-M3050 | 70001758007 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-10-15 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109306 | CB-ZZ-PT-3456MCMA-3050 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-15 |  |  |  | 0 | 3 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109286 | CB-ZZ-PT-3456MCMA-3000 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-15 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109306 | CB-ZZ-PT-3456MCMA-3050 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-15 |  |  |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103703 | CB-FE-HT-288MCM-030 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103704 | CB-FE-HT-288MCM-029 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 32 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103705 | CB-FE-HT-288MCM-037 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103706 | CB-FE-HT-288MCM-035 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103707 | CB-FE-HT-288MCM-039 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103708 | CB-FE-HT-288MCM-040 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103709 | CB-FE-HT-288MCM-033 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103711 | CB-FE-HT-288MCM-036 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103712 | CB-FE-HT-288MCM-022 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103714 | CB-FE-HT-288MCM-031 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103715 | CB-FE-HT-288MCM-021 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103716 | CB-FE-HT-288MCM-023 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 28 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103717 | CB-FE-HT-288MCM-032 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103718 | CB-FE-HT-288MCM-026 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 20 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103719 | CB-FE-HT-288MCM-024 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103720 | CB-FE-HT-288MCM-027 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103721 | CB-FE-HT-288MCM-025 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104213 | CB-FE-HT-288MCM-051 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 36 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104215 | CB-FE-HT-288MCM-052 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104216 | CB-FE-HT-288MCM-056 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104217 | CB-FE-HT-288MCM-053 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104220 | CB-FE-HT-288MCM-048 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 24 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104222 | CB-FE-HT-288MCM-045 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 26 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104225 | CB-FE-HT-288MCM-062 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 20 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104228 | CB-FE-HT-288MCM-061 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 18 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104229 | CB-FE-HT-288MCM-042 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104230 | CB-FE-HT-288MCM-066 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104231 | CB-FE-HT-288MCM-063 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104232 | CB-FE-HT-288MCM-070 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104233 | CB-FE-HT-288MCM-065 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104234 | CB-FE-HT-288MCM-059 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104235 | CB-FE-HT-288MCM-069 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104238 | CB-FE-HT-288MCM-044 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104240 | CB-FE-HT-288MCM-054 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104241 | CB-FE-HT-288MCM-058 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 34 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104242 | CB-FE-HT-288MCM-067 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104244 | CB-FE-HT-288MCM-057 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104246 | CB-FE-HT-288MCM-047 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 26 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104247 | CB-FE-HT-288MCM-055 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 24 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104248 | CB-FE-HT-288MCM-060 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104252 | CB-FE-HT-288MCM-068 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104253 | CB-FE-HT-288MCM-050 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 24 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104254 | CB-FE-HT-288MCM-049 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104256 | CB-FE-HT-288MCM-064 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 24 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104257 | CB-FE-HT-288MCM-043 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104262 | CB-FE-HT-288MCM-046 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104263 | CB-FE-HT-288MCM-075 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104265 | CB-FE-HT-288MCM-096 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104266 | CB-FE-HT-288MCM-081 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104268 | CB-FE-HT-288MCM-093 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104269 | CB-FE-HT-288MCM-079 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104272 | CB-FE-HT-288MCM-071 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 18 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104273 | CB-FE-HT-288MCM-073 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104274 | CB-FE-HT-288MCM-083 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 22 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104276 | CB-FE-HT-288MCM-077 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 20 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104278 | CB-FE-HT-288MCM-074 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104280 | CB-FE-HT-288MCM-095 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104281 | CB-FE-HT-288MCM-086 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104283 | CB-FE-HT-288MCM-097 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104285 | CB-FE-HT-288MCM-080 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104286 | CB-FE-HT-288MCM-090 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104288 | CB-FE-HT-288MCM-094 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104289 | CB-FE-HT-288MCM-092 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104290 | CB-FE-HT-288MCM-085 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112826 | CB-FE-ET-096MCFMCM-199 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112827 | CB-FE-ET-096MCFMCM-201 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112827 | CB-FE-ET-096MCFMCM-201 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112827 | CB-FE-ET-096MCFMCM-201 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112828 | CB-FE-ET-096MCFMCM-175 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 3 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112828 | CB-FE-ET-096MCFMCM-175 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112828 | CB-FE-ET-096MCFMCM-175 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112829 | CB-FE-ET-096MCFMCM-192 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112829 | CB-FE-ET-096MCFMCM-192 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112829 | CB-FE-ET-096MCFMCM-192 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112830 | CB-FE-ET-096MCFMCM-271 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112831 | CB-FE-ET-096MCFMCM-189 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112831 | CB-FE-ET-096MCFMCM-189 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112832 | CB-FE-ET-096MCFMCM-227 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112832 | CB-FE-ET-096MCFMCM-227 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112833 | CB-FE-ET-096MCFMCM-078 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112834 | CB-FE-ET-096MCFMCM-176 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112834 | CB-FE-ET-096MCFMCM-176 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112834 | CB-FE-ET-096MCFMCM-176 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112835 | CB-FE-ET-096MCFMCM-108 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112835 | CB-FE-ET-096MCFMCM-108 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112836 | CB-FE-ET-096MCFMCM-225 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112836 | CB-FE-ET-096MCFMCM-225 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112837 | CB-FE-ET-096MCFMCM-217 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112837 | CB-FE-ET-096MCFMCM-217 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112837 | CB-FE-ET-096MCFMCM-217 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112838 | CB-FE-ET-096MCFMCM-158 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112838 | CB-FE-ET-096MCFMCM-158 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112838 | CB-FE-ET-096MCFMCM-158 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112838 | CB-FE-ET-096MCFMCM-158 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112839 | CB-FE-ET-096MCFMCM-140 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112839 | CB-FE-ET-096MCFMCM-140 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112840 | CB-FE-ET-096MCFMCM-127 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112840 | CB-FE-ET-096MCFMCM-127 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112841 | CB-FE-ET-096MCFMCM-244 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112841 | CB-FE-ET-096MCFMCM-244 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112842 | CB-FE-ET-096MCFMCM-216 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112842 | CB-FE-ET-096MCFMCM-216 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105381 | CB-FE-ET-288MCFMCM-023 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 48 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105383 | CB-FE-ET-288MCFMCM-020 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 192 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105385 | CB-FE-ET-288MCFMCM-014 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 56 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105387 | CB-FE-ET-288MCFMCM-022 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 112 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105392 | CB-FE-ET-288MCFMCM-021 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 168 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105400 | CB-FE-ET-288MCFMCM-018 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 184 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105404 | CB-FE-ET-288MCFMCM-024 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105405 | CB-FE-ET-288MCFMCM-017 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 190 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105406 | CB-FE-ET-288MCFMCM-019 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 168 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105412 | CB-FE-ET-288MCFMCM-013 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 16 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105413 | CB-FE-ET-288MCFMCM-015 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 128 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105414 | CB-FE-ET-288MCFMCM-016 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 170 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-100753 | CB-FE-ET-384MCFMCM-012 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-100775 | CB-FE-ET-384MCFMCM-014 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 528 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-103080 | CB-FE-ET-384MCFMCM-013 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 128 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-105742 | CB-FE-ET-384MCFMCM-015 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-105746 | CB-FE-ET-384MCFMCM-011 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 272 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-103697 | CB-FE-ET-192MCFMCM-013 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-103698 | CB-FE-ET-192MCFMCM-015 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 48 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-104499 | CB-FE-ET-192MCFMCM-020 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 64 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-104500 | CB-FE-ET-192MCFMCM-024 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-104512 | CB-FE-ET-192MCFMCM-022 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 24 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-104532 | CB-FE-ET-192MCFMCM-019 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 52 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-104538 | CB-FE-ET-192MCFMCM-016 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 52 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-106631 | CB-FE-ET-192MCFMCM-017 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 64 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-106632 | CB-FE-ET-192MCFMCM-018 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 60 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-106633 | CB-FE-ET-192MCFMCM-023 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 24 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-106636 | CB-FE-ET-192MCFMCM-021 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 52 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-106637 | CB-FE-ET-192MCFMCM-014 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 28 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112769 | CB-FE-ET-096MCFMCM-241 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112770 | CB-FE-ET-096MCFMCM-139 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112770 | CB-FE-ET-096MCFMCM-139 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112770 | CB-FE-ET-096MCFMCM-139 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112771 | CB-FE-ET-096MCFMCM-259 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112772 | CB-FE-ET-096MCFMCM-134 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112772 | CB-FE-ET-096MCFMCM-134 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112773 | CB-FE-ET-096MCFMCM-193 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112773 | CB-FE-ET-096MCFMCM-193 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112773 | CB-FE-ET-096MCFMCM-193 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112774 | CB-FE-ET-096MCFMCM-085 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112774 | CB-FE-ET-096MCFMCM-085 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112775 | CB-FE-ET-096MCFMCM-211 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112776 | CB-FE-ET-096MCFMCM-186 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112776 | CB-FE-ET-096MCFMCM-186 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112776 | CB-FE-ET-096MCFMCM-186 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112777 | CB-FE-ET-096MCFMCM-242 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112777 | CB-FE-ET-096MCFMCM-242 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112778 | CB-FE-ET-096MCFMCM-190 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112778 | CB-FE-ET-096MCFMCM-190 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112779 | CB-FE-ET-096MCFMCM-208 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112779 | CB-FE-ET-096MCFMCM-208 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112780 | CB-FE-ET-096MCFMCM-173 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112780 | CB-FE-ET-096MCFMCM-173 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112780 | CB-FE-ET-096MCFMCM-173 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112781 | CB-FE-ET-096MCFMCM-203 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112781 | CB-FE-ET-096MCFMCM-203 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112782 | CB-FE-ET-096MCFMCM-184 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112783 | CB-FE-ET-096MCFMCM-062 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112784 | CB-FE-ET-096MCFMCM-213 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112784 | CB-FE-ET-096MCFMCM-213 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112785 | CB-FE-ET-096MCFMCM-110 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112785 | CB-FE-ET-096MCFMCM-110 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112786 | CB-FE-ET-096MCFMCM-224 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112786 | CB-FE-ET-096MCFMCM-224 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112787 | CB-FE-ET-096MCFMCM-272 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112788 | CB-FE-ET-096MCFMCM-245 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112788 | CB-FE-ET-096MCFMCM-245 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112789 | CB-FE-ET-096MCFMCM-243 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112789 | CB-FE-ET-096MCFMCM-243 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112790 | CB-FE-ET-096MCFMCM-178 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112790 | CB-FE-ET-096MCFMCM-178 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112791 | CB-FE-ET-096MCFMCM-248 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112792 | CB-FE-ET-096MCFMCM-253 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112792 | CB-FE-ET-096MCFMCM-253 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112793 | CB-FE-ET-096MCFMCM-133 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112793 | CB-FE-ET-096MCFMCM-133 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112794 | CB-FE-ET-096MCFMCM-097 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112794 | CB-FE-ET-096MCFMCM-097 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112795 | CB-FE-ET-096MCFMCM-212 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112795 | CB-FE-ET-096MCFMCM-212 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112796 | CB-FE-ET-096MCFMCM-195 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112796 | CB-FE-ET-096MCFMCM-195 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112796 | CB-FE-ET-096MCFMCM-195 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112796 | CB-FE-ET-096MCFMCM-195 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112797 | CB-FE-ET-096MCFMCM-089 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112798 | CB-FE-ET-096MCFMCM-187 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112798 | CB-FE-ET-096MCFMCM-187 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112798 | CB-FE-ET-096MCFMCM-187 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112799 | CB-FE-ET-096MCFMCM-257 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112800 | CB-FE-ET-096MCFMCM-181 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112801 | CB-FE-ET-096MCFMCM-221 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112801 | CB-FE-ET-096MCFMCM-221 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112801 | CB-FE-ET-096MCFMCM-221 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112802 | CB-FE-ET-096MCFMCM-265 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112803 | CB-FE-ET-096MCFMCM-188 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112803 | CB-FE-ET-096MCFMCM-188 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112803 | CB-FE-ET-096MCFMCM-188 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112804 | CB-FE-ET-096MCFMCM-232 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112805 | CB-FE-ET-096MCFMCM-250 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112805 | CB-FE-ET-096MCFMCM-250 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112806 | CB-FE-ET-096MCFMCM-214 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112806 | CB-FE-ET-096MCFMCM-214 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112807 | CB-FE-ET-096MCFMCM-238 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112807 | CB-FE-ET-096MCFMCM-238 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112808 | CB-FE-ET-096MCFMCM-230 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112809 | CB-FE-ET-096MCFMCM-126 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112809 | CB-FE-ET-096MCFMCM-126 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112810 | CB-FE-ET-096MCFMCM-249 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112811 | CB-FE-ET-096MCFMCM-115 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112811 | CB-FE-ET-096MCFMCM-115 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112812 | CB-FE-ET-096MCFMCM-179 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112812 | CB-FE-ET-096MCFMCM-179 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112813 | CB-FE-ET-096MCFMCM-143 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112813 | CB-FE-ET-096MCFMCM-143 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112814 | CB-FE-ET-096MCFMCM-177 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112814 | CB-FE-ET-096MCFMCM-177 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112814 | CB-FE-ET-096MCFMCM-177 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112814 | CB-FE-ET-096MCFMCM-177 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112815 | CB-FE-ET-096MCFMCM-220 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112815 | CB-FE-ET-096MCFMCM-220 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112815 | CB-FE-ET-096MCFMCM-220 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112816 | CB-FE-ET-096MCFMCM-200 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 3 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112816 | CB-FE-ET-096MCFMCM-200 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112816 | CB-FE-ET-096MCFMCM-200 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112817 | CB-FE-ET-096MCFMCM-163 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112818 | CB-FE-ET-096MCFMCM-183 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112818 | CB-FE-ET-096MCFMCM-183 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112818 | CB-FE-ET-096MCFMCM-183 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112819 | CB-FE-ET-096MCFMCM-267 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112820 | CB-FE-ET-096MCFMCM-198 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112820 | CB-FE-ET-096MCFMCM-198 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112821 | CB-FE-ET-096MCFMCM-174 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112821 | CB-FE-ET-096MCFMCM-174 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112821 | CB-FE-ET-096MCFMCM-174 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112821 | CB-FE-ET-096MCFMCM-174 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112822 | CB-FE-ET-096MCFMCM-191 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112822 | CB-FE-ET-096MCFMCM-191 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112822 | CB-FE-ET-096MCFMCM-191 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112823 | CB-FE-ET-096MCFMCM-150 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112823 | CB-FE-ET-096MCFMCM-150 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112823 | CB-FE-ET-096MCFMCM-150 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112824 | CB-FE-ET-096MCFMCM-207 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112824 | CB-FE-ET-096MCFMCM-207 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112824 | CB-FE-ET-096MCFMCM-207 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112825 | CB-FE-ET-096MCFMCM-274 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112826 | CB-FE-ET-096MCFMCM-199 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112826 | CB-FE-ET-096MCFMCM-199 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112826 | CB-FE-ET-096MCFMCM-199 | 70001776819 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110568 | CB-FE-HT-288MCM-105 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110608 | CB-FE-HT-288MCM-156 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110609 | CB-FE-HT-288MCM-125 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110619 | CB-FE-HT-288MCM-155 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110623 | CB-FE-HT-288MCM-128 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110637 | CB-FE-HT-288MCM-148 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110653 | CB-FE-HT-288MCM-158 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 48f | 23-112685 | CB-FE-HT-048MCM-004 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 384 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106256 | CB-FE-ET-096MCFMCM-169 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106256 | CB-FE-ET-096MCFMCM-169 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106256 | CB-FE-ET-096MCFMCM-169 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106257 | CB-FE-ET-096MCFMCM-160 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106257 | CB-FE-ET-096MCFMCM-160 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106257 | CB-FE-ET-096MCFMCM-160 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106261 | CB-FE-ET-096MCFMCM-088 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106262 | CB-FE-ET-096MCFMCM-142 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106262 | CB-FE-ET-096MCFMCM-142 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106263 | CB-FE-ET-096MCFMCM-100 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106263 | CB-FE-ET-096MCFMCM-100 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106265 | CB-FE-ET-096MCFMCM-065 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106266 | CB-FE-ET-096MCFMCM-170 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106266 | CB-FE-ET-096MCFMCM-170 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106266 | CB-FE-ET-096MCFMCM-170 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106266 | CB-FE-ET-096MCFMCM-170 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106267 | CB-FE-ET-096MCFMCM-105 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106267 | CB-FE-ET-096MCFMCM-105 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106271 | CB-FE-ET-096MCFMCM-117 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106271 | CB-FE-ET-096MCFMCM-117 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106272 | CB-FE-ET-096MCFMCM-116 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106272 | CB-FE-ET-096MCFMCM-116 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106277 | CB-FE-ET-096MCFMCM-107 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106277 | CB-FE-ET-096MCFMCM-107 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106279 | CB-FE-ET-096MCFMCM-087 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106280 | CB-FE-ET-096MCFMCM-131 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106280 | CB-FE-ET-096MCFMCM-131 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106285 | CB-FE-ET-096MCFMCM-102 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106285 | CB-FE-ET-096MCFMCM-102 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106286 | CB-FE-ET-096MCFMCM-128 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106289 | CB-FE-ET-096MCFMCM-141 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106290 | CB-FE-ET-096MCFMCM-112 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106292 | CB-FE-ET-096MCFMCM-099 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106292 | CB-FE-ET-096MCFMCM-099 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106293 | CB-FE-ET-096MCFMCM-136 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106293 | CB-FE-ET-096MCFMCM-136 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106293 | CB-FE-ET-096MCFMCM-136 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106296 | CB-FE-ET-096MCFMCM-072 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106297 | CB-FE-ET-096MCFMCM-083 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106300 | CB-FE-ET-096MCFMCM-093 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106301 | CB-FE-ET-096MCFMCM-070 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106302 | CB-FE-ET-096MCFMCM-086 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106305 | CB-FE-ET-096MCFMCM-167 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106305 | CB-FE-ET-096MCFMCM-167 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106305 | CB-FE-ET-096MCFMCM-167 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106306 | CB-FE-ET-096MCFMCM-095 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106307 | CB-FE-ET-096MCFMCM-152 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106307 | CB-FE-ET-096MCFMCM-152 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106307 | CB-FE-ET-096MCFMCM-152 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106307 | CB-FE-ET-096MCFMCM-152 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106311 | CB-FE-ET-096MCFMCM-144 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106311 | CB-FE-ET-096MCFMCM-144 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106311 | CB-FE-ET-096MCFMCM-144 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106313 | CB-FE-ET-096MCFMCM-151 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106313 | CB-FE-ET-096MCFMCM-151 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106313 | CB-FE-ET-096MCFMCM-151 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106314 | CB-FE-ET-096MCFMCM-145 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106314 | CB-FE-ET-096MCFMCM-145 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106314 | CB-FE-ET-096MCFMCM-145 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106314 | CB-FE-ET-096MCFMCM-145 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106315 | CB-FE-ET-096MCFMCM-094 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106316 | CB-FE-ET-096MCFMCM-129 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106316 | CB-FE-ET-096MCFMCM-129 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106320 | CB-FE-ET-096MCFMCM-157 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106320 | CB-FE-ET-096MCFMCM-157 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106320 | CB-FE-ET-096MCFMCM-157 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106320 | CB-FE-ET-096MCFMCM-157 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106321 | CB-FE-ET-096MCFMCM-113 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106323 | CB-FE-ET-096MCFMCM-161 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106323 | CB-FE-ET-096MCFMCM-161 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106323 | CB-FE-ET-096MCFMCM-161 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106324 | CB-FE-ET-096MCFMCM-109 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106324 | CB-FE-ET-096MCFMCM-109 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106326 | CB-FE-ET-096MCFMCM-084 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106326 | CB-FE-ET-096MCFMCM-084 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106327 | CB-FE-ET-096MCFMCM-164 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106327 | CB-FE-ET-096MCFMCM-164 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106327 | CB-FE-ET-096MCFMCM-164 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106329 | CB-FE-ET-096MCFMCM-123 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106329 | CB-FE-ET-096MCFMCM-123 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106331 | CB-FE-ET-096MCFMCM-132 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106331 | CB-FE-ET-096MCFMCM-132 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106331 | CB-FE-ET-096MCFMCM-132 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106335 | CB-FE-ET-096MCFMCM-118 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106336 | CB-FE-ET-096MCFMCM-082 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106336 | CB-FE-ET-096MCFMCM-082 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106340 | CB-FE-ET-096MCFMCM-121 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106340 | CB-FE-ET-096MCFMCM-121 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106343 | CB-FE-ET-096MCFMCM-159 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106345 | CB-FE-ET-096MCFMCM-146 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106345 | CB-FE-ET-096MCFMCM-146 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106345 | CB-FE-ET-096MCFMCM-146 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106345 | CB-FE-ET-096MCFMCM-146 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106346 | CB-FE-ET-096MCFMCM-165 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106346 | CB-FE-ET-096MCFMCM-165 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106346 | CB-FE-ET-096MCFMCM-165 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106350 | CB-FE-ET-096MCFMCM-125 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106350 | CB-FE-ET-096MCFMCM-125 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106350 | CB-FE-ET-096MCFMCM-125 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106351 | CB-FE-ET-096MCFMCM-076 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106352 | CB-FE-ET-096MCFMCM-090 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106352 | CB-FE-ET-096MCFMCM-090 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106353 | CB-FE-ET-096MCFMCM-124 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106353 | CB-FE-ET-096MCFMCM-124 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110414 | CB-FE-HT-192MCM-170 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110415 | CB-FE-HT-192MCM-136 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110419 | CB-FE-HT-192MCM-148 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110421 | CB-FE-HT-192MCM-061 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110423 | CB-FE-HT-192MCM-079 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110425 | CB-FE-HT-192MCM-051 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110432 | CB-FE-HT-192MCM-098 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110441 | CB-FE-HT-192MCM-142 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110445 | CB-FE-HT-192MCM-100 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110446 | CB-FE-HT-192MCM-071 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 9 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110450 | CB-FE-HT-192MCM-085 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110454 | CB-FE-HT-192MCM-110 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110455 | CB-FE-HT-192MCM-120 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110461 | CB-FE-HT-192MCM-091 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110464 | CB-FE-HT-192MCM-122 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110465 | CB-FE-HT-192MCM-067 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110470 | CB-FE-HT-192MCM-160 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110471 | CB-FE-HT-192MCM-158 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110483 | CB-FE-HT-192MCM-138 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110491 | CB-FE-HT-192MCM-116 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110492 | CB-FE-HT-192MCM-073 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110495 | CB-FE-HT-192MCM-176 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110496 | CB-FE-HT-192MCM-104 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110501 | CB-FE-HT-192MCM-154 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110505 | CB-FE-HT-192MCM-164 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110508 | CB-FE-HT-192MCM-139 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111119 | CB-FE-HT-192MCM-043 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111120 | CB-FE-HT-192MCM-097 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111121 | CB-FE-HT-192MCM-078 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111122 | CB-FE-HT-192MCM-084 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111123 | CB-FE-HT-192MCM-090 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111125 | CB-FE-HT-192MCM-037 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111126 | CB-FE-HT-192MCM-039 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111127 | CB-FE-HT-192MCM-049 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111129 | CB-FE-HT-192MCM-096 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111130 | CB-FE-HT-192MCM-087 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112692 | CB-FE-HT-192MCM-150 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112693 | CB-FE-HT-192MCM-134 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112694 | CB-FE-HT-192MCM-183 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112695 | CB-FE-HT-192MCM-118 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112696 | CB-FE-HT-192MCM-128 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112700 | CB-FE-HT-192MCM-156 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112703 | CB-FE-HT-192MCM-102 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 9 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112705 | CB-FE-HT-192MCM-133 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 9 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112706 | CB-FE-HT-192MCM-103 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112707 | CB-FE-HT-192MCM-112 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112708 | CB-FE-HT-192MCM-124 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112709 | CB-FE-HT-192MCM-146 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112710 | CB-FE-HT-192MCM-152 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112711 | CB-FE-HT-192MCM-144 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112712 | CB-FE-HT-192MCM-141 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112713 | CB-FE-HT-192MCM-106 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112714 | CB-FE-HT-192MCM-127 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112717 | CB-FE-HT-192MCM-108 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112718 | CB-FE-HT-192MCM-131 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112719 | CB-FE-HT-192MCM-114 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112720 | CB-FE-HT-192MCM-130 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112721 | CB-FE-HT-192MCM-126 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-101114 | CB-FE-HT-288MCM-005 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 32 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103588 | CB-FE-HT-288MCM-015 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103589 | CB-FE-HT-288MCM-016 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103591 | CB-FE-HT-288MCM-017 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103592 | CB-FE-HT-288MCM-018 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103593 | CB-FE-HT-288MCM-019 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103594 | CB-FE-HT-288MCM-020 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104291 | CB-FE-HT-288MCM-091 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104295 | CB-FE-HT-288MCM-098 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104297 | CB-FE-HT-288MCM-100 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104298 | CB-FE-HT-288MCM-099 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104299 | CB-FE-HT-288MCM-084 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104300 | CB-FE-HT-288MCM-088 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104301 | CB-FE-HT-288MCM-072 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104302 | CB-FE-HT-288MCM-087 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104310 | CB-FE-HT-288MCM-078 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104311 | CB-FE-HT-288MCM-089 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 22 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105437 | CB-FE-HT-288MCM-145 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105438 | CB-FE-HT-288MCM-150 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105439 | CB-FE-HT-288MCM-123 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105441 | CB-FE-HT-288MCM-108 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 24 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105442 | CB-FE-HT-288MCM-111 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105443 | CB-FE-HT-288MCM-122 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105446 | CB-FE-HT-288MCM-179 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105447 | CB-FE-HT-288MCM-141 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105455 | CB-FE-HT-288MCM-102 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 18 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105456 | CB-FE-HT-288MCM-151 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105459 | CB-FE-HT-288MCM-153 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105460 | CB-FE-HT-288MCM-113 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105461 | CB-FE-HT-288MCM-133 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 18 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105462 | CB-FE-HT-288MCM-101 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105463 | CB-FE-HT-288MCM-147 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105466 | CB-FE-HT-288MCM-138 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105468 | CB-FE-HT-288MCM-120 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105469 | CB-FE-HT-288MCM-139 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105470 | CB-FE-HT-288MCM-142 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105474 | CB-FE-HT-288MCM-154 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105476 | CB-FE-HT-288MCM-114 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 24 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105477 | CB-FE-HT-288MCM-134 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105478 | CB-FE-HT-288MCM-110 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105485 | CB-FE-HT-288MCM-135 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105486 | CB-FE-HT-288MCM-126 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106767 | CB-FE-HT-288MCM-115 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106772 | CB-FE-HT-288MCM-146 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106773 | CB-FE-HT-288MCM-118 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106774 | CB-FE-HT-288MCM-144 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106777 | CB-FE-HT-288MCM-104 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106779 | CB-FE-HT-288MCM-116 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106780 | CB-FE-HT-288MCM-143 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106781 | CB-FE-HT-288MCM-137 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106782 | CB-FE-HT-288MCM-129 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106786 | CB-FE-HT-288MCM-127 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106791 | CB-FE-HT-288MCM-112 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106802 | CB-FE-HT-288MCM-152 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106804 | CB-FE-HT-288MCM-121 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106809 | CB-FE-HT-288MCM-103 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-111743 | CB-FE-HT-288MCM-130 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-111744 | CB-FE-HT-288MCM-161 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-112687 | CB-FE-HT-288MCM-164 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-112688 | CB-FE-HT-288MCM-167 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-112689 | CB-FE-HT-288MCM-173 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-112690 | CB-FE-HT-288MCM-176 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110251 | CB-FE-HT-288MCM-106 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110252 | CB-FE-HT-288MCM-109 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110253 | CB-FE-HT-288MCM-119 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110254 | CB-FE-HT-288MCM-124 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110255 | CB-FE-HT-288MCM-131 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110256 | CB-FE-HT-288MCM-136 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110529 | CB-FE-HT-288MCM-160 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110534 | CB-FE-HT-288MCM-117 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110541 | CB-FE-HT-288MCM-170 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110559 | CB-FE-HT-288MCM-140 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110560 | CB-FE-HT-288MCM-183 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106353 | CB-FE-ET-096MCFMCM-124 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106358 | CB-FE-ET-096MCFMCM-119 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106358 | CB-FE-ET-096MCFMCM-119 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106359 | CB-FE-ET-096MCFMCM-101 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106359 | CB-FE-ET-096MCFMCM-101 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106362 | CB-FE-ET-096MCFMCM-122 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106362 | CB-FE-ET-096MCFMCM-122 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106363 | CB-FE-ET-096MCFMCM-069 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106364 | CB-FE-ET-096MCFMCM-106 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106365 | CB-FE-ET-096MCFMCM-156 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106365 | CB-FE-ET-096MCFMCM-156 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106369 | CB-FE-ET-096MCFMCM-114 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106370 | CB-FE-ET-096MCFMCM-168 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106370 | CB-FE-ET-096MCFMCM-168 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106371 | CB-FE-ET-096MCFMCM-149 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106371 | CB-FE-ET-096MCFMCM-149 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106371 | CB-FE-ET-096MCFMCM-149 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106373 | CB-FE-ET-096MCFMCM-135 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106373 | CB-FE-ET-096MCFMCM-135 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106379 | CB-FE-ET-096MCFMCM-155 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106379 | CB-FE-ET-096MCFMCM-155 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106381 | CB-FE-ET-096MCFMCM-064 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106382 | CB-FE-ET-096MCFMCM-120 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106382 | CB-FE-ET-096MCFMCM-120 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106383 | CB-FE-ET-096MCFMCM-079 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106384 | CB-FE-ET-096MCFMCM-153 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106385 | CB-FE-ET-096MCFMCM-104 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-106385 | CB-FE-ET-096MCFMCM-104 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-109613 | CB-FE-ET-096MCFMCM-147 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-109613 | CB-FE-ET-096MCFMCM-147 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112722 | CB-FE-ET-096MCFMCM-237 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112722 | CB-FE-ET-096MCFMCM-237 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112723 | CB-FE-ET-096MCFMCM-252 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112724 | CB-FE-ET-096MCFMCM-268 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112725 | CB-FE-ET-096MCFMCM-266 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112726 | CB-FE-ET-096MCFMCM-219 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112726 | CB-FE-ET-096MCFMCM-219 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112727 | CB-FE-ET-096MCFMCM-206 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112728 | CB-FE-ET-096MCFMCM-130 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112728 | CB-FE-ET-096MCFMCM-130 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112729 | CB-FE-ET-096MCFMCM-236 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112730 | CB-FE-ET-096MCFMCM-154 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112730 | CB-FE-ET-096MCFMCM-154 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112730 | CB-FE-ET-096MCFMCM-154 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112731 | CB-FE-ET-096MCFMCM-092 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112732 | CB-FE-ET-096MCFMCM-196 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112732 | CB-FE-ET-096MCFMCM-196 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112732 | CB-FE-ET-096MCFMCM-196 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112733 | CB-FE-ET-096MCFMCM-171 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112733 | CB-FE-ET-096MCFMCM-171 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112733 | CB-FE-ET-096MCFMCM-171 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112733 | CB-FE-ET-096MCFMCM-171 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112734 | CB-FE-ET-096MCFMCM-148 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112734 | CB-FE-ET-096MCFMCM-148 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112734 | CB-FE-ET-096MCFMCM-148 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112735 | CB-FE-ET-096MCFMCM-180 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112735 | CB-FE-ET-096MCFMCM-180 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112735 | CB-FE-ET-096MCFMCM-180 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112736 | CB-FE-ET-096MCFMCM-111 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112737 | CB-FE-ET-096MCFMCM-235 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112738 | CB-FE-ET-096MCFMCM-226 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112739 | CB-FE-ET-096MCFMCM-246 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112740 | CB-FE-ET-096MCFMCM-218 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112740 | CB-FE-ET-096MCFMCM-218 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112741 | CB-FE-ET-096MCFMCM-185 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112741 | CB-FE-ET-096MCFMCM-185 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112741 | CB-FE-ET-096MCFMCM-185 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112742 | CB-FE-ET-096MCFMCM-202 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112742 | CB-FE-ET-096MCFMCM-202 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112742 | CB-FE-ET-096MCFMCM-202 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112743 | CB-FE-ET-096MCFMCM-162 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112743 | CB-FE-ET-096MCFMCM-162 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112743 | CB-FE-ET-096MCFMCM-162 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112744 | CB-FE-ET-096MCFMCM-182 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112744 | CB-FE-ET-096MCFMCM-182 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112744 | CB-FE-ET-096MCFMCM-182 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112744 | CB-FE-ET-096MCFMCM-182 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112745 | CB-FE-ET-096MCFMCM-166 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112745 | CB-FE-ET-096MCFMCM-166 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112745 | CB-FE-ET-096MCFMCM-166 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112746 | CB-FE-ET-096MCFMCM-258 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112747 | CB-FE-ET-096MCFMCM-234 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112748 | CB-FE-ET-096MCFMCM-240 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112749 | CB-FE-ET-096MCFMCM-247 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112749 | CB-FE-ET-096MCFMCM-247 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112750 | CB-FE-ET-096MCFMCM-205 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112750 | CB-FE-ET-096MCFMCM-205 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112751 | CB-FE-ET-096MCFMCM-233 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112751 | CB-FE-ET-096MCFMCM-233 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112752 | CB-FE-ET-096MCFMCM-251 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112753 | CB-FE-ET-096MCFMCM-223 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112754 | CB-FE-ET-096MCFMCM-197 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112754 | CB-FE-ET-096MCFMCM-197 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112754 | CB-FE-ET-096MCFMCM-197 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112755 | CB-FE-ET-096MCFMCM-222 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112755 | CB-FE-ET-096MCFMCM-222 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112755 | CB-FE-ET-096MCFMCM-222 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112756 | CB-FE-ET-096MCFMCM-138 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112757 | CB-FE-ET-096MCFMCM-204 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112758 | CB-FE-ET-096MCFMCM-228 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112758 | CB-FE-ET-096MCFMCM-228 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112759 | CB-FE-ET-096MCFMCM-172 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112759 | CB-FE-ET-096MCFMCM-172 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112759 | CB-FE-ET-096MCFMCM-172 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112760 | CB-FE-ET-096MCFMCM-215 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112760 | CB-FE-ET-096MCFMCM-215 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112761 | CB-FE-ET-096MCFMCM-194 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 2 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112761 | CB-FE-ET-096MCFMCM-194 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112761 | CB-FE-ET-096MCFMCM-194 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112762 | CB-FE-ET-096MCFMCM-231 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112763 | CB-FE-ET-096MCFMCM-263 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112764 | CB-FE-ET-096MCFMCM-210 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112764 | CB-FE-ET-096MCFMCM-210 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112765 | CB-FE-ET-096MCFMCM-264 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 |  |  |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112766 | CB-FE-ET-096MCFMCM-137 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112766 | CB-FE-ET-096MCFMCM-137 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112766 | CB-FE-ET-096MCFMCM-137 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112767 | CB-FE-ET-096MCFMCM-096 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 96f | 23-112768 | CB-FE-ET-096MCFMCM-080 | 70001776848 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102970 | CB-FE-HT-192MCM-020 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102973 | CB-FE-HT-192MCM-094 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102974 | CB-FE-HT-192MCM-070 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102976 | CB-FE-HT-192MCM-092 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102977 | CB-FE-HT-192MCM-080 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102978 | CB-FE-HT-192MCM-069 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102980 | CB-FE-HT-192MCM-058 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102982 | CB-FE-HT-192MCM-056 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102983 | CB-FE-HT-192MCM-045 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102984 | CB-FE-HT-192MCM-081 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102985 | CB-FE-HT-192MCM-033 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102987 | CB-FE-HT-192MCM-046 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102990 | CB-FE-HT-192MCM-031 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102991 | CB-FE-HT-192MCM-068 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102992 | CB-FE-HT-192MCM-057 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102993 | CB-FE-HT-192MCM-093 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103174 | CB-FE-HT-192MCM-086 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103175 | CB-FE-HT-192MCM-075 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103176 | CB-FE-HT-192MCM-052 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103177 | CB-FE-HT-192MCM-089 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 11 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103178 | CB-FE-HT-192MCM-065 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103179 | CB-FE-HT-192MCM-111 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103181 | CB-FE-HT-192MCM-101 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103183 | CB-FE-HT-192MCM-074 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103184 | CB-FE-HT-192MCM-047 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103186 | CB-FE-HT-192MCM-095 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103187 | CB-FE-HT-192MCM-063 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103188 | CB-FE-HT-192MCM-062 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103190 | CB-FE-HT-192MCM-119 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103191 | CB-FE-HT-192MCM-105 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103192 | CB-FE-HT-192MCM-083 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 11 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103193 | CB-FE-HT-192MCM-077 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103194 | CB-FE-HT-192MCM-135 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103195 | CB-FE-HT-192MCM-059 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103196 | CB-FE-HT-192MCM-123 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103197 | CB-FE-HT-192MCM-113 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103198 | CB-FE-HT-192MCM-099 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103199 | CB-FE-HT-192MCM-064 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103200 | CB-FE-HT-192MCM-129 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103201 | CB-FE-HT-192MCM-117 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103203 | CB-FE-HT-192MCM-040 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105726 | CB-FE-HT-192MCM-036 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105727 | CB-FE-HT-192MCM-143 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105728 | CB-FE-HT-192MCM-115 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105729 | CB-FE-HT-192MCM-125 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105733 | CB-FE-HT-192MCM-137 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105737 | CB-FE-HT-192MCM-121 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105739 | CB-FE-HT-192MCM-027 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105740 | CB-FE-HT-192MCM-140 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105741 | CB-FE-HT-192MCM-109 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106818 | CB-FE-HT-192MCM-155 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106822 | CB-FE-HT-192MCM-167 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106826 | CB-FE-HT-192MCM-072 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106836 | CB-FE-HT-192MCM-030 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106841 | CB-FE-HT-192MCM-147 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106842 | CB-FE-HT-192MCM-145 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106843 | CB-FE-HT-192MCM-153 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106846 | CB-FE-HT-192MCM-151 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106853 | CB-FE-HT-192MCM-161 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106860 | CB-FE-HT-192MCM-179 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106867 | CB-FE-HT-192MCM-173 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-108723 | CB-FE-HT-192MCM-024 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-18 | 123 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-108726 | CB-FE-HT-192MCM-042 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-108727 | CB-FE-HT-192MCM-054 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-108728 | CB-FE-HT-192MCM-088 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-108729 | CB-FE-HT-192MCM-018 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-108732 | CB-FE-HT-192MCM-066 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-18 | 2026-10-19 | 124 |  | 0 | 1 | Upcoming
Fiber - Fanout - OFNR - 24f | 23-101499 | MB24SHF1ESS3300F20 | 70001776859 | RPL6 | MLX ELECTRONICS HOLDING LP | 2026-10-18 | 2026-11-04 | 140 |  | 0 | 1920 | Upcoming
Fiber - Fanout - OFNR - 24f | 23-101499 | MB24SHF1ESS3300F20 | 70001776859 | RPL6 | MLX ELECTRONICS HOLDING LP | 2026-10-18 | 2026-11-04 | 140 |  | 0 | 1920 | Upcoming
Fiber - Fanout - OFNR - 24f | 23-101499 | MB24SHF1ESS3300F20 | 70001776859 | RPL6 | MLX ELECTRONICS HOLDING LP | 2026-10-18 | 2026-11-04 | 140 |  | 0 | 1920 | Upcoming
Fiber - Fanout - OFNR - 24f | 23-101499 | MB24SHF1ESS3300F20 | 70001776859 | RPL6 | MLX ELECTRONICS HOLDING LP | 2026-10-18 | 2026-11-04 | 140 |  | 0 | 1920 | Upcoming
Hardware - FAP | 23-101185 | MC-1RUC-4X-LC-APS-B-01 | 70001776861 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-10-18 |  |  |  | 0 | 1360 | Upcoming
Hardware - FAP | 23-107113 | MC-10IN1RU-FAPB-2P-MMC-01 | 70001776861 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-10-18 |  |  |  | 0 | 1584 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109306 | MTA-PT3456WR1-M3050 | 70001758007 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-10-22 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109286 | TA-3456-MM24P0-SMROIM-3000 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-10-22 | 2026-10-21 | 126 |  | 0 | 6 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109306 | CB-ZZ-PT-3456MCMA-3050 | 70001776881 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-10-22 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109286 | TA-3456-MM24P0-SMROIM-3000 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-01 | 2026-11-21 | 157 |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109306 | TA-3456-MM24P0-SMROIM-3050 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-01 | 2026-11-21 | 157 |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109307 | MTA-PT3456WR1-M2950 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-11-01 |  |  |  | 0 | 3 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109187 | TAT-3456-MM24PMM24P-A2J-320 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-07 | 2026-11-21 | 157 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109187 | TAT-3456-MM24PMM24P-A2J-320 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-07 | 2026-11-21 | 157 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109189 | TAT-3456-MM24PMM24P-A2J-328 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-07 | 2026-11-21 | 157 |  | 0 | 2 | Upcoming
| 23-112428 | TAT-3456-MM24PMM24P-A2J-412 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-109246 | TAT-3456-MM24PMM24P-A2J-368 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-07 | 2026-11-21 | 157 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111809 | TAT-3456-MM24PMM24P-A2J-443 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-07 | 2026-11-21 | 157 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112128 | TAT-3456-MM24PMM24P-A2J-369 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-07 | 2026-11-21 | 157 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112093 | CB-ZZ-HT-3456MCM-420 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-11-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112138 | CB-ZZ-HT-3456MCM-413 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-11-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109286 | TA-3456-MM24P0-SMROIM-3000 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-08 | 2026-11-21 | 157 |  | 0 | 3 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109307 | MTA-PT3456WR1-M2950 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-11-08 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109290 | TA-3456-MM24P0-SMROIM-3350 | 70001733313 | RPL-6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-08 | 2026-11-19 | 155 |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109290 | MTA-PT3456WR1-M3350 | 70001758010 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-11-15 |  |  |  | 0 | 4 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109307 | MTA-PT3456WR1-M2950 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-11-15 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109290 | TA-3456-MM24P0-SMROIM-3350 | 70001733313 | RPL-6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-11-15 | 2026-11-19 | 155 |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109290 | MTA-PT3456WR1-M3350 | 70001758010 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-11-22 |  |  |  | 0 | 7 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109307 | MTA-PT3456WR1-M2950 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-11-22 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109290 | MTA-PT3456WR1-M3350 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-12-01 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109316 | MTA-PT3456WR1-M3300 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-12-01 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103702 | CB-FE-HT-288MCM-034 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103704 | CB-FE-HT-288MCM-029 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 32 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103705 | CB-FE-HT-288MCM-037 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103706 | CB-FE-HT-288MCM-035 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103707 | CB-FE-HT-288MCM-039 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103708 | CB-FE-HT-288MCM-040 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103709 | CB-FE-HT-288MCM-033 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103710 | CB-FE-HT-288MCM-028 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103712 | CB-FE-HT-288MCM-022 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103714 | CB-FE-HT-288MCM-031 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103715 | CB-FE-HT-288MCM-021 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103716 | CB-FE-HT-288MCM-023 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 48 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103717 | CB-FE-HT-288MCM-032 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103718 | CB-FE-HT-288MCM-026 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103720 | CB-FE-HT-288MCM-027 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103721 | CB-FE-HT-288MCM-025 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104213 | CB-FE-HT-288MCM-051 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 32 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104215 | CB-FE-HT-288MCM-052 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104216 | CB-FE-HT-288MCM-056 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104217 | CB-FE-HT-288MCM-053 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 18 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104220 | CB-FE-HT-288MCM-048 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104222 | CB-FE-HT-288MCM-045 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104225 | CB-FE-HT-288MCM-062 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104228 | CB-FE-HT-288MCM-061 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104230 | CB-FE-HT-288MCM-066 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 18 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104231 | CB-FE-HT-288MCM-063 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104235 | CB-FE-HT-288MCM-069 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 22 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104238 | CB-FE-HT-288MCM-044 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 20 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104240 | CB-FE-HT-288MCM-054 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104241 | CB-FE-HT-288MCM-058 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 28 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104242 | CB-FE-HT-288MCM-067 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104243 | CB-FE-HT-288MCM-041 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104244 | CB-FE-HT-288MCM-057 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104246 | CB-FE-HT-288MCM-047 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 32 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104247 | CB-FE-HT-288MCM-055 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 18 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104248 | CB-FE-HT-288MCM-060 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 26 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104252 | CB-FE-HT-288MCM-068 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104253 | CB-FE-HT-288MCM-050 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 24 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104254 | CB-FE-HT-288MCM-049 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 20 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104256 | CB-FE-HT-288MCM-064 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104257 | CB-FE-HT-288MCM-043 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104262 | CB-FE-HT-288MCM-046 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104263 | CB-FE-HT-288MCM-075 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 22 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104264 | CB-FE-HT-288MCM-082 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104266 | CB-FE-HT-288MCM-081 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104268 | CB-FE-HT-288MCM-093 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104269 | CB-FE-HT-288MCM-079 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104273 | CB-FE-HT-288MCM-073 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104279 | CB-FE-HT-288MCM-076 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104281 | CB-FE-HT-288MCM-086 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104283 | CB-FE-HT-288MCM-097 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 22 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104285 | CB-FE-HT-288MCM-080 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104288 | CB-FE-HT-288MCM-094 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104289 | CB-FE-HT-288MCM-092 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104290 | CB-FE-HT-288MCM-085 | 70001776728 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 20 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105383 | CB-FE-ET-288MCFMCM-020 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 192 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105385 | CB-FE-ET-288MCFMCM-014 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 56 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105387 | CB-FE-ET-288MCFMCM-022 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 120 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105392 | CB-FE-ET-288MCFMCM-021 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 184 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105400 | CB-FE-ET-288MCFMCM-018 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 184 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105404 | CB-FE-ET-288MCFMCM-024 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 32 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105405 | CB-FE-ET-288MCFMCM-017 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 192 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105406 | CB-FE-ET-288MCFMCM-019 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 168 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105412 | CB-FE-ET-288MCFMCM-013 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105413 | CB-FE-ET-288MCFMCM-015 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 128 | Upcoming
Fiber - Extender Trunk - OFNR - 288f | 23-105414 | CB-FE-ET-288MCFMCM-016 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 168 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-100753 | CB-FE-ET-384MCFMCM-012 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 136 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-100775 | CB-FE-ET-384MCFMCM-014 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 272 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-103080 | CB-FE-ET-384MCFMCM-013 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 264 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-105742 | CB-FE-ET-384MCFMCM-015 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-105746 | CB-FE-ET-384MCFMCM-011 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 264 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-103697 | CB-FE-ET-192MCFMCM-013 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-103698 | CB-FE-ET-192MCFMCM-015 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 48 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-104499 | CB-FE-ET-192MCFMCM-020 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 64 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-104512 | CB-FE-ET-192MCFMCM-022 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 44 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-104532 | CB-FE-ET-192MCFMCM-019 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 52 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-104538 | CB-FE-ET-192MCFMCM-016 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 52 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-106631 | CB-FE-ET-192MCFMCM-017 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 64 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-106632 | CB-FE-ET-192MCFMCM-018 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 60 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-106636 | CB-FE-ET-192MCFMCM-021 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 60 | Upcoming
Fiber - Extender Trunk - OFNR - 192f | 23-106637 | CB-FE-ET-192MCFMCM-014 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 28 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110570 | CB-FE-HT-288MCM-168 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110608 | CB-FE-HT-288MCM-156 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110609 | CB-FE-HT-288MCM-125 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110619 | CB-FE-HT-288MCM-155 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110623 | CB-FE-HT-288MCM-128 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 18 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110637 | CB-FE-HT-288MCM-148 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 48f | 23-112685 | CB-FE-HT-048MCM-004 | 70001776829 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 384 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-108732 | CB-FE-HT-192MCM-066 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110415 | CB-FE-HT-192MCM-136 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110419 | CB-FE-HT-192MCM-148 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110421 | CB-FE-HT-192MCM-061 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110423 | CB-FE-HT-192MCM-079 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110432 | CB-FE-HT-192MCM-098 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110441 | CB-FE-HT-192MCM-142 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110445 | CB-FE-HT-192MCM-100 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 9 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110450 | CB-FE-HT-192MCM-085 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110454 | CB-FE-HT-192MCM-110 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110461 | CB-FE-HT-192MCM-091 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110464 | CB-FE-HT-192MCM-122 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 11 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110465 | CB-FE-HT-192MCM-067 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110470 | CB-FE-HT-192MCM-160 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110483 | CB-FE-HT-192MCM-138 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110490 | CB-FE-HT-192MCM-055 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110491 | CB-FE-HT-192MCM-116 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110492 | CB-FE-HT-192MCM-073 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110496 | CB-FE-HT-192MCM-104 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-110501 | CB-FE-HT-192MCM-154 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111119 | CB-FE-HT-192MCM-043 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111120 | CB-FE-HT-192MCM-097 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 11 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111121 | CB-FE-HT-192MCM-078 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111122 | CB-FE-HT-192MCM-084 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111125 | CB-FE-HT-192MCM-037 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111127 | CB-FE-HT-192MCM-049 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111128 | CB-FE-HT-192MCM-060 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-111130 | CB-FE-HT-192MCM-087 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112692 | CB-FE-HT-192MCM-150 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112693 | CB-FE-HT-192MCM-134 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112695 | CB-FE-HT-192MCM-118 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112696 | CB-FE-HT-192MCM-128 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 9 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112697 | CB-FE-HT-192MCM-180 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112698 | CB-FE-HT-192MCM-178 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112699 | CB-FE-HT-192MCM-166 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112700 | CB-FE-HT-192MCM-156 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112701 | CB-FE-HT-192MCM-174 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112702 | CB-FE-HT-192MCM-132 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112704 | CB-FE-HT-192MCM-168 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112706 | CB-FE-HT-192MCM-103 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112707 | CB-FE-HT-192MCM-112 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 9 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112708 | CB-FE-HT-192MCM-124 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112711 | CB-FE-HT-192MCM-144 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112712 | CB-FE-HT-192MCM-141 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112713 | CB-FE-HT-192MCM-106 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 11 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112715 | CB-FE-HT-192MCM-172 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112716 | CB-FE-HT-192MCM-162 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112718 | CB-FE-HT-192MCM-131 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 9 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-112721 | CB-FE-HT-192MCM-126 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-101114 | CB-FE-HT-288MCM-005 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 32 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103588 | CB-FE-HT-288MCM-015 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103589 | CB-FE-HT-288MCM-016 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103593 | CB-FE-HT-288MCM-019 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-103594 | CB-FE-HT-288MCM-020 | 70001776839 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104291 | CB-FE-HT-288MCM-091 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 24 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104295 | CB-FE-HT-288MCM-098 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104297 | CB-FE-HT-288MCM-100 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 18 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104298 | CB-FE-HT-288MCM-099 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104299 | CB-FE-HT-288MCM-084 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104300 | CB-FE-HT-288MCM-088 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104301 | CB-FE-HT-288MCM-072 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104302 | CB-FE-HT-288MCM-087 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-104310 | CB-FE-HT-288MCM-078 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105438 | CB-FE-HT-288MCM-150 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105439 | CB-FE-HT-288MCM-123 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105442 | CB-FE-HT-288MCM-111 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105443 | CB-FE-HT-288MCM-122 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 22 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105445 | CB-FE-HT-288MCM-178 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105447 | CB-FE-HT-288MCM-141 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105448 | CB-FE-HT-288MCM-132 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105459 | CB-FE-HT-288MCM-153 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105460 | CB-FE-HT-288MCM-113 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105462 | CB-FE-HT-288MCM-101 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105463 | CB-FE-HT-288MCM-147 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105466 | CB-FE-HT-288MCM-138 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105470 | CB-FE-HT-288MCM-142 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105472 | CB-FE-HT-288MCM-166 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105474 | CB-FE-HT-288MCM-154 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105477 | CB-FE-HT-288MCM-134 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105478 | CB-FE-HT-288MCM-110 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105479 | CB-FE-HT-288MCM-159 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105485 | CB-FE-HT-288MCM-135 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-105486 | CB-FE-HT-288MCM-126 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106767 | CB-FE-HT-288MCM-115 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106771 | CB-FE-HT-288MCM-107 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106773 | CB-FE-HT-288MCM-118 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 14 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106774 | CB-FE-HT-288MCM-144 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106777 | CB-FE-HT-288MCM-104 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106779 | CB-FE-HT-288MCM-116 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 20 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106780 | CB-FE-HT-288MCM-143 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106781 | CB-FE-HT-288MCM-137 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106782 | CB-FE-HT-288MCM-129 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106791 | CB-FE-HT-288MCM-112 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 18 | Upcoming
Fiber - Trunk - OFNR - 288f | 23-106809 | CB-FE-HT-288MCM-103 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-112686 | CB-FE-HT-288MCM-149 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-112691 | CB-FE-HT-288MCM-180 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110251 | CB-FE-HT-288MCM-106 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 22 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110252 | CB-FE-HT-288MCM-109 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 10 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110253 | CB-FE-HT-288MCM-119 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 16 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110254 | CB-FE-HT-288MCM-124 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 12 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110255 | CB-FE-HT-288MCM-131 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 18 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110256 | CB-FE-HT-288MCM-136 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110517 | CB-FE-HT-288MCM-174 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110529 | CB-FE-HT-288MCM-160 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110534 | CB-FE-HT-288MCM-117 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110549 | CB-FE-HT-288MCM-162 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 384f | 23-110565 | CB-FE-HT-288MCM-172 | 70001776841 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102973 | CB-FE-HT-192MCM-094 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102976 | CB-FE-HT-192MCM-092 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102977 | CB-FE-HT-192MCM-080 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102978 | CB-FE-HT-192MCM-069 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 11 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102979 | CB-FE-HT-192MCM-019 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102982 | CB-FE-HT-192MCM-056 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102984 | CB-FE-HT-192MCM-081 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102987 | CB-FE-HT-192MCM-046 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102988 | CB-FE-HT-192MCM-044 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102989 | CB-FE-HT-192MCM-082 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102990 | CB-FE-HT-192MCM-031 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102991 | CB-FE-HT-192MCM-068 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102992 | CB-FE-HT-192MCM-057 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-102993 | CB-FE-HT-192MCM-093 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103174 | CB-FE-HT-192MCM-086 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103175 | CB-FE-HT-192MCM-075 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 11 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103176 | CB-FE-HT-192MCM-052 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103179 | CB-FE-HT-192MCM-111 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103180 | CB-FE-HT-192MCM-107 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103181 | CB-FE-HT-192MCM-101 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103182 | CB-FE-HT-192MCM-076 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103184 | CB-FE-HT-192MCM-047 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103185 | CB-FE-HT-192MCM-034 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 3 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103187 | CB-FE-HT-192MCM-063 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103188 | CB-FE-HT-192MCM-062 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103189 | CB-FE-HT-192MCM-053 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103190 | CB-FE-HT-192MCM-119 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103194 | CB-FE-HT-192MCM-135 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103196 | CB-FE-HT-192MCM-123 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103197 | CB-FE-HT-192MCM-113 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103198 | CB-FE-HT-192MCM-099 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103200 | CB-FE-HT-192MCM-129 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103201 | CB-FE-HT-192MCM-117 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103202 | CB-FE-HT-192MCM-050 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-103203 | CB-FE-HT-192MCM-040 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105727 | CB-FE-HT-192MCM-143 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105728 | CB-FE-HT-192MCM-115 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105729 | CB-FE-HT-192MCM-125 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105733 | CB-FE-HT-192MCM-137 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105736 | CB-FE-HT-192MCM-025 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-105741 | CB-FE-HT-192MCM-109 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 5 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106816 | CB-FE-HT-192MCM-159 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106818 | CB-FE-HT-192MCM-155 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106826 | CB-FE-HT-192MCM-072 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106841 | CB-FE-HT-192MCM-147 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 7 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106843 | CB-FE-HT-192MCM-153 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 6 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106848 | CB-FE-HT-192MCM-149 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 4 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106857 | CB-FE-HT-192MCM-028 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-106870 | CB-FE-HT-192MCM-022 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-108724 | CB-FE-HT-192MCM-041 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 1 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-108727 | CB-FE-HT-192MCM-054 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 2 | Upcoming
Fiber - Trunk - OFNR - 192f | 23-108728 | CB-FE-HT-192MCM-088 | 70001776853 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-01 | 2026-12-01 | 167 |  | 0 | 8 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109290 | TA-3456-MM24P0-SMROIM-3350 | 70001733313 | RPL-6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-12-01 | 2026-12-06 | 172 |  | 0 | 9 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111798 | TAT-3456-MM24PMM24P-A2J-429 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-12-07 | 2026-12-21 | 187 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112067 | TAT-3456-MM24PMM24P-A2J-416 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-12-07 | 2026-12-21 | 187 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112084 | TAT-3456-MM24PMM24P-A2J-395 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-12-07 | 2026-12-21 | 187 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112088 | TAT-3456-MM24PMM24P-A2J-468 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-12-07 | 2026-12-21 | 187 |  | 0 | 1 | Upcoming
| 23-112429 | TAT-3456-MM24PMM24P-A2J-444 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-12-07 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112434 | TAT-3456-MM24PMM24P-A2J-428 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-12-07 | 2026-12-21 | 187 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111794 | CB-ZZ-HT-3456MCM-430 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111798 | CB-ZZ-HT-3456MCM-429 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111968 | CB-ZZ-HT-3456MCM-469 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112083 | CB-ZZ-HT-3456MCM-387 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-07 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112127 | CB-ZZ-HT-3456MCM-403 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112150 | CB-ZZ-HT-3456MCM-415 | 70001776878 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2026-12-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109316 | MTA-PT3456WR1-M3300 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-12-08 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109290 | TA-3456-MM24P0-SMROIM-3350 | 70001733313 | RPL-6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-12-08 | 2026-12-20 | 186 |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109290 | MTA-PT3456WR1-M3350 | 70001758010 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-12-15 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109316 | MTA-PT3456WR1-M3300 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-12-15 |  |  |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor - 3456f | 23-109290 | TA-3456-MM24P0-SMROIM-3350 | 70001733313 | RPL-6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2026-12-15 | 2026-12-17 | 183 |  | 0 | 3 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109290 | MTA-PT3456WR1-M3350 | 70001758010 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-12-22 |  |  |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109316 | MTA-PT3456WR1-M3300 | 70001758368 | RPL6 | AFL TELECOMMUNICATIONS LLC | 2026-12-22 |  |  |  | 0 | 9 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111828 | TAT-3456-MM24PMM24P-A2J-494 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-01-01 | 2027-01-21 | 218 |  | 0 | 1 | Upcoming
| 23-112068 | TAT-3456-MM24PMM24P-A2J-432 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-01-01 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112099 | TAT-3456-MM24PMM24P-A2J-441 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-01-01 | 2027-01-21 | 218 |  | 0 | 1 | Upcoming
| 23-112430 | TAT-3456-MM24PMM24P-A2J-452 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-01-01 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112435 | TAT-3456-MM24PMM24P-A2J-440 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-01-01 | 2027-01-21 | 218 |  | 0 | 1 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109316 | TA-3456-MM24P0-SMROIM-3300 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-01-01 | 2027-01-21 | 218 |  | 0 | 6 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111828 | TAT-3456-MM24PMM24P-A2J-494 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-01-01 | 2027-01-21 | 218 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111793 | CB-ZZ-HT-3456MCM-455 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-01-01 |  |  |  | 0 | 2 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109316 | TA-3456-MM24P0-SMROIM-3300 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-01-08 | 2027-01-21 | 218 |  | 0 | 5 | Upcoming
Fiber - Pigtail - Indoor/Outdoor | 23-109316 | TA-3456-MM24P0-SMROIM-3300 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-01-15 | 2027-01-21 | 218 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112435 | TAT-3456-MM24PMM24P-A2J-440 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-01-22 | 2027-01-21 | 218 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112080 | TAT-3456-MM24PMM24P-A2J-466 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-01-22 | 2027-01-21 | 218 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111966 | CB-ZZ-HT-3456MCM-437 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-01-22 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112427 | CB-ZZ-HT-3456MCM-448 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-01-22 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111965 | TAT-3456-MM24PMM24P-A2J-473 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-02-01 | 2027-02-21 | 249 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111796 | CB-ZZ-HT-3456MCM-481 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-02-01 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111825 | CB-ZZ-HT-3456MCM-519 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-02-01 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112143 | CB-ZZ-HT-3456MCM-480 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-02-01 |  |  |  | 0 | 3 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111965 | CB-ZZ-HT-3456MCM-473 | 70001776878 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-02-01 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111793 | TAT-3456-MM24PMM24P-A2J-455 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-02-22 | 2027-02-21 | 249 |  | 0 | 1 | Upcoming
| 23-111927 | TAT-3456-MM24PMM24P-A2J-491 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-02-22 |  |  |  | 0 | 1 | Upcoming
| 23-111928 | TAT-3456-MM24PMM24P-A2J-462 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-02-22 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112092 | TAT-3456-MM24PMM24P-A2J-544 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-02-22 | 2027-02-21 | 249 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112137 | TAT-3456-MM24PMM24P-A2J-464 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-02-22 | 2027-02-21 | 249 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112140 | TAT-3456-MM24PMM24P-A2J-463 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-02-22 | 2027-02-21 | 249 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112140 | TAT-3456-MM24PMM24P-A2J-463 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-02-22 | 2027-02-21 | 249 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112436 | TAT-3456-MM24PMM24P-A2J-456 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-02-22 | 2027-02-21 | 249 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112437 | TAT-3456-MM24PMM24P-A2J-500 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-02-22 | 2027-02-21 | 249 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-111789 | CB-ZZ-HT-3456MCM-505 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-02-22 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor - 3456f | 23-112438 | CB-ZZ-HT-3456MCM-492 | 70001776870 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-02-22 |  |  |  | 0 | 2 | Upcoming
| 23-112069 | TAT-3456-MM24PMM24P-A2J-570 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-01 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112081 | TAT-3456-MM24PMM24P-A2J-569 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-01 | 2027-03-21 | 277 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111814 | TAT-3456-MM24PMM24P-A2J-531 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-01 | 2027-03-21 | 277 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111832 | TAT-3456-MM24PMM24P-A2J-530 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-01 | 2027-03-21 | 277 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-100775 | CB-FE-ET-384MCFMCM-014 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-03-01 | 2027-03-01 | 257 |  | 0 | 256 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-105746 | CB-FE-ET-384MCFMCM-011 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-03-01 | 2027-03-01 | 257 |  | 0 | 256 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-100775 | CB-FE-ET-384MCFMCM-014 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-03-06 | 2027-03-08 | 264 |  | 0 | 256 | Upcoming
Fiber - Extender Trunk - OFNR - 384f | 23-105746 | CB-FE-ET-384MCFMCM-011 | 70001776816 | RPL6 | CORNING OPTICAL COMMUNICATIONS LLC | 2027-03-06 | 2027-03-08 | 264 |  | 0 | 256 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111941 | TAT-3456-MM24PMM24P-A2J-517 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-07 | 2027-03-21 | 277 |  | 0 | 1 | Upcoming
| 23-112431 | TAT-3456-MM24PMM24P-A2J-516 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-07 |  |  |  | 0 | 1 | Upcoming
| 23-112433 | TAT-3456-MM24PMM24P-A2J-488 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-07 |  |  |  | 0 | 1 | Upcoming
| 23-112433 | TAT-3456-MM24PMM24P-A2J-488 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-07 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111971 | TAT-3456-MM24PMM24P-A2J-487 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-15 | 2027-03-21 | 277 |  | 0 | 1 | Upcoming
| 23-112433 | TAT-3456-MM24PMM24P-A2J-488 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-15 |  |  |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112143 | TAT-3456-MM24PMM24P-A2J-480 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-15 | 2027-03-21 | 277 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112066 | TAT-3456-MM24PMM24P-A2J-512 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-22 | 2027-03-21 | 277 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112124 | TAT-3456-MM24PMM24P-A2J-520 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-22 | 2027-03-21 | 277 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112124 | TAT-3456-MM24PMM24P-A2J-520 | 70001758011 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-03-22 | 2027-03-21 | 277 |  | 0 | 1 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111940 | TAT-3456-MM24PMM24P-A2J-513 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-04-07 | 2027-04-21 | 308 |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-111952 | TAT-3456-MM24PMM24P-A2J-541 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-04-07 | 2027-04-21 | 308 |  | 0 | 1 | Upcoming
| 23-112073 | TAT-3456-MM24PMM24P-A2J-503 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-04-07 |  |  |  | 0 | 2 | Upcoming
| 23-112109 | TAT-3456-MM24PMM24P-A2J-495 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-04-07 |  |  |  | 0 | 2 | Upcoming
Fiber - Trunk - Indoor/Outdoor | 23-112129 | TAT-3456-MM24PMM24P-A2J-542 | 70001758012 | RPL6 | SUMITOMO ELECTRIC LIGHTWAVE CORP | 2027-04-07 | 2027-04-21 | 308 |  | 0 | 1 | Upcoming
Fiber - Extender Trunk - OFNR | 23-106987 | CB-FE-HT-096MCM-210 | 70001631927 | RPL6 | [5 empty] | 0 | 1 | Pending
PDU Basic | 03-000904 | STV-FB118WA | 70001638515 | RPL6 | [5 empty] | 0 | 144 | Pending
Hardware - MBOX | 23-009793 | FB-MB-SM-10N40480U | 70001638516 | RPL6 | [5 empty] | 0 | 48 | Pending
Hardware - FAP | 23-101185 | FB-FC-1RU4X12LC | 70001638516 | RPL6 | [5 empty] | 0 | 208 | Pending
Hardware - OSE | 23-100899 | FB-FC-OSEUHDKIT-FAB | 70001638516 | RPL6 |  |  |  |  | 2026-06-03 | 20 | 20 | Delivered
Hardware - OSE | 23-100900 | FB-FC-WSH96RIB-KIT | 70001638516 | RPL6 | [5 empty] | 0 | 18 | Pending
Fiber - Super Trunk - OFNP | 23-011869 | CB-FB-ST-8SM24098 | 70001638516 | RPL6 | [5 empty] | 0 | 2 | Pending
Fiber - Super Trunk - OFNP | 23-011870 | CB-FB-ST-8SM24108 | 70001638516 | RPL6 | [5 empty] | 0 | 2 | Pending
Fiber - Super Trunk - OFNP | 23-011872 | CB-FB-ST-8SM24118 | 70001638516 | RPL6 | [5 empty] | 0 | 2 | Pending
Fiber - Super Trunk - OFNP | 23-011876 | CB-FB-ST-8SM24128 | 70001638516 | RPL6 | [5 empty] | 0 | 2 | Pending
Fiber - Trunk - OFNP | 23-012516 | CB-FB-ST-8SM24213 | 70001638516 | RPL6 | [5 empty] | 0 | 4 | Pending
Fiber - Super Trunk - OFNP | 23-012523 | CB-FB-ST-8SM24248 | 70001638516 | RPL6 | [5 empty] | 0 | 5 | Pending
Fiber - Super Trunk - OFNP | 23-012524 | CB-FB-ST-8SM24253 | 70001638516 | RPL6 | [5 empty] | 0 | 1 | Pending
Fiber - Super Trunk - OFNP | 23-012525 | CB-FB-ST-8SM24258 | 70001638516 | RPL6 | [5 empty] | 0 | 2 | Pending
Fiber - Super Trunk - OFNP | 23-012527 | CB-FB-ST-8SM24268 | 70001638516 | RPL6 | [5 empty] | 0 | 2 | Pending
Fiber - Super Trunk - OFNP | 23-012529 | CB-FB-ST-8SM24278 | 70001638516 | RPL6 | [5 empty] | 0 | 2 | Pending
Fiber - Trunk - OFNP | 23-012544 | CB-FB-ST-8SM24353 | 70001638516 | RPL6 | [5 empty] | 0 | 4 | Pending
Fiber - Trunk - OFNP | 23-012551 | CB-FB-ST-8SM24388 | 70001638516 | RPL6 | [5 empty] | 0 | 4 | Pending
Hardware - MBOX | 23-009793 | FB-MB-SM-10N40480U | 70001678964 | RPL7 | [5 empty] | 0 | 48 | Pending
Fiber - Pigtail - OFNP | 23-013638 | CB-PT-192SMPLRS035 | 70001678964 | RPL7 | [5 empty] | 0 | 8 | Pending
Fiber - Blunt - OSP | 23-014491 | GCYFY-192B6a1 | 70001678965 | RPL7 | [5 empty] | 0 | 14854 | Pending
PDU Basic | 03-000904 | STV-FB118WA | 70001678966 | RPL7 | [5 empty] | 0 | 144 | Pending
Fiber - Blunt - OSP | 23-019182 | CB-FB-96SMOSP1 | 70001457473 | RPL10 | [5 empty] | 0 | 6000 | Pending
Hardware - OSE | 23-100899 | FB-FC-OSEUHDKIT-FAB | 70001457473 | RPL10 | [5 empty] | 0 | 2 | Pending
Hardware - OSE | 23-100899 | FB-FC-OSEUHDKIT-FAB | 70001457473 | RPL10 | [5 empty] | 0 | 2 | Pending
Hardware - OSE | 23-100899 | FB-FC-OSEUHDKIT-FAB | 70001457473 | RPL10 | [5 empty] | 0 | 4 | Pending
Hardware - OSE | 23-100899 | FB-FC-OSEUHDKIT-FAB | 70001457473 | RPL10 | [5 empty] | 0 | 32 | Pending
Hardware - OSE | 23-100900 | FB-FC-WSH96RIB-KIT | 70001457473 | RPL10 | [5 empty] | 0 | 3 | Pending
Hardware - OSE | 23-100900 | FB-FC-WSH96RIB-KIT | 70001457473 | RPL10 | [5 empty] | 0 | 3 | Pending
Hardware - OSE | 23-100900 | FB-FC-WSH96RIB-KIT | 70001457473 | RPL10 | [5 empty] | 0 | 2 | Pending
Hardware - OSE | 23-100900 | FB-FC-WSH96RIB-KIT | 70001457473 | RPL10 | [5 empty] | 0 | 56 | Pending
Hardware - FAP | 23-101185 | FB-FC-1RU4X12LC | 70001457473 | RPL10 | [5 empty] | 0 | 8 | Pending
Hardware - FAP | 23-101185 | FB-FC-1RU4X12LC | 70001457473 | RPL10 | [5 empty] | 0 | 40 | Pending
Hardware - FAP | 23-101185 | FB-FC-1RU4X12LC | 70001457473 | RPL10 | [5 empty] | 0 | 32 | Pending
Hardware - FAP | 23-101185 | FB-FC-1RU4X12LC | 70001457473 | RPL10 | [5 empty] | 0 | 8 | Pending
Hardware - FAP | 23-101185 | FB-FC-1RU4X12LC | 70001457473 | RPL10 | [5 empty] | 0 | 8 | Pending
Hardware - FAP | 23-101185 | FB-FC-1RU4X12LC | 70001457473 | RPL10 | [5 empty] | 0 | 550 | Pending
Hardware - FAP | 23-101185 | FB-FC-1RU4X12LC | 70001457473 | RPL10 | [5 empty] | 0 | 128 | Pending
Fiber - Patch Cord - OFNR | 23-103370 | CB-FB-SM2LCU075 | 70001457473 | RPL10 | [5 empty] | 0 | 48 | Pending
Fiber - Pigtail - OFNP | 23-013744 | CB-PT-96SMPLRS025 | 70001457473 | RPL10 | [5 empty] | 0 | 126 | Pending
Fiber - Pigtail - OFNP | 23-013744 | CB-PT-96SMPLRS025 | 70001457473 | RPL10 | [5 empty] | 0 | 1 | Pending
Fiber - Pigtail - OFNP | 23-013743 | CB-PT-96SMPLRS020 | 70001457473 | RPL10 | [5 empty] | 0 | 4 | Pending
Fiber - Pigtail - OFNP | 23-013743 | CB-PT-96SMPLRS020 | 70001457473 | RPL10 | [5 empty] | 0 | 2 | Pending
Fiber - Pigtail - OFNP | 23-013743 | CB-PT-96SMPLRS020 | 70001457473 | RPL10 | [5 empty] | 0 | 18 | Pending
Fiber - Pigtail - OFNP | 23-013747 | CB-PT-96SMPLRS040 | 70001457473 | RPL10 | [5 empty] | 0 | 1 | Pending
Fiber - Pigtail - OFNP | 23-100605 | CB-PT-96SMPLRS015 | 70001457473 | RPL10 | [5 empty] | 0 | 2 | Pending
Fiber - Pigtail - OFNP | 23-013635 | CB-PT-192SMPLRS020 | 70001457473 | RPL10 |  |  |  |  | 2026-06-09 | 57 | 57 | Delivered
Fiber - Pigtail - OFNP | 23-013635 | CB-PT-192SMPLRS020 | 70001457473 | RPL10 | [5 empty] | 0 | 12 | Pending
Fiber - Pigtail - OFNP | 23-013634 | CB-PT-192SMPLRS015 | 70001457473 | RPL10 | [5 empty] | 0 | 2 | Pending
Fiber - Pigtail - OFNP | 23-013634 | CB-PT-192SMPLRS015 | 70001457473 | RPL10 | [5 empty] | 0 | 2 | Pending
Fiber - Pigtail - OFNP | 23-013634 | CB-PT-192SMPLRS015 | 70001457473 | RPL10 | [5 empty] | 0 | 2 | Pending
Fiber - Pigtail - OFNP | 23-013634 | CB-PT-192SMPLRS015 | 70001457473 | RPL10 |  |  |  |  | 2026-05-22 | 2 | 2 | Delivered
Fiber - Pigtail - OFNP | 23-013634 | CB-PT-192SMPLRS015 | 70001457473 | RPL10 |  |  |  |  | 2026-05-22 | 67 | 67 | Delivered
Fiber - Pigtail - OFNP | 23-101384 | CB-PT-48SMPL020 | 70001457473 | RPL10 | [5 empty] | 0 | 4 | Pending
Fiber - Pigtail - OFNP | 23-101384 | CB-PT-48SMPL020 | 70001457473 | RPL10 | [5 empty] | 0 | 4 | Pending
Fiber - Pigtail - OFNP | 23-101384 | CB-PT-48SMPL020 | 70001457473 | RPL10 | [5 empty] | 0 | 1 | Pending
Fiber - Extender Trunk - OFNP | 23-012557 | CB-FB-ST-4SM24218 | 70001457473 | RPL10 | [5 empty] | 0 | 2 | Pending
Fiber - Blunt - OSP | 23-107025 | 048ZM4-T4E49A20 | 70001491817 | RPL10 | [5 empty] | 0 | 6000 | Pending
Fiber - Blunt - OSP | 23-107025 | 048ZM4-T4E49A20 | 70001491817 | RPL10 | [5 empty] | 0 | 6000 | Pending
Fiber - Blunt - OSP | 23-014491 | 192ZH4-Y4C49A20 | 70001528552 | RPL10 | [5 empty] | 0 | 6000 | Pending
Fiber - Blunt - OSP | 23-014491 | 192ZH4-Y4C49A20 | 70001528552 | RPL10 | [5 empty] | 0 | 6000 | Pending
Fiber - Blunt - OSP | 23-014491 | 192ZH4-Y4C49A20 | 70001528552 | RPL10 | [5 empty] | 0 | 6000 | Pending
Fiber - Trunk - OFNR | 23-104261 | CB-FE-HT-096MCM-022 | 70001631929 | RPL10 | [5 empty] | 0 | 2 | Pending